## Sheet1
A/C | Type | Event/Description | Dimension（日期单位 | To go（还剩多少时间 | Due at | Expected（同一单位日期 | Planned（组合工包之后的初始plan | Workpackage | Interval | P | Yield | EstMH (All) | Rotable | Remarks左右engines
B-LAE | D | EO-AOT-A32N033-24-1/REPETITIVE INSPECTION OF AFFECTED MLG DOOR ACTUATORS PN 114122015 | D | 2 | 29.Oct.2025 | 2025-10-29 |  | 0 | 8 D | 1 | 75 | 0.0625 | 114122015 / TA2004697 | OPS INFO: if replacement cannot be perform , please arrange this
B-LAE | D | EO-AOT-A32N033-24-1/REPETITIVE INSPECTION OF AFFECTED MLG DOOR ACTUATORS PN 114122015 | D | 2 | 29.Oct.2025 | 2025-10-29 |  | 0 | 8 D | 1 | 75 | 0.0625 | 114122015 / TA2005298 | OPS INFO: if replacement cannot be perform , please arrange this
B-LAC | Q | HE32-381000-01-1 (R0002)/P60306 / DISINFECTION OF POTABLE WATER SYSTEM AND DISCARD THE WATER FILTER ELEMENTS, IF INSTALL | D | 3 | 30.Oct.2025 | 2025-10-30 | 2025-10-29 | B-LAC-PLN-261025-LM | 91 D | 1 | 99 | 0.29722 |  | MUST DO
B-LAB | D | EOI-49-0004/W1681523 /P60459 /[131-9A] APU VISUAL INSPECTION AND OIL SERVICE | D | 4 | 31.Oct.2025 | 2025-10-31 | 2025-10-28 | B-LAB-PLN-281025-LM1 | 40 D | 2 | 92 | 0.065972 | 3800708-1 / P-7003
B-LAB | Q | HE32-383100-06-1 (R0004) / CLEAN THE VACUUM WASTE LINES WITH CHEMICAL CLEANING AGENT AND CRUSHED ICE | H | 43:52 | 12454:15飞机航行时间12454h到期 | 2025-10-31 | 2025-10-28 | B-LAB-PLN-281025-LM1 | 150 | 1 | 82 | 0.070833
B-LAE | Q | HE32-383100-06-1 (R0004) / CLEAN THE VACUUM WASTE LINES WITH CHEMICAL CLEANING AGENT AND CRUSHED ICE | H | 50:35 | 9126:54 | 2025-10-31 | 2025-10-27 | B-LAE-PLN-301025-LM | 150 | 1 | 71 | 0.070833
B-LAA | Q | HE32-383100-06-1 (R0004)/P60680 / CLEAN THE VACUUM WASTE LINES WITH CHEMICAL CLEANING AGENT AND CRUSHED ICE | H | 49:45 | 15486:19 | 2025-10-31 | 2025-10-28 | B-LAA-PLN-201025-LM | 150 | 1 | 77 | 0.070833
B-LAD | Q | HE32-242400-01-2 (R0004) / OPERATIONAL CHECK OF EMERGENCY GENERATING SYSTEM | H | 57:34 | 9990:31 | 2025-11-01 | 2025-10-28 | B-LAD-PLN-311025-LM | 120 | 1 | 66 | 0.034722
B-LAC | Q | HE32-242400-01-2 (R0004) / OPERATIONAL CHECK OF EMERGENCY GENERATING SYSTEM | H | 65:49 | 8094:21 | 2025-11-01 | 2025-10-28 | B-LAC-PLN-201025-LM1 | 120 | 1 | 65 | 0.034722
B-LAE | Q | HE32-279000-05-1 (R0003) / OPERATIONAL CHECK OF LOGICS ACTIVATING ELAC 1, ELAC 2 AND SEC.1 STANDBY POWER SUPPLIES | H | 69:18 | 9145:37 | 2025-11-02 | 2025-10-27 | B-LAE-PLN-301025-LM | 400 | 1 | 85 | 0.054861
B-LAA | Q | HE32-242400-01-2 (R0004) / OPERATIONAL CHECK OF EMERGENCY GENERATING SYSTEM | H | 88:40 | 15525:14 | 2025-11-03 | 2025-11-01 | B-LAA- PLN-031125-LM | 120 | 1 | 81 | 0.034722
B-LAE | Q | HE32-242000-23-1-01 (R0005)/P60264 / DISCARD NO.1 IDG SCAVENGE AND CHARGE FILTERS, DRAIN AND REPLENISH OIL SYSTEM | H | 91:19 | 9167:38 | 2025-11-04 | 2025-10-27 | B-LAE-PLN-301025-LM | 800 | 1 | 90 | 0.13542
B-LAE | D | EOI-49-0004/W1684940 /P60499 /[131-9A] APU VISUAL INSPECTION AND OIL SERVICE | D | 9 | 05.Nov.2025 | 2025-11-05 | 2025-10-27 | B-LAE-PLN-301025-LM | 40 D | 2 | 78 | 0.065972 | 3800708-1 / P-9078
B-LAA | Q | HE32-242000-23-1-01 (R0005)/P60314 / DISCARD NO.1 IDG SCAVENGE AND CHARGE FILTERS, DRAIN AND REPLENISH OIL SYSTEM | H | 106:09 | 15542:43 | 2025-11-05 | 2025-10-28 | B-LAA-PLN-201025-LM | 800 | 1 | 89 | 0.13542
B-LAE | Q | HE32-242400-01-2 (R0004) / OPERATIONAL CHECK OF EMERGENCY GENERATING SYSTEM | H | 97:15 | 9173:34 | 2025-11-05 | 2025-11-02 | B-LAE-PLN-021125-LM | 120 | 1 | 78 | 0.034722
B-LAA | Q | HE32-272400-01-1 (R0004) / OPERATIONAL CHECK OF RUDDER SERVOCONTROLS WITH INDIVIDUAL HYDRAULIC SYSTEMS | H | 108:35 | 15545:09 | 2025-11-05 | 2025-10-28 | B-LAA-PLN-201025-LM | 750 | 1 | 88 | 0.020833
B-LAA | Q | HE32-279000-05-1 (R0003) / OPERATIONAL CHECK OF LOGICS ACTIVATING ELAC 1, ELAC 2 AND SEC.1 STANDBY POWER SUPPLIES | H | 101:28 | 15538:02 | 2025-11-05 | 2025-10-31 | B-LAA-PLN-271025-LM | 400 | 1 | 89 | 0.054861
B-LAB | Q | HE32-242400-01-2 (R0004) / OPERATIONAL CHECK OF EMERGENCY GENERATING SYSTEM | H | 108:41 | 12519:04 | 2025-11-06 | 2025-11-03 | B-LAB-PLN-100326-LM | 120 | 1 | 78 | 0.034722
B-LAC | Q | HE32-383100-06-1 (R0004) / CLEAN THE VACUUM WASTE LINES WITH CHEMICAL CLEANING AGENT AND CRUSHED ICE | H | 117:23 | 8145:55 | 2025-11-06 | 2025-11-04 | B-LAC-PLN-310327-LM | 150 | 1 | 88 | 0.070833
B-LAE | D | EO-PW-79-0034/W1583812 /P60498 /REPETITIVE INSPECTION AND TORQUE CHECK OF THE MGB AND AGB TUBE BOSS | H | 125:32 | 9201:51 | 2025-11-07 | 2025-11-04 | B-LAE-PLN-291025-LM1 | 1'500 | 3 | 98 | 0.22917 | PW1127GA-JM / P772226 | RH ENG
B-LAD | Q | HE32-291000-14-1 (R0003) / CHECK NITROGEN CHARGE PRESSURE ON HYDRAULIC POWER ACCUMULATORS | H | 126:05 | 10059:02 | 2025-11-07 | 2025-11-01 | B-LAD-PLN-311225-LM | 600 | 1 | 89 | 0.030556
B-LAD | Q | HE32-383100-06-1 (R0004) / CLEAN THE VACUUM WASTE LINES WITH CHEMICAL CLEANING AGENT AND CRUSHED ICE | H | 125:24 | 10058:21 | 2025-11-07 | 2025-11-05 | B-LAD-PLN-071125-LM | 150 | 1 | 85 | 0.070833
B-LAD | V | REPLACE 416526/202200358/W1548018 (BATTERY) | H | 126:13 | 10059:10 | 2025-11-07 | 2025-10-24 | B-LAD-PLN-141025-LM1 |  | 2 |  | 0.0875 | 416526 / 202200358
B-LAA | D | EOI-49-0004/W1685560 /[131-9A] APU VISUAL INSPECTION AND OIL SERVICE | D | 12 | 08.Nov.2025 | 2025-11-08 | 2025-11-05 | B-LAA-PLN-051125-LM | 40 D | 2 | 92 | 0.065972 | 3800708-1 / P-5514
B-LAD | D | EOI-49-0004/W1685618 /[131-9A] APU VISUAL INSPECTION AND OIL SERVICE | D | 12 | 08.Nov.2025 | 2025-11-08 | 2025-11-01 | B-LAD-PLN-311225-LM | 40 D | 2 | 82 | 0.065972 | 3800708-1 / P-8927
B-LAE | Q | 18903 (0) / B-LAE/RI-LM/BDD013/#2 ENG COMBUSTION CHAMBER FOUND CRACK | H | 143:29 | 9219:48 | 2025-11-09 | 2025-11-04 | B-LAE-PLN-281025-LM | 375 | 1 | 85 | 0.083333 |  | OPS INFO: Assign with HE32-724000-W2-1
B-LAE | Q | 18907 (0) / B-LAE/RI-LM/BDD015/#2 ENG COMBUSTION CHAMBER FOUND CRACK | H | 143:29 | 9219:48 | 2025-11-09 | 2025-11-04 | B-LAE-PLN-281025-LM | 375 | 1 | 85 | 0.083333 |  | OPS INFO: Assign with HE32-724000-W2-1
B-LAE | Q | 18909 (0) / B-LAE/RI-LM/BDD016/#2 ENG COMBUSTION CHAMBER FOUND CRACK | H | 143:29 | 9219:48 | 2025-11-09 | 2025-11-04 | B-LAE-PLN-281025-LM | 375 | 1 | 85 | 0.083333 |  | OPS INFO: Assign with HE32-724000-W2-1
B-LAE | Q | 19101 (0) / B-LAE/BDD018/ ENG#2 COMB CHAMBER REAR OUTER LINER SEG BURN | H | 142:41 | 9219:00 | 2025-11-09 | 2025-11-04 | B-LAE-PLN-281025-LM | Before 9'219 | 1 | 100 |  |  | OPS INFO: Assign with HE32-724000-W2-1
B-LAE | Q | B-LAE/BDD009/RI-LM/#2ENG CC BSI (0) / B-LAE/BDD009/RI-LM/#2ENG COMUSTION CHAMBER BSI | H | 143:29 | 9219:48 | 2025-11-09 | 2025-11-04 | B-LAE-PLN-281025-LM | 375 | 1 | 85 | 0.041667 |  | Assign with HE32-724000-W2-1
B-LAE | Q | B-LAE/BDD010/RI-LM/#2ENG 772226 CC BSI (0) / B-LAE/BDD010/RI-LM/#2ENG 772226 COMBUSTION CHAMBER BSI | H | 143:29 | 9219:48 | 2025-11-09 | 2025-11-04 | B-LAE-PLN-281025-LM | 375 | 1 | 85 | 0.041667 |  | Assign with HE32-724000-W2-1
B-LAB | D | EO-PW-73-0020/W1563969 /P60521 /REPETITIVE REPLACEMENT OF THE MAIN FUEL FILTER (PW1100G) | H | 144:50 | 12555:13 | 2025-11-09 | 2025-10-30 | B-LAB-PLN-051125-LM | 1'700 | 3 | 94 | 0.16667 | PW1127GA-JM / P770214 | EOE: DO NOT replace fuel filters on both engine in the same ground
B-LAA | D | EO-A320-56-1023/W1543224 /WINDOWS - FIXED WINDOWS - INSPECTION OF FRONT WINDSHIELD | D | 14 | 10.Nov.2025 | 2025-11-10 | 2025-11-01 | B-LAA-PLN-7.5K_2025 | 730 D | 1 | 99 | 0.13542 | STA320-2-8-2 / 23184
B-LAA | D | EOA32-24-0016/W1400311 /APPLY TEMPORARY PROTECTION TO END FITTINGS OF A32 SERIES AIRCRAFT OF E | D | 14 | 10.Nov.2025 | 2025-11-10 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 | 36 MT | 2 | 100 | 0.055556 |  | EOE: Plan with HE32-ZL-575-01-1 with standard C CHK package
B-LAA | Q | HE32-200435-02-1-01 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE FAN COMPARTMENT OF NO.1 ENG (EWIS) | D | 14 | 10.Nov.2025 | 2025-11-10 | 2025-11-01 | B-LAA-PLN-7.5K_2025 | 730 D | 1 | 99 | 0.027778
B-LAA | Q | HE32-200435-02-1-02 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE FAN COMPARTMENT OF NO.2 ENG (EWIS) | D | 14 | 10.Nov.2025 | 2025-11-10 | 2025-11-01 | B-LAA-PLN-7.5K_2025 | 730 D | 1 | 99 | 0.027778
B-LAA | Q | HE32-200453-02-1-01 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE CORE COMPARTMENT OF NO.1 ENG (EWIS) | D | 14 | 10.Nov.2025 | 2025-11-10 | 2025-11-01 | B-LAA-PLN-7.5K_2025 | 730 D | 1 | 99 | 0.05
B-LAA | Q | HE32-200453-02-1-02 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE CORE COMPARTMENT OF NO.2 ENG (EWIS) | D | 14 | 10.Nov.2025 | 2025-11-10 | 2025-11-01 | B-LAA-PLN-7.5K_2025 | 730 D | 1 | 99 | 0.05
B-LAA | Q | HE32-291000-25-1 (R0001) / OPERATIONAL CHECK OF PORT D CHECK VALVE OF PTU MANIFOLD IN GREEN AND YELLOW HYDRAULIC SYSTEM | D | 14 | 10.Nov.2025 | 2025-11-10 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 1 |  | 0.22917 |  | MR info: AMS I5R0 Bridging applied. Do not defer this task.
B-LAA | Q | HE32-ZL-435-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF FAN COMPARTMENT OF NO.1 ENG (EWIS) | D | 14 | 10.Nov.2025 | 2025-11-10 | 2025-11-01 | B-LAA-PLN-7.5K_2025 | 730 D | 1 | 99 | 0.017361
B-LAA | Q | HE32-ZL-435-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF FAN COMPARTMENT OF NO.2 ENG (EWIS) | D | 14 | 10.Nov.2025 | 2025-11-10 | 2025-11-01 | B-LAA-PLN-7.5K_2025 | 730 D | 1 | 99 | 0.017361
B-LAA | D | EO-PW-72-0193/W1614618 /TUBE ASSEMBLY; OIL; NO. 4 BEARING(LR111); SCAVENGE - EXAMINE THE NO. 4 | H | 184:33 | 15621:07 | 2025-11-12 | 2025-10-31 | B-LAA-PLN-271025-LM | 1'000 | 2 | 87 | 0.090278 | PW1127GA-JM / P770440
B-LAE | Q | 15703 (0) / B-LAE/BDD012/RI-LM/#2 ENG (P772226) HPT STG1 T/E BLADES INSP | H | 196:15 | 9269:51 | 2025-11-13 | 2025-11-04 | B-LAE-PLN-041125-LM | 675 | 1 | 85 |  |  | Assign with HE32-725100-W1
B-LAE | Q | B-LAE/BDD011/RI-LM/#2 ENG HPT BLADE INSP (0) / B-LAE/BDD011/RI-LM/#2 ENG (P772226) HPT STG1 T/E BLADES INSP | H | 196:15 | 9269:51 | 2025-11-13 | 2025-11-04 | B-LAE-PLN-041125-LM | 675 | 1 | 85 | 0.041667 |  | Assign with HE32-725100-W1-1
B-LAE | Q | HE32-242000-23-1-02 (R0005) / DISCARD NO.2 IDG SCAVENGE AND CHARGE FILTERS, DRAIN AND REPLENISH OIL SYSTEM | H | 196:54 | 9270:30 | 2025-11-13 | 2025-11-06 | B-LAE-PLN-051125-LM | 800 | 1 | 91 | 0.13542
B-LAE | D | EO-PW-79-0034/W1587604 /REPETITIVE INSPECTION AND TORQUE CHECK OF THE MGB AND AGB TUBE BOSS | H | 202:58 | 9276:34 | 2025-11-14 | 2025-11-06 | B-LAE-PLN-291025-LM | 1'500 | 3 | 95 | 0.22917 | PW1127GA-JM / P772225 | LH ENG
B-LAA | D | EO-PW-79-0034/W1588427 /REPETITIVE INSPECTION AND TORQUE CHECK OF THE MGB AND AGB TUBE BOSS | H | 223:34 | 15660:08 | 2025-11-16 |  | 0 | 1'500 | 3 | 85 | 0.22917 | PW1127GA-JM / P771230 | LH ENG
B-LAB | D | EOI-79-0001/W1690464 /DO A REPETITIVE INSPECTION AND TORQUE CHECK OF | C | 80 | 4'637 | 2025-11-16 |  | 0 | 150 | 2 | 46 | 0.1875 | PW1127GA-JM / P770214 | LH ENG
B-LAA | Q | HE32-381000-01-1 (R0002) / DISINFECTION OF POTABLE WATER SYSTEM AND DISCARD THE WATER FILTER ELEMENTS, IF INSTALLED | D | 20 | 16.Nov.2025 | 2025-11-16 | 2025-11-11 | B-LAA-PLN-111125-LM1 | 91 D | 1 | 95 | 0.29722
B-LAE | Q | 18905 (0) / B-LAE/RI-LM/BDD014/#2 ENG COMBUSTION CHAMBER FOUND CRACK | H | 234:13 | 9307:49 | 2025-11-17 | 2025-11-04 | B-LAE-PLN-281025-LM | 750 | 1 | 81 | 0.083333 |  | OPS INFO: Assign with HE32-724000-W2-1
B-LAE | D | EO-PW-72-0193/W1618476 /TUBE ASSEMBLY; OIL; NO. 4 BEARING(LR111); SCAVENGE - EXAMINE THE NO. 4 | H | 237:40 | 9311:16 | 2025-11-17 | 2025-11-14 | B-LAE-PLN-171125-LM | 1'000 | 2 | 97 | 0.090278 | PW1127GA-JM / P772225
B-LAC | Q | HE32-291000-14-1 (R0003) / CHECK NITROGEN CHARGE PRESSURE ON HYDRAULIC POWER ACCUMULATORS | H | 233:02 | 8261:34 | 2025-11-17 | 2025-11-12 | B-LAC-PLN-081125-LM | 600 | 1 | 92 | 0.030556
B-LAC | D | EOI-49-0004/W1690469 /[131-9A] APU VISUAL INSPECTION AND OIL SERVICE | D | 22 | 18.Nov.2025 | 2025-11-18 | 2025-11-12 | B-LAC-PLN-081125-LM | 40 D | 2 | 85 | 0.065972 | 3800708-1 / P-7062
B-LAC | Q | HE32-279000-05-1 (R0003) / OPERATIONAL CHECK OF LOGICS ACTIVATING ELAC 1, ELAC 2 AND SEC.1 STANDBY POWER SUPPLIES | H | 251:24 | 8279:56 | 2025-11-19 | 2025-11-12 | B-LAC-PLN-081125-LM | 400 | 1 | 84 | 0.054861
B-LAD | Q | B-LAD/BDD010/LM-RI/RH WING NO.1 SLAT DENT INSP (0) / B-LAD/BDD010/LM-RI/RH WING NO.1 SLAT OUTBOARD SIDE DENT INSP | H | 278:57 | 10209:02 | 2025-11-21 |  | 0 | 750 | 1 | 62 | 0.034722
B-LAB | D | EOI-72-0001/W1581052 /ANTI-IFSD KEY INSPECTION POINTS OF PW1100G ENGINE | H | 282:31 | 12689:58 | 2025-11-21 | 2025-11-15 | B-LAB-PLN-201125-LM1 | 1'500 | 2 | 96 | 0.16667 | PW1127GA-JM / P770214
B-LAD | Q | HE32-242000-23-1-01 (R0005) / DISCARD NO.1 IDG SCAVENGE AND CHARGE FILTERS, DRAIN AND REPLENISH OIL SYSTEM | H | 279:42 | 10209:47 | 2025-11-21 | 2025-11-14 | B-LAD-PLN-211125-LM | 800 | 1 | 91 | 0.13542
B-LAB | Q | HE32-279000-05-1 (R0003) / OPERATIONAL CHECK OF LOGICS ACTIVATING ELAC 1, ELAC 2 AND SEC.1 STANDBY POWER SUPPLIES | H | 296:48 | 12704:15 | 2025-11-23 | 2025-11-15 | B-LAB-PLN-201125-LM1 | 400 | 1 | 80 | 0.054861
B-LAB | Q | HE32-272400-01-1 (R0004) / OPERATIONAL CHECK OF RUDDER SERVOCONTROLS WITH INDIVIDUAL HYDRAULIC SYSTEMS | H | 310:03 | 12717:30 | 2025-11-24 | 2025-11-15 | B-LAB-PLN-201125-LM1 | 750 | 1 | 88 | 0.020833
B-LAE | Q | HE32-272400-01-1 (R0004) / OPERATIONAL CHECK OF RUDDER SERVOCONTROLS WITH INDIVIDUAL HYDRAULIC SYSTEMS | H | 321:25 | 9395:01 | 2025-11-25 | 2025-11-14 | B-LAE-PLN-241125-LM | 750 | 1 | 85 | 0.020833
B-LAA | Q | HE32-730000-W1-1 (R0002) / CORRECT FAULTS OF THE ENGINE SCHEDULED MAINTENANCE REPORT (SMR) | H | 315:36 | 15752:10 | 2025-11-25 | 2025-11-21 | B-LAA-PLN-261125-LM | 750 | 1 | 96 | 0.0083333
B-LAE | Q | HE32-730000-W1-1 (R0002) / CORRECT FAULTS OF THE ENGINE SCHEDULED MAINTENANCE REPORT (SMR) | H | 321:25 | 9395:01 | 2025-11-25 | 2025-11-14 | B-LAE-PLN-241125-LM | 750 | 1 | 85 | 0.0083333
B-LAA | D | EO-PW-79-0034/W1534481 /REPETITIVE INSPECTION AND TORQUE CHECK OF THE MGB AND AGB TUBE BOSS | C | 107 | 5'803 | 2025-11-26 |  | 0 | Thr. 750 | 3 | 85 | 0.22917 | PW1127GA-JM / P770440 | RH ENG
B-LAA | V | REPLACE 60592-201/A22726/W484613 (RESERVOIR ASSY) | D | 31 | 27.Nov.2025 | 2025-11-27 | 2025-10-31 | B-LAA-PLN-271125-LM |  | 2 |  | 0.10417 | 60592-201 / A22726
B-LAB | D | EOI-72-0001/W1586052 /ANTI-IFSD KEY INSPECTION POINTS OF PW1100G ENGINE | H | 353:15 | 12760:42 | 2025-11-28 | 2025-11-20 | B-LAB-PLN-201125-LM | 1'500 | 2 | 95 | 0.16667 | PW1127GA-JM / P770220
B-LAC | Q | HE32-25-SCME-070 (R0002) / INSPECTION OF LOOSE FLOTATION EQUIPMENT | D | 32 | 28.Nov.2025 | 2025-11-28 | 2025-11-21 | B-LAC-PLN-271125-LM | 120 D | 1 | 94 | 0.013889
B-LAB | Q | HE32-291000-23-1 (R0001) / DETAILED INSPECTION OF THE PYLON / ENGINE INTERFACE ROD ENDS, ROD ATTACHMENT FITTINGS, INTERF | H | 355:49 | 12763:16 | 2025-11-28 | 2025-11-11 | B-LAB-PLN-111125-LM | 2'500 | 1 | 93 | 0.16944
B-LAB | Q | HE32-291000-24-1 (R0001) / DETAILED INSPECTION OF THE PYLON / ENGINE INTERFACE ROD ENDS, ROD ATTACHMENT FITTINGS, INTERF | H | 355:49 | 12763:16 | 2025-11-28 | 2025-11-11 | B-LAB-PLN-111125-LM | 2'500 | 1 | 93 | 0.16944
B-LAB | V | REPLACE 3214-31/943763/W1600558 (EPSU BATTERY) | D | 32 | 28.Nov.2025 | 2025-11-28 | 2025-11-20 | B-LAB-PLN-281125-LM |  | 2 |  | 0.0625 | 3214-31 / 943763
B-LAA | D | EO-PW-72-0193/W1623969 /TUBE ASSEMBLY; OIL; NO. 4 BEARING(LR111); SCAVENGE - EXAMINE THE NO. 4 | H | 358:35 | 15795:09 | 2025-11-29 | 2025-11-21 | B-LAA-PLN-261125-LM | 1'000 | 2 | 93 | 0.090278 | PW1127GA-JM / P771230
B-LAB | D | EO-PW-79-0034/REPETITIVE INSPECTION AND TORQUE CHECK OF THE MGB AND AGB TUBE BOSS | H | 359:56 | 12767:23 | 2025-11-29 |  | 0 | 1'500 | 3 | 76 | 0.22917 | PW1127GA-JM / P770214 | LH ENG
B-LAD | Q | HE32-279000-05-1 (R0003) / OPERATIONAL CHECK OF LOGICS ACTIVATING ELAC 1, ELAC 2 AND SEC.1 STANDBY POWER SUPPLIES | H | 378:16 | 10308:21 | 2025-11-30 |  | 0 | 400 | 1 | 5 | 0.054861
B-LAA | Q | HE32-291000-23-1 (R0001) / DETAILED INSPECTION OF THE PYLON / ENGINE INTERFACE ROD ENDS, ROD ATTACHMENT FITTINGS, INTERF | H | 377:22 | 15813:56 | 2025-11-30 | 2025-11-05 | B-LAA-PLN-051125-LM | 2'500 | 1 | 90 | 0.16944
B-LAA | Q | HE32-291000-24-1 (R0001) / DETAILED INSPECTION OF THE PYLON / ENGINE INTERFACE ROD ENDS, ROD ATTACHMENT FITTINGS, INTERF | H | 377:22 | 15813:56 | 2025-11-30 | 2025-11-05 | B-LAA-PLN-051125-LM | 2'500 | 1 | 90 | 0.16944
B-LAD | V | REPLACE 34600017/53754F1/W279607 (CARGO FIRE EXTINGUISHER) | D | 34 | 30.Nov.2025 | 2025-11-30 | 2025-11-01 | B-LAD-PLN-301125-LM |  | 2 |  | 0.1 | 34600017 / 53754F1
B-LAD | V | REPLACE MF20-534/B157557/W279681 (MASK-FULL FACE QUICK DONNING) | D | 34 | 30.Nov.2025 | 2025-11-30 | 2025-11-01 | B-LAD-PLN-301125-LM |  | 2 |  | 0.083333 | MF20-534 / B157557
B-LAD | V | REPLACE MK-HKG-02/EMK-052/W1579157 (MEDICAL KIT) | D | 34 | 30.Nov.2025 | 2025-11-30 | 2025-11-01 | B-LAD-PLN-301125-LM |  | 2 |  | 0.0034722 | MK-HKG-02 / EMK-052
B-LAE | V | REPLACE MK-HKG-02/EMK-151/W1594268 (MEDICAL KIT) | D | 34 | 30.Nov.2025 | 2025-11-30 | 2025-11-25 | B-LAE-PLN-311225-LM |  | 2 |  | 0.0034722 | MK-HKG-02 / EMK-151
B-LAD | V | REPLACE RCF6717/23157/W279555 (PRESSURE REGULATOR TRANSMITTER) | D | 34 | 30.Nov.2025 | 2025-11-30 | 2025-11-01 | B-LAD-PLN-301125-LM |  | 2 |  | 0.083333 | RCF6717 / 23157
B-LAD | V | REPLACE RCF6717/23160/W279685 (PRESSURE REGULATOR TRANSMITTER) | D | 34 | 30.Nov.2025 | 2025-11-30 | 2025-11-15 | B-LAD-PLN-151125-LM |  | 2 |  | 0.083333 | RCF6717 / 23160
B-LAD | D | EO-PW-72-0193/W1402405 /TUBE ASSEMBLY; OIL; NO. 4 BEARING(LR111); SCAVENGE - EXAMINE THE NO. 4 | H | 382:23 | 10312:28 | 2025-12-01 | 2025-11-24 | B-LAD-PLN-301125-LM1 | 1'000 | 2 | 93 | 0.090278 | PW1127GA-JM / P771915
B-LAA | D | EO-VSB-49-8371/W1551425 /[131-9A] REPLACE THE IGNITION UNIT PN 3888058-7 OR 3888058-5 WITH | D | 35 | 01.Dec.2025 | 2025-12-01 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 | Before 01.Dec.2025 | 3 | 100 | 0.041667 | 3800708-1 / P-5514 | EOE: Suggest to arrange EOI-49-0004 with this EO
B-LAB | D | EO-VSB-49-8371/W1551429 /P55601 /[131-9A] REPLACE THE IGNITION UNIT PN 3888058-7 OR 3888058-5 WITH | D | 35 | 01.Dec.2025 | 2025-12-01 |  | 0 | Before 01.Dec.2025 | 3 | 99 | 0.041667 | 3800708-1 / P-7003 | EOE: Suggest to arrange EOI-49-0004 with this EO
B-LAE | D | EO-VSB-49-8371/W1556608 /P59450 /[131-9A] REPLACE THE IGNITION UNIT PN 3888058-7 OR 3888058-5 WITH | D | 35 | 01.Dec.2025 | 2025-12-01 |  | 0 | Before 01.Dec.2025 | 2 | 99 | 0.041667 | 3800708-1 / P-9078 | EOE: Suggest to arrange EOI-49-0004 with this EO
B-LAE | D | EOI-72-0001/W1597395 /ANTI-IFSD KEY INSPECTION POINTS OF PW1100G ENGINE | H | 383:10 | 9456:46 | 2025-12-01 | 2025-11-14 | B-LAE-PLN-241125-LM | 1'500 | 2 | 89 | 0.16667 | PW1127GA-JM / P772225
B-LAC | Q | HE32-272400-01-1 (R0004) / OPERATIONAL CHECK OF RUDDER SERVOCONTROLS WITH INDIVIDUAL HYDRAULIC SYSTEMS | H | 383:02 | 8411:34 | 2025-12-01 | 2025-11-21 | B-LAC-PLN-271125-LM | 750 | 1 | 87 | 0.020833
B-LAC | Q | HE32-730000-W1-1 (R0002) / CORRECT FAULTS OF THE ENGINE SCHEDULED MAINTENANCE REPORT (SMR) | H | 383:02 | 8411:34 | 2025-12-01 | 2025-11-21 | B-LAC-PLN-271125-LM | 750 | 1 | 87 | 0.0083333
B-LAE | V | REPLACE D31865-112/M14007RP/W487894 (SLIDE-OFF-WING) | D | 35 | 01.Dec.2025 | 2025-12-01 | 2025-11-09 | B-LAE-PLN-091125-LM |  | 2 |  | 0.10417 | D31865-112 / M14007RP
B-LAC | D | EO-PW-73-0020/W951110 /REPETITIVE REPLACEMENT OF THE MAIN FUEL FILTER (PW1100G) | H | 391:09 | 8419:41 | 2025-12-02 | 2025-11-21 | B-LAC-PLN-271125-LM | Thr. 1'700 | 3 | 94 | 0.16667 | PW1127GA-JM / P772061 | EOE: DO NOT replace fuel filters on both engine in the same ground
B-LAC | D | EO-PW-57686/W1682246 /WATER WASH FOR PW1100G ENGINES | H | 412:14 | 8440:46 | 2025-12-04 | 2025-11-21 | B-LAC-PLN-191125-LM | 1'500 | 2 | 92 | 0.25 | PW1127GA-JM / P772061
B-LAE | Q | HE32-381000-01-1 (R0002) / DISINFECTION OF POTABLE WATER SYSTEM AND DISCARD THE WATER FILTER ELEMENTS, IF INSTALLED | D | 38 | 04.Dec.2025 | 2025-12-04 | 2025-11-25 | B-LAE-PLN-041225-LM1 | 91 D | 1 | 90 | 0.29722
B-LAE | D | EO-PW-72-0193/W1627448 /TUBE ASSEMBLY; OIL; NO. 4 BEARING(LR111); SCAVENGE - EXAMINE THE NO. 4 | H | 429:45 | 9503:21 | 2025-12-05 | 2025-11-30 | B-LAE-PLN-041225-LM | 1'000 | 2 | 95 | 0.090278 | PW1127GA-JM / P772226
B-LAA | Q | HE32-292000-04-1 (R0003) / OPERATIONAL CHECK OF RAT MANUAL DEPLOYMENT AND FUNCTIONAL CHECK OF RAT USING GROUND TEST UNIT | H | 433:55 | 15870:29 | 2025-12-06 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 | 4'000 | 1 | 91 | 0.38611
B-LAC | D | EO-PW-73-0020/W1570370 /REPETITIVE REPLACEMENT OF THE MAIN FUEL FILTER (PW1100G) | H | 449:25 | 8477:57 | 2025-12-07 | 2025-11-26 | B-LAC-PLN-181125-LM | 1'700 | 3 | 94 | 0.16667 | PW1127GA-JM / P772359 | EOE: DO NOT replace fuel filters on both engine in the same ground
B-LAD | Q | 17603 (0) / B-LAD/BDD012/RI-LM/#1 ENG P770277 CC FOUND 1EA BURN THROUGH AREA REPEAT INSP | H | 460:29 | 10390:34 | 2025-12-08 |  | 0 | 750 | 1 | 38 | 0.083333 |  | LH ENG P770277. Assign with HE32-724000-W2-1.
B-LAD | Q | 17807 (0) / B-LAD/BDD013/LM/#1 ENG P770277 CC FOUND 1EA BURN THROUGH AREA | H | 460:29 | 10390:34 | 2025-12-08 |  | 0 | 750 | 1 | 38 | 0.083333 |  | OPS INFO: ASSIGN WITH AMS HE32-724000-W2-1
B-LAB | Q | HE32-730000-W1-1 (R0002) / CORRECT FAULTS OF THE ENGINE SCHEDULED MAINTENANCE REPORT (SMR) | H | 462:57 | 12870:24 | 2025-12-08 | 2025-12-01 | B-LAB-PLN-071225-LM1 | 750 | 1 | 91 | 0.0083333
B-LAA | V | REPLACE FAKHKG02SW/EFK-1148/W1468191 (FIRST AID KIT) | ID | 42 | 1'492 | 2025-12-08 | 2025-11-11 | B-LAA-PLN-111125-LM |  | 2 |  | 0.0125 | FAKHKG02SW / EFK-1148 | PLN: Please double check if the expiry day of the sad kit is correct.
B-LAC | D | EO-PW-57686/W1682311 /WATER WASH FOR PW1100G ENGINES | H | 471:05 | 8499:37 | 2025-12-09 | 2025-11-21 | B-LAC-PLN-191125-LM | 1'500 | 2 | 88 | 0.25 | PW1127GA-JM / P772359
B-LAE | V | REPLACE 416526/202304743/W1576249 (BATTERY) | H | 482:41 | 9556:17 | 2025-12-10 | 2025-11-30 | B-LAE-PLN-091225-LM |  | 2 |  | 0.0875 | 416526 / 202304743
B-LAE | V | REPLACE 3214-31/954395/W1629434 (EPSU BATTERY) | D | 45 | 11.Dec.2025 | 2025-12-11 | 2025-11-24 | B-LAE-PLN-111225-LM |  | 2 |  | 0.0625 | 3214-31 / 954395
B-LAE | V | REPLACE 3214-31/954401/W1605565 (EPSU BATTERY) | D | 45 | 11.Dec.2025 | 2025-12-11 | 2025-11-24 | B-LAE-PLN-111225-LM |  | 2 |  | 0.0625 | 3214-31 / 954401
B-LAE | V | REPLACE 3214-31/954404/W1605560 (EPSU BATTERY) | D | 45 | 11.Dec.2025 | 2025-12-11 | 2025-11-24 | B-LAE-PLN-111225-LM |  | 2 |  | 0.0625 | 3214-31 / 954404
B-LAA | Q | HE32-291000-14-1 (R0003) / CHECK NITROGEN CHARGE PRESSURE ON HYDRAULIC POWER ACCUMULATORS | H | 499:45 | 15936:19 | 2025-12-12 | 2025-12-03 | B-LAA-PLN-101225-LM | 600 | 1 | 85 | 0.030556
B-LAE | Q | HE32-291000-14-1 (R0003) / CHECK NITROGEN CHARGE PRESSURE ON HYDRAULIC POWER ACCUMULATORS | H | 503:18 | 9576:54 | 2025-12-12 | 2025-11-30 | B-LAE-PLN-221025-LM1 | 600 | 1 | 80 | 0.030556
B-LAA | V | REPLACE 2758/201801804/W1631291 (BATTERY) | H | 503:07 | 15939:41 | 2025-12-12 | 2025-11-29 | B-LAA-PLN-251125-LM |  | 2 |  | 0.0875 | 2758 / 201801804
B-LAA | V | REPLACE 2758/202202021/W1631284 (BATTERY) | H | 503:07 | 15939:41 | 2025-12-12 | 2025-11-29 | B-LAA-PLN-251125-LM |  | 2 |  | 0.0875 | 2758 / 202202021
B-LAA | D | EO-PW-73-0020/W1593628 /REPETITIVE REPLACEMENT OF THE MAIN FUEL FILTER (PW1100G) | H | 514:52 | 15951:26 | 2025-12-13 | 2025-11-21 | B-LAA-PLN-261125-LM | 1'700 | 3 | 87 | 0.16667 | PW1127GA-JM / P771230 | EOE: DO NOT replace fuel filters on both engine in the same ground
B-LAE | Q | B-LAE/BDD019/ ENG#2 COMB CHAMBER REAR (0) / B-LAE/BDD019/ ENG#2 COMB CHAMBER REAR INNER LINER SEG BURN | H | 520:24 | 9594:00 | 2025-12-14 |  | 0 | Before 9'594 | 1 | 94 |  |  | OPS INFO: Assign with HE32-724000-W2-1
B-LAD | Q | HE32-25-SCME-070 (R0002) / INSPECTION OF LOOSE FLOTATION EQUIPMENT | D | 48 | 14.Dec.2025 | 2025-12-14 | 2025-12-09 | B-LAD-PLN-091225-LM | 120 D | 1 | 96 | 0.013889
B-LAB | V | REPLACE 3214-31/949528/W1621604 (EPSU BATTERY) | D | 50 | 16.Dec.2025 | 2025-12-16 | 2025-12-01 | B-LAB-PLN-161225-LM |  | 2 |  | 0.0625 | 3214-31 / 949528
B-LAC | D | EO-PW-72-0193/W1625409 /TUBE ASSEMBLY; OIL; NO. 4 BEARING(LR111); SCAVENGE - EXAMINE THE NO. 4 | H | 555:09 | 8583:41 | 2025-12-17 | 2025-11-26 | B-LAC-PLN-26112LM | 1'000 | 2 | 78 | 0.090278 | PW1127GA-JM / P772359
B-LAB | V | REPLACE 3214-31/941911/W1630896 (EPSU BATTERY) | D | 51 | 17.Dec.2025 | 2025-12-17 | 2025-12-01 | B-LAB-PLN-161225-LM |  | 2 |  | 0.0625 | 3214-31 / 941911
B-LAB | V | REPLACE 3214-31/943852/W1621598 (EPSU BATTERY) | D | 51 | 17.Dec.2025 | 2025-12-17 | 2025-12-01 | B-LAB-PLN-161225-LM |  | 2 |  | 0.0625 | 3214-31 / 943852
B-LAD | D | EO-PW-72-0193/W1629400 /TUBE ASSEMBLY; OIL; NO. 4 BEARING(LR111); SCAVENGE - EXAMINE THE NO. 4 | H | 564:22 | 10494:27 | 2025-12-18 | 2025-12-10 | B-LAD-PLN-171225-LM | 1'000 | 2 | 92 | 0.090278 | PW1127GA-JM / P770277
B-LAD | D | EO-PW-73-0020/W1541434 /REPETITIVE REPLACEMENT OF THE MAIN FUEL FILTER (PW1100G) | H | 566:55 | 10497:00 | 2025-12-18 | 2025-12-10 | B-LAD-PLN-171225-LM | Thr. 1'700 | 3 | 96 | 0.16667 | PW1127GA-JM / P771915 | EOE: DO NOT replace fuel filters on both engine in the same ground
B-LAB | Q | 17762 (0) / B-LAB/BDD033/RI-LM/#1 ENG P770214 7 O`CLOCK POSITION 2 CRACKS REPEAT INSP | H | 575:45 | 12983:12 | 2025-12-19 |  | 0 | 750 | 1 | 23 | 0.125 |  | assign with 32-724000
B-LAB | Q | B-LAB/BDD032/RI-LM/#1 ENG P770214 REPEAT INSP (0) / B-LAB/BDD032/RI-LM/#1 ENG P770214 7O`CLOCK POSITION BURNBACK REPEAT | H | 575:45 | 12983:12 | 2025-12-19 |  | 0 | 750 | 1 | 23 | 0.16667 |  | assign with 32-724000
B-LAB | Q | B-LAB/BDD034/RI-LM/#1 ENG P770214 6 O (0) / B-LAB/BDD034/RI-LM/#1 ENG P770214 6 O`CLOCK POSITION BURNBACK INSP | H | 575:33 | 12983:00 | 2025-12-19 |  | 0 | Before 12'983 | 1 | 95 |  |  | OPS INFO: Assign with HE32-724000-W2-1
B-LAB | Q | B-LAB/BDD035/RI-LM/#1 ENG P770214 4 O (0) / B-LAB/BDD035/RI-LM/#1 ENG P770214 4 O`CLOCK POSITION BURNBACK INSP | H | 575:33 | 12983:00 | 2025-12-19 |  | 0 | Before 12'983 | 1 | 95 |  |  | OPS INFO: Assign with HE32-724000-W2-1
B-LAB | Q | HE32-242000-23-1-02 (R0005) / DISCARD NO.2 IDG SCAVENGE AND CHARGE FILTERS, DRAIN AND REPLENISH OIL SYSTEM | H | 591:18 | 12998:45 | 2025-12-20 | 2025-12-08 | B-LAB-PLN-191225-LM | 800 | 1 | 85 | 0.13542
B-LAB | Q | HE32-291000-14-1 (R0003) / CHECK NITROGEN CHARGE PRESSURE ON HYDRAULIC POWER ACCUMULATORS | H | 591:37 | 12999:04 | 2025-12-20 |  | 0 | 600 | 1 | 1 | 0.030556
B-LAD | Q | HE32-272400-01-1 (R0004) / OPERATIONAL CHECK OF RUDDER SERVOCONTROLS WITH INDIVIDUAL HYDRAULIC SYSTEMS | H | 610:18 | 10540:23 | 2025-12-22 | 2025-12-18 | B-LAD-PLN-291225-LM | 750 | 1 | 95 | 0.020833
B-LAD | Q | HE32-730000-W1-1 (R0002) / CORRECT FAULTS OF THE ENGINE SCHEDULED MAINTENANCE REPORT (SMR) | H | 610:18 | 10540:23 | 2025-12-22 | 2025-12-18 | B-LAD-PLN-291225-LM | 750 | 1 | 95 | 0.0083333
B-LAC | D | EO-PW-72-0193/W1606882 /TUBE ASSEMBLY; OIL; NO. 4 BEARING(LR111); SCAVENGE - EXAMINE THE NO. 4 | H | 633:02 | 8661:34 | 2025-12-24 | 2025-12-16 | B-LAC-PLN-231225-LM1 | 1'000 | 2 | 92 | 0.090278 | PW1127GA-JM / P772061
B-LAB | D | EO-PW-79-0034/REPETITIVE INSPECTION AND TORQUE CHECK OF THE MGB AND AGB TUBE BOSS | H | 634:51 | 13042:18 | 2025-12-24 |  | 0 | 1'500 | 3 | 57 | 0.22917 | PW1127GA-JM / P770220 | RH ENG
B-LAC | V | REPLACE 2758/201909890/W1616777 (BATTERY) | H | 633:02 | 8661:34 | 2025-12-24 | 2025-12-15 | B-LAC-PLN-061225-LM |  | 2 |  | 0.0875 | 2758 / 201909890
B-LAC | V | REPLACE 2758/202205672/W1616744 (BATTERY) | H | 633:02 | 8661:34 | 2025-12-24 | 2025-12-15 | B-LAC-PLN-061225-LM |  | 2 |  | 0.0875 | 2758 / 202205672
B-LAC | V | REPLACE 3214-31/943888/W1631346 (EPSU BATTERY) | D | 58 | 24.Dec.2025 | 2025-12-24 | 2025-12-10 | B-LAC-PLN-241225-LM |  | 2 |  | 0.0625 | 3214-31 / 943888
B-LAC | V | REPLACE 3214-31/954400/W1631334 (EPSU BATTERY) | D | 58 | 24.Dec.2025 | 2025-12-24 | 2025-12-10 | B-LAC-PLN-241225-LM |  | 2 |  | 0.0625 | 3214-31 / 954400
B-LAC | V | REPLACE 3214-31/960945/W1631328 (EPSU BATTERY) | D | 58 | 24.Dec.2025 | 2025-12-24 | 2025-12-10 | B-LAC-PLN-241225-LM |  | 2 |  | 0.0625 | 3214-31 / 960945
B-LAC | D | EOI-72-0001/W1240842 /ANTI-IFSD KEY INSPECTION POINTS OF PW1100G ENGINE | H | 643:45 | 8672:17 | 2025-12-25 | 2025-12-15 | B-LAC-PLN-241225-LM1 | 1'500 | 2 | 93 | 0.16667 | PW1127GA-JM / P772061
B-LAB | V | REPLACE 2758/202306387/W1635485 (BATTERY) | H | 646:59 | 13054:26 | 2025-12-25 | 2025-12-17 | B-LAB-PLN-071225-LM |  | 2 |  | 0.0875 | 2758 / 202306387
B-LAB | V | REPLACE 2758/202309351/W1635490 (BATTERY) | H | 646:59 | 13054:26 | 2025-12-25 | 2025-12-17 | B-LAB-PLN-071225-LM |  | 2 |  | 0.0875 | 2758 / 202309351
B-LAB | Q | HE32-25-SCME-080 (R0004) / INSPECTION OF COCKPIT AND CABIN | H | 658:26 | 13065:53 | 2025-12-26 | 2025-12-17 | B-LAB-PLN-251225-LM | 1'000 | 1 | 91 | 0.33333
B-LAB | Q | HE32-256241-01-1 (R0003) / CHECK OF THE DOOR / EMERGENCY EXIT / OFFWING ESCAPE SLIDE/RAFT INFLATION RESERVOIR PRESSURE | H | 658:26 | 13065:53 | 2025-12-26 | 2025-12-17 | B-LAB-PLN-251225-LM | 1'000 | 1 | 91 | 0.036111
B-LAD | D | EO-VSB-26-0001/W1481298 /FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 61 | 27.Dec.2025 | 2025-12-27 | 2025-12-10 | B-LAD-PLN-171225-LM | 365 D | 1 | 96 | 0.020833 | P3APP003010A / 021689
B-LAD | D | EO-VSB-26-0001/W1481300 /FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 61 | 27.Dec.2025 | 2025-12-27 | 2025-12-10 | B-LAD-PLN-171225-LM | 365 D | 1 | 96 | 0.020833 | P3APP003010A / 021680
B-LAD | D | EO-VSB-26-0001/W1481302 /FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 61 | 27.Dec.2025 | 2025-12-27 | 2025-12-10 | B-LAD-PLN-171225-LM | 365 D | 1 | 96 | 0.020833 | P3APP003010A / 021721
B-LAD | D | EO-VSB-26-0001/W1481304 /FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 61 | 27.Dec.2025 | 2025-12-27 | 2025-12-10 | B-LAD-PLN-171225-LM | 365 D | 1 | 96 | 0.020833 | P3APP003010A / 021688
B-LAD | Q | HE32-242000-23-1-02 (R0005) / DISCARD NO.2 IDG SCAVENGE AND CHARGE FILTERS, DRAIN AND REPLENISH OIL SYSTEM | H | 660:18 | 10590:23 | 2025-12-27 | 2025-12-09 | B-LAD-PLN-091225-LM | 800 | 1 | 77 | 0.13542
B-LAD | Q | HE32-212300-02-1 (R0004) / DISCARD LAVATORY AIR EXTRACTION FILTER ELEMENT | H | 678:29 | 10608:34 | 2025-12-28 | 2025-12-09 | B-LAD-PLN-091225-LM | 1'000 | 1 | 80 | 0.020833
B-LAD | Q | HE32-381000-01-1 (R0002) / DISINFECTION OF POTABLE WATER SYSTEM AND DISCARD THE WATER FILTER ELEMENTS, IF INSTALLED | D | 63 | 29.Dec.2025 | 2025-12-29 | 2025-12-18 | B-LAD-PLN-291225-LM | 91 D | 1 | 88 | 0.29722
B-LAD | D | EO-PW-79-0034/REPETITIVE INSPECTION AND TORQUE CHECK OF THE MGB AND AGB TUBE BOSS | H | 692:11 | 10622:16 | 2025-12-30 |  | 0 | 1'500 | 3 | 53 | 0.22917 | PW1127GA-JM / P770277 | LH ENG
B-LAD | D | EO-A320-73-1155-2/W1625626 /UPGRADE EIU SOFTWARE TO STANDARD S4.5 (CONF 002 – NEO PW) | D | 65 | 31.Dec.2025 | 2025-12-31 | 2025-11-01 | B-LAD-PLN-311225-LM | Before 31.Dec.2025 | 2 | 100 | 0.125
B-LAA | D | EO-A320-73-1155-2/W1625633 /UPGRADE EIU SOFTWARE TO STANDARD S4.5 (CONF 002 – NEO PW) | D | 65 | 31.Dec.2025 | 2025-12-31 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 | Before 31.Dec.2025 | 2 | 100 | 0.125
B-LAD | D | EO-PW-57686/WATER WASH FOR PW1100G ENGINES | H | 708:14 | 10638:19 | 2025-12-31 |  | 0 | 1'500 | 2 | 52 | 0.25 | PW1127GA-JM / P771915
B-LAC | D | EO-PW-79-0034/REPETITIVE INSPECTION AND TORQUE CHECK OF THE MGB AND AGB TUBE BOSS | H | 705:46 | 8734:18 | 2025-12-31 |  | 0 | 1'500 | 3 | 52 | 0.22917 | PW1127GA-JM / P772359 | RH ENG
B-LAC | D | EO-VSB-71-0002/W1568366 /POWERPLANT- FAN COWL DOORS - INTRODUCTION OF LOW-PROFILE LATCH | D | 65 | 31.Dec.2025 | 2025-12-31 | 2025-11-26 | B-LAC-PLN-26112LM | Before 31.Dec.2024 | 2 | 100 | 0.0625 | 636-2040-507 / 0207001
B-LAC | D | EOD-25-0017/W949826 /EQUIPMENT AND FURNISHINGS - CABIN INTERIOR LAMINATE REPLACEMENT | D | 65 | 31.Dec.2025 | 2025-12-31 |  | 0 | Before 31.Dec.2025 | 2 | 99 | 0.33333
B-LAD | D | EOD-25-0017/W949830 /EQUIPMENT AND FURNISHINGS - CABIN INTERIOR LAMINATE REPLACEMENT | D | 65 | 31.Dec.2025 | 2025-12-31 |  | 0 | Before 31.Dec.2025 | 2 | 99 | 0.33333
B-LAE | D | EOD-25-0017/W949831 /EQUIPMENT AND FURNISHINGS - CABIN INTERIOR LAMINATE REPLACEMENT | D | 65 | 31.Dec.2025 | 2025-12-31 |  | 0 | Before 31.Dec.2025 | 2 | 99 | 0.33333
B-LAA | D | EOD-25-0041/W1684665 /A320 FAMILY - INSTALLATION OF PITOT COVER STOWAGE POUCH | D | 65 | 31.Dec.2025 | 2025-12-31 | 2025-11-05 | B-LAA-PLN-051125-LM | Before 31.Dec.2025 | 2 | 100 | 0.089583
B-LAB | D | EOD-25-0041/W1684666 /P60523 /A320 FAMILY - INSTALLATION OF PITOT COVER STOWAGE POUCH | D | 65 | 31.Dec.2025 | 2025-12-31 | 2025-10-30 | B-LAB-PLN-051125-LM | Before 31.Dec.2025 | 2 | 100 | 0.089583
B-LAA | Q | HE32-242100-17-1-02 (R0003) / TORQUE CHECK OF QAD TENSION BOLT OF NO.2 IDG | H | 703:07 | 16139:41 | 2025-12-31 | 2025-12-12 | B-LAA-PLN-291225-LM | 1'200 | 1 | 84 | 0.063889
B-LAE | V | REPLACE DVE90-07/17237/W1406715 (VALVE-SOLENOID) | D | 65 | 31.Dec.2025 | 2025-12-31 | 2025-11-25 | B-LAE-PLN-311225-LM |  | 2 |  |  | DVE90-07 / 17237
B-LAE | V | REPLACE DVE90-07/17238/W1406717 (VALVE-SOLENOID) | D | 65 | 31.Dec.2025 | 2025-12-31 | 2025-11-25 | B-LAE-PLN-311225-LM |  | 2 |  | 0.083333 | DVE90-07 / 17238
B-LAD | V | REPLACE MF20-534/B159320/W279679 (MASK-FULL FACE QUICK DONNING) | D | 65 | 31.Dec.2025 | 2025-12-31 | 2025-11-25 | B-LAD-PLN-311225-LM1 |  | 2 |  | 0.083333 | MF20-534 / B159320
B-LAD | V | REPLACE MF20-534/B159391/W279682 (MASK-FULL FACE QUICK DONNING) | D | 65 | 31.Dec.2025 | 2025-12-31 | 2025-11-25 | B-LAD-PLN-311225-LM1 |  | 2 |  | 0.083333 | MF20-534 / B159391
B-LAC | Q | HE32-255000-16-1 (R0004) / DETAILED INSPECTION OF DIVIDER NETS, DOOR NETS AND NET ATTACHMENT POINTS | H | 728:24 | 8756:56 | 2026-01-02 | 2025-12-16 | B-LAC-PLN-231225-LM1 | 1'000 | 1 | 83 | 0.029167
B-LAE | D | EO-PW-73-0020/REPETITIVE REPLACEMENT OF THE MAIN FUEL FILTER (PW1100G) | H | 735:47 | 9809:23 | 2026-01-03 |  | 0 | 1'700 | 3 | 56 | 0.16667 | PW1127GA-JM / P772225 | EOE: DO NOT replace fuel filters on both engine in the same ground
B-LAD | Q | HE32-25-SCME-080 (R0004) / INSPECTION OF COCKPIT AND CABIN | H | 753:10 | 10683:15 | 2026-01-04 |  | 0 | 1'000 | 1 | 24 | 0.33333
B-LAD | Q | HE32-256241-01-1 (R0003) / CHECK OF THE DOOR / EMERGENCY EXIT / OFFWING ESCAPE SLIDE/RAFT INFLATION RESERVOIR PRESSURE | H | 753:10 | 10683:15 | 2026-01-04 |  | 0 | 1'000 | 1 | 24 | 0.036111
B-LAB | Q | HE32-381000-01-1 (R0002) / DISINFECTION OF POTABLE WATER SYSTEM AND DISCARD THE WATER FILTER ELEMENTS, IF INSTALLED | D | 69 | 04.Jan.2026 | 2026-01-04 |  | 0 | 91 D | 1 | 24 | 0.29722
B-LAE | V | REPLACE 416526/202304785/W1589408 (BATTERY) | H | 745:06 | 9818:42 | 2026-01-04 | 2025-11-30 | B-LAE-PLN-091225-LM |  | 2 |  | 0.0875 | 416526 / 202304785
B-LAD | Q | HE32-242100-17-1-01 (R0003) / TORQUE CHECK OF QAD TENSION BOLT OF NO.1 IDG | H | 764:22 | 10694:27 | 2026-01-05 |  | 0 | 1'200 | 1 | 36 | 0.063889
B-LAA | Q | HE32-25-SCME-070 (R0002) / INSPECTION OF LOOSE FLOTATION EQUIPMENT | D | 70 | 05.Jan.2026 | 2026-01-05 | 2025-12-12 | B-LAA-PLN-291225-LM | 120 D | 1 | 80 | 0.013889
B-LAC | Q | HE32-242000-23-1-01 (R0005) / DISCARD NO.1 IDG SCAVENGE AND CHARGE FILTERS, DRAIN AND REPLENISH OIL SYSTEM | H | 767:23 | 8795:55 | 2026-01-06 |  | 0 | 800 | 1 | 4 | 0.13542
B-LAA | Q | HE32-242000-23-1-02 (R0005) / DISCARD NO.2 IDG SCAVENGE AND CHARGE FILTERS, DRAIN AND REPLENISH OIL SYSTEM | H | 768:40 | 16205:14 | 2026-01-06 |  | 0 | 800 | 1 | 3 | 0.13542
B-LAA | Q | HE32-323000-01-1 (R0002) / VISUAL CHECK OF NLG AND MLG DOWNLOCK SPRINGS AND ATTACHMENTS | H | 769:01 | 16205:35 | 2026-01-06 |  | 0 | 1'000 | 1 | 23 | 0.016667
B-LAA | Q | HE32-323000-19-1 (R0003) / GENERAL VISUAL INSPECTION OF L/G EXTENSION/RETRACTION SYSTEM COMPONENTS | H | 769:01 | 16205:35 | 2026-01-06 |  | 0 | 1'000 | 1 | 23 | 0.041667
B-LAB | D | EO-PW-72-0193/TUBE ASSEMBLY; OIL; NO. 4 BEARING(LR111); SCAVENGE - EXAMINE THE NO. 4 | H | 791:18 | 13198:45 | 2026-01-08 |  | 0 | 1'000 | 2 | 20 | 0.090278 | PW1127GA-JM / P770220
B-LAB | Q | HE32-242000-23-1-01 (R0005) / DISCARD NO.1 IDG SCAVENGE AND CHARGE FILTERS, DRAIN AND REPLENISH OIL SYSTEM | H | 791:37 | 13199:04 | 2026-01-08 |  | 0 | 800 | 1 | 1 | 0.13542
B-LAC | Q | HE32-242000-23-1-02 (R0005) / DISCARD NO.2 IDG SCAVENGE AND CHARGE FILTERS, DRAIN AND REPLENISH OIL SYSTEM | H | 796:32 | 8825:04 | 2026-01-08 |  | 0 | 800 | 1 | 0 | 0.13542
B-LAE | Q | HE32-323000-01-1 (R0002) / VISUAL CHECK OF NLG AND MLG DOWNLOCK SPRINGS AND ATTACHMENTS | H | 800:44 | 9874:20 | 2026-01-09 |  | 0 | 1'000 | 1 | 19 | 0.016667
B-LAE | Q | HE32-323000-19-1 (R0003) / GENERAL VISUAL INSPECTION OF L/G EXTENSION/RETRACTION SYSTEM COMPONENTS | H | 800:44 | 9874:20 | 2026-01-09 |  | 0 | 1'000 | 1 | 19 | 0.041667
B-LAC | V | REPLACE 3214-31/944590 (EPSU BATTERY) | D | 74 | 09.Jan.2026 | 2026-01-09 |  | 0 |  | 2 |  | 0.0625 | 3214-31 / 944590
B-LAC | Q | HE32-212300-02-1 (R0004) / DISCARD LAVATORY AIR EXTRACTION FILTER ELEMENT | H | 815:34 | 8844:06 | 2026-01-10 |  | 0 | 1'000 | 1 | 18 | 0.020833
B-LAC | Q | HE32-242000-01-1 (R0003) / OPERATIONAL CHECK OF THE GAPCU VIA THE CFDS | H | 815:34 | 8844:06 | 2026-01-10 |  | 0 | 1'000 | 1 | 18 | 0.0125
B-LAC | Q | HE32-242800-01-2 (R0003) / OPERATIONAL TEST OF THE STATIC INVERTER | H | 815:34 | 8844:06 | 2026-01-10 |  | 0 | 1'000 | 1 | 18 | 0.022222
B-LAC | Q | HE32-243800-01-1 (R0003) / OPERATIONAL CHECK OF THE BATTERY CHARGE LIMITER (BCL) NO.1 AND NO.2 VIA CENTRALIZED FAULT DIS | H | 815:34 | 8844:06 | 2026-01-10 |  | 0 | 1'000 | 1 | 18 | 0.034722
B-LAC | Q | HE32-261200-01-1 (R0003) / OPERATIONAL CHECK OF LOOP/SQUIB | H | 815:34 | 8844:06 | 2026-01-10 |  | 0 | 1'000 | 1 | 18 | 0.016667
B-LAC | Q | HE32-313000-01-1 (R0005) / READ CENTRALIZED FAULT DISPLAY SYSTEM (CFDS) FOR CLASS 3 FAULTS | H | 815:34 | 8844:06 | 2026-01-10 |  | 0 | 1'000 | 1 | 18 | 0.0125
B-LAC | Q | HE32-324411-01-1 (R0004) / FUNCTIONAL CHECK OF PARKING/EMERGENCY BRAKE ACCUMULATOR BY READING THE CHARGE PRESSURE ON THE | H | 815:34 | 8844:06 | 2026-01-10 |  | 0 | 1'000 | 1 | 18 | 0.031944
B-LAB | D | EO-PW-72-0193/TUBE ASSEMBLY; OIL; NO. 4 BEARING(LR111); SCAVENGE - EXAMINE THE NO. 4 | H | 825:45 | 13233:12 | 2026-01-11 |  | 0 | 1'000 | 2 | 17 | 0.090278 | PW1127GA-JM / P770214
B-LAA | Q | HE32-281100-02-1 (R0003) / OPERATIONAL CHECK OF LEAK MONITOR FOR EVIDENCE OF FUEL LEAKAGE AND CORRECT CLOSURE OF THE VAL | H | 824:51 | 16261:25 | 2026-01-11 |  | 0 | 1'000 | 1 | 17 | 0.020833
B-LAA | Q | HE32-291000-01-1 (R0003) / CHECK OF THE FLUID LEVEL ON RESERVOIR INDICATORS | H | 824:51 | 16261:25 | 2026-01-11 |  | 0 | 1'000 | 1 | 17 | 0.030556
B-LAB | Q | HE32-323000-01-1 (R0002) / VISUAL CHECK OF NLG AND MLG DOWNLOCK SPRINGS AND ATTACHMENTS | H | 825:45 | 13233:12 | 2026-01-11 |  | 0 | 1'000 | 1 | 17 | 0.016667
B-LAB | Q | HE32-323000-19-1 (R0003) / GENERAL VISUAL INSPECTION OF L/G EXTENSION/RETRACTION SYSTEM COMPONENTS | H | 825:45 | 13233:12 | 2026-01-11 |  | 0 | 1'000 | 1 | 17 | 0.041667
B-LAE | D | EO-PW-57686/WATER WASH FOR PW1100G ENGINES | H | 862:02 | 9935:38 | 2026-01-14 |  | 0 | 1'500 | 2 | 42 | 0.25 | PW1127GA-JM / P772226
B-LAE | D | EO-PW-57686/WATER WASH FOR PW1100G ENGINES | H | 862:02 | 9935:38 | 2026-01-14 |  | 0 | 1'500 | 2 | 42 | 0.25 | PW1127GA-JM / P772225
B-LAD | D | EO-PW-73-0020/REPETITIVE REPLACEMENT OF THE MAIN FUEL FILTER (PW1100G) | H | 858:47 | 10788:52 | 2026-01-14 |  | 0 | 1'700 | 3 | 49 | 0.16667 | PW1127GA-JM / P770277 | EOE: DO NOT replace fuel filters on both engine in the same ground
B-LAB | Q | HE32-242000-25-1 (R0001) / OPERATIONAL CHECK OF NETWORK RECONFIGURATION IN CASE OF SINGLE GENERATOR FAILURE | H | 855:49 | 13263:16 | 2026-01-14 |  | 0 | 3'000 | 1 | 71 | 0.125
B-LAB | Q | HE32-242100-17-1-01 (R0003) / TORQUE CHECK OF QAD TENSION BOLT OF NO.1 IDG | H | 858:26 | 13265:53 | 2026-01-14 |  | 0 | 1'200 | 1 | 28 | 0.063889
B-LAC | Q | HE32-242100-17-1-02 (R0003) / TORQUE CHECK OF QAD TENSION BOLT OF NO.2 IDG | H | 857:54 | 8886:26 | 2026-01-14 |  | 0 | 1'200 | 1 | 28 | 0.063889
B-LAD | Q | HE32-323000-01-1 (R0002) / VISUAL CHECK OF NLG AND MLG DOWNLOCK SPRINGS AND ATTACHMENTS | H | 860:18 | 10790:23 | 2026-01-14 |  | 0 | 1'000 | 1 | 13 | 0.016667
B-LAD | Q | HE32-323000-19-1 (R0003) / GENERAL VISUAL INSPECTION OF L/G EXTENSION/RETRACTION SYSTEM COMPONENTS | H | 860:18 | 10790:23 | 2026-01-14 |  | 0 | 1'000 | 1 | 13 | 0.041667
B-LAD | D | EOI-72-0001/ANTI-IFSD KEY INSPECTION POINTS OF PW1100G ENGINE | H | 882:23 | 10812:28 | 2026-01-16 |  | 0 | 1'500 | 2 | 41 | 0.16667 | PW1127GA-JM / P771915
B-LAE | V | REPLACE PW1127GA-JM/P772226 (ENGINE FOR 320NEO) | C | 289 | 3'800 | 2026-01-18 |  | 0 |  | 2 |  |  | PW1127GA-JM / P772226
B-LAB | Q | B-LAB/BDD036/#2 ENG FOUND STR GUIDE V (0) / B-LAB/BDD036/#2 ENG FOUND STR GUIDE VANES EROSION | C | 322 | 4'879 | 2026-01-20 |  | 0 | Before 4'879 | 1 | 93
B-LAD | D | EOCOM-72-0225/VISUAL INSPECTION OF FAN BLADE COVER TRANSITION AREA (PW1100G-JM) | C | 304 | 4'190 | 2026-01-20 |  | 0 | 1'000 | 2 | 69 | 0.0625 | PW1127GA-JM / P771915
B-LAB | Q | HE32-323000-26-1 (R0001) / LUBRICATE GEAR UPLOCK UNITS | D | 85 | 20.Jan.2026 | 2026-01-20 |  | 0 | 121 D | 1 | 29 | 0.0125
B-LAA | V | REPLACE 3214-31/150763/W1634569 (EPSU BATTERY) | D | 85 | 20.Jan.2026 | 2026-01-20 | 2026-01-05 | B-LAA-PLN-200126-LM |  | 2 |  | 0.0625 | 3214-31 / 150763
B-LAB | D | EOCOM-32-0324/DETAILED VISUAL INSPECTION OF NLG TORQUE LINK APEX PIN AND NUT | D | 86 | 21.Jan.2026 | 2026-01-21 |  | 0 | 540 D | 2 | 84 | 0.25 |  | EOE: Align with AMS task HE32-322127-01-1 if possible
B-LAC | Q | HE32-274000-02-1 (R0002) / OPERATIONAL CHECK OF THS ACTUATOR WITH INDIVIDUAL HYDRAULIC SYSTEMS | H | 928:24 | 8956:56 | 2026-01-21 |  | 0 | 1'200 | 1 | 22 | 0.027083
B-LAA | V | REPLACE 3214-31/150761/W1634566 (EPSU BATTERY) | D | 87 | 22.Jan.2026 | 2026-01-22 | 2026-01-05 | B-LAA-PLN-200126-LM |  | 2 |  | 0.0625 | 3214-31 / 150761
B-LAA | V | REPLACE 3214-31/150765/W1634572 (EPSU BATTERY) | D | 87 | 22.Jan.2026 | 2026-01-22 | 2026-01-05 | B-LAA-PLN-200126-LM |  | 2 |  | 0.0625 | 3214-31 / 150765
B-LAB | D | EOCOM-72-0225/VISUAL INSPECTION OF FAN BLADE COVER TRANSITION AREA (PW1100G-JM) | C | 332 | 4'889 | 2026-01-23 |  | 0 | 1'000 | 2 | 66 | 0.0625 | PW1127GA-JM / P770220
B-LAD | Q | HE32-242100-17-1-02 (R0003) / TORQUE CHECK OF QAD TENSION BOLT OF NO.2 IDG | H | 953:10 | 10883:15 | 2026-01-23 |  | 0 | 1'200 | 1 | 20 | 0.063889
B-LAE | Q | HE32-281100-02-1 (R0003) / OPERATIONAL CHECK OF LEAK MONITOR FOR EVIDENCE OF FUEL LEAKAGE AND CORRECT CLOSURE OF THE VAL | H | 952:00 | 10025:36 | 2026-01-23 |  | 0 | 1'000 | 1 | 4 | 0.020833
B-LAE | Q | HE32-291000-01-1 (R0003) / CHECK OF THE FLUID LEVEL ON RESERVOIR INDICATORS | H | 952:00 | 10025:36 | 2026-01-23 |  | 0 | 1'000 | 1 | 4 | 0.030556
B-LAA | D | EO-PW-57686/WATER WASH FOR PW1100G ENGINES | H | 964:36 | 16401:10 | 2026-01-24 |  | 0 | 1'500 | 2 | 35 | 0.25 | PW1127GA-JM / P770440
B-LAA | D | EO-PW-57686/WATER WASH FOR PW1100G ENGINES | H | 964:36 | 16401:10 | 2026-01-24 |  | 0 | 1'500 | 2 | 35 | 0.25 | PW1127GA-JM / P771230
B-LAC | Q | HE32-25-SCME-080 (R0004) / INSPECTION OF COCKPIT AND CABIN | H | 967:23 | 8995:55 | 2026-01-24 |  | 0 | 1'000 | 1 | 3 | 0.33333
B-LAC | Q | HE32-256241-01-1 (R0003) / CHECK OF THE DOOR / EMERGENCY EXIT / OFFWING ESCAPE SLIDE/RAFT INFLATION RESERVOIR PRESSURE | H | 967:23 | 8995:55 | 2026-01-24 |  | 0 | 1'000 | 1 | 3 | 0.036111
B-LAA | Q | HE32-274000-02-1 (R0002) / OPERATIONAL CHECK OF THS ACTUATOR WITH INDIVIDUAL HYDRAULIC SYSTEMS | H | 969:01 | 16405:35 | 2026-01-24 |  | 0 | 1'200 | 1 | 19 | 0.027083
B-LAD | D | EOI-72-0001/ANTI-IFSD KEY INSPECTION POINTS OF PW1100G ENGINE | H | 979:42 | 10909:47 | 2026-01-25 |  | 0 | 1'500 | 2 | 34 | 0.16667 | PW1127GA-JM / P770277
B-LAB | Q | HE32-25-SCME-070 (R0002) / INSPECTION OF LOOSE FLOTATION EQUIPMENT | D | 90 | 25.Jan.2026 | 2026-01-25 |  | 0 | 120 D | 1 | 25 | 0.013889
B-LAA | Q | HE32-255000-16-1 (R0004) / DETAILED INSPECTION OF DIVIDER NETS, DOOR NETS AND NET ATTACHMENT POINTS | H | 975:15 | 16411:49 | 2026-01-25 |  | 0 | 1'000 | 1 | 2 | 0.029167
B-LAB | Q | HE32-281100-02-1 (R0003) / OPERATIONAL CHECK OF LEAK MONITOR FOR EVIDENCE OF FUEL LEAKAGE AND CORRECT CLOSURE OF THE VAL | H | 991:37 | 13399:04 | 2026-01-26 |  | 0 | 1'000 | 1 | 0 | 0.020833
B-LAB | Q | HE32-291000-01-1 (R0003) / CHECK OF THE FLUID LEVEL ON RESERVOIR INDICATORS | H | 991:37 | 13399:04 | 2026-01-26 |  | 0 | 1'000 | 1 | 0 | 0.030556
B-LAB | D | EO-PW-73-0020/REPETITIVE REPLACEMENT OF THE MAIN FUEL FILTER (PW1100G) | H | 994:09 | 13401:36 | 2026-01-27 |  | 0 | 1'700 | 3 | 41 | 0.16667 | PW1127GA-JM / P770220 | EOE: DO NOT replace fuel filters on both engine in the same ground
B-LAA | Q | HE32-274451-01-1 (R0003) / LUBRICATE THS ACTUATOR BALL SCREW NUT | H | 1000:15 | 16436:49 | 2026-01-27 |  | 0 | 1'600 | 1 | 37 | 0.040278
B-LAE | Q | HE32-291000-23-1 (R0001) / DETAILED INSPECTION OF THE PYLON / ENGINE INTERFACE ROD ENDS, ROD ATTACHMENT FITTINGS, INTERF | H | 1002:43 | 10076:19 | 2026-01-28 |  | 0 | 2'500 | 1 | 59 | 0.16944
B-LAE | Q | HE32-291000-24-1 (R0001) / DETAILED INSPECTION OF THE PYLON / ENGINE INTERFACE ROD ENDS, ROD ATTACHMENT FITTINGS, INTERF | H | 1002:43 | 10076:19 | 2026-01-28 |  | 0 | 2'500 | 1 | 59 | 0.16944
B-LAC | Q | HE32-281100-05-1 (R0002) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS | D | 94 | 29.Jan.2026 | 2026-01-29 |  | 0 | 182 D | 1 | 48 | 0.016667
B-LAC | Q | HE32-281100-06-1 (R0002) / OPERATIONAL CHECK OF WATER DRAIN VALVES | D | 94 | 29.Jan.2026 | 2026-01-29 |  | 0 | 182 D | 1 | 48 | 0.030556
B-LAB | Q | HE32-242100-17-1-02 (R0003) / TORQUE CHECK OF QAD TENSION BOLT OF NO.2 IDG | H | 1025:45 | 13433:12 | 2026-01-30 |  | 0 | 1'200 | 1 | 14 | 0.063889
B-LAD | Q | HE32-25-SCME-180 (R0002) / CHECK OF CABIN LOOSE EQUIPMENT | D | 95 | 30.Jan.2026 | 2026-01-30 |  | 0 | 120 D | 1 | 20 | 0.22083
B-LAA | Q | HE32-290000-05-1 (R0004) / CHECK CLOGGING INDICATORS ON RETURN, CASE DRAIN, GROUND SERVICING, HP DELIVERY, BLEED AIR, WA | H | 1031:30 | 16468:04 | 2026-01-30 |  | 0 | 2'000 | 1 | 48 | 0.12083
B-LAD | Q | HE32-323000-26-1 (R0001) / LUBRICATE GEAR UPLOCK UNITS | D | 96 | 31.Jan.2026 | 2026-01-31 |  | 0 | 121 D | 1 | 20 | 0.0125
B-LAB | V | REPLACE 33600105-4/A3090D1/W282647 (ENGINE FIRE EXTINGUISHER) | D | 96 | 31.Jan.2026 | 2026-01-31 | 2026-01-05 | B-LAB-PLN-310126-LM |  | 2 |  | 0.12917 | 33600105-4 / A3090D1
B-LAB | V | REPLACE 33600105-4/A3091D1/W282646 (ENGINE FIRE EXTINGUISHER) | D | 96 | 31.Jan.2026 | 2026-01-31 | 2026-01-05 | B-LAB-PLN-310126-LM |  | 2 |  | 0.12917 | 33600105-4 / A3091D1
B-LAB | V | REPLACE 33600105-4/A3094D1/W282648 (ENGINE FIRE EXTINGUISHER) | D | 96 | 31.Jan.2026 | 2026-01-31 | 2026-01-05 | B-LAB-PLN-310126-LM |  | 2 |  | 0.12917 | 33600105-4 / A3094D1
B-LAC | V | REPLACE 3552AAADAACXCD/P16053077 (CYLINDER ASSY-OXYGEN PORTABLE) | D | 96 | 31.Jan.2026 | 2026-01-31 |  | 0 |  | 2 |  | 0.016667 | 3552AAADAACXCD / P16053077
B-LAC | Q | HE32-25-SCME-180 (R0002) / CHECK OF CABIN LOOSE EQUIPMENT | D | 97 | 01.Feb.2026 | 2026-02-01 |  | 0 | 120 D | 1 | 19 | 0.22083
B-LAB | Q | HE32-276400-01-1-02 (R0003) / LUBRICATE SPOILER NO 1 TO 5 ACTUATOR ATTACHMENTS - RH | H | 1052:56 | 13460:23 | 2026-02-01 |  | 0 | 2'000 | 1 | 47 | 0.1
B-LAB | Q | HE32-281200-01-1-01 (R0003) / VISUAL CHECK OF LH VENT SURGE TANK BURST DISC (EXTERNAL) | H | 1052:56 | 13460:23 | 2026-02-01 |  | 0 | 2'000 | 1 | 47 | 0.025
B-LAB | Q | HE32-281200-01-1-02 (R0003) / VISUAL CHECK OF RH VENT SURGE TANK BURST DISC (EXTERNAL) | H | 1052:56 | 13460:23 | 2026-02-01 |  | 0 | 2'000 | 1 | 47 | 0.025
B-LAB | D | EO-PW-57686/WATER WASH FOR PW1100G ENGINES | H | 1060:03 | 13467:30 | 2026-02-02 |  | 0 | 1'500 | 2 | 29 | 0.25 | PW1127GA-JM / P770220
B-LAB | D | EO-PW-57686/WATER WASH FOR PW1100G ENGINES | H | 1060:03 | 13467:30 | 2026-02-02 |  | 0 | 1'500 | 2 | 29 | 0.25 | PW1127GA-JM / P770214
B-LAA | D | EO-PW-72-0152/INSPECTION OF THE AIR SEALASSEMBLIES THROUGH THE MAIN GEARBOXHOUSING B | H | 1059:33 | 16496:07 | 2026-02-02 |  | 0 | 1'875 | 2 | 43 | 0.16667 | PW1127GA-JM / P771230 | LH ENG
B-LAE | Q | HE32-25-SCME-070 (R0002) / INSPECTION OF LOOSE FLOTATION EQUIPMENT | D | 98 | 02.Feb.2026 | 2026-02-02 |  | 0 | 120 D | 1 | 18 | 0.013889
B-LAD | Q | HE32-274000-02-1 (R0002) / OPERATIONAL CHECK OF THS ACTUATOR WITH INDIVIDUAL HYDRAULIC SYSTEMS | H | 1060:18 | 10990:23 | 2026-02-02 |  | 0 | 1'200 | 1 | 11 | 0.027083
B-LAE | Q | HE32-276400-01-1-02 (R0003) / LUBRICATE SPOILER NO 1 TO 5 ACTUATOR ATTACHMENTS - RH | H | 1074:54 | 10148:30 | 2026-02-03 |  | 0 | 2'000 | 1 | 46 | 0.1
B-LAE | Q | HE32-281200-01-1-01 (R0003) / VISUAL CHECK OF LH VENT SURGE TANK BURST DISC (EXTERNAL) | H | 1074:54 | 10148:30 | 2026-02-03 |  | 0 | 2'000 | 1 | 46 | 0.025
B-LAE | Q | HE32-281200-01-1-02 (R0003) / VISUAL CHECK OF RH VENT SURGE TANK BURST DISC (EXTERNAL) | H | 1074:54 | 10148:30 | 2026-02-03 |  | 0 | 2'000 | 1 | 46 | 0.025
B-LAA | Q | HE32-321000-01-1-01 (R0002) / LUBRICATE LH MAIN LANDING GEAR AND DOOR | D | 100 | 04.Feb.2026 | 2026-02-04 |  | 0 | 121 D | 1 | 17 | 0.21458
B-LAA | Q | HE32-321000-01-1-02 (R0002) / LUBRICATE RH MAIN LANDING GEAR AND DOOR | D | 100 | 04.Feb.2026 | 2026-02-04 |  | 0 | 121 D | 1 | 17 | 0.21458
B-LAA | Q | HE32-322000-01-1 (R0002) / LUBRICATE NOSE LANDING GEAR AND DOORS | D | 100 | 04.Feb.2026 | 2026-02-04 |  | 0 | 121 D | 1 | 17 | 0.0875
B-LAA | V | REPLACE 3214-31/150758/W1634575 (EPSU BATTERY) | D | 102 | 06.Feb.2026 | 2026-02-06 | 2026-01-05 | B-LAA-PLN-200126-LM |  | 2 |  | 0.0625 | 3214-31 / 150758
B-LAC | D | EOI-72-0001/ANTI-IFSD KEY INSPECTION POINTS OF PW1100G ENGINE | H | 1126:49 | 9155:21 | 2026-02-08 |  | 0 | 1'500 | 2 | 24 | 0.16667 | PW1127GA-JM / P772359
B-LAD | D | EO-PW-57686/WATER WASH FOR PW1100G ENGINES | H | 1149:46 | 11079:51 | 2026-02-10 |  | 0 | 1'500 | 2 | 23 | 0.25 | PW1127GA-JM / P770277
B-LAE | Q | HE32-242100-17-1-01 (R0003) / TORQUE CHECK OF QAD TENSION BOLT OF NO.1 IDG | H | 1152:00 | 10225:36 | 2026-02-10 |  | 0 | 1'200 | 1 | 4 | 0.063889
B-LAC | Q | B-LAC/BDD022/ENG #2 P772359 FOUND HPT (0) / B-LAC/BDD022/ENG #2 P772359 FOUND HPT ST1 BLADES ERROSION | H | 1165:28 | 9194:00 | 2026-02-12 |  | 0 | Before 9'194 | 1 | 87
B-LAD | Q | HE32-274451-01-1 (R0003) / LUBRICATE THS ACTUATOR BALL SCREW NUT | H | 1164:22 | 11094:27 | 2026-02-12 |  | 0 | 1'600 | 1 | 27 | 0.040278
B-LAE | Q | HE32-291000-18-1 (R0003) / DRAIN THE RECOVERY TANK | H | 1181:43 | 10255:19 | 2026-02-13 |  | 0 | 1'500 | 1 | 21 | 0.045833
B-LAD | V | REPLACE 3214-31/151419 (EPSU BATTERY) | D | 109 | 13.Feb.2026 | 2026-02-13 |  | 0 |  | 2 |  | 0.0625 | 3214-31 / 151419
B-LAB | Q | HE32-274000-02-1 (R0002) / OPERATIONAL CHECK OF THS ACTUATOR WITH INDIVIDUAL HYDRAULIC SYSTEMS | H | 1191:37 | 13599:04 | 2026-02-14 |  | 0 | 1'200 | 1 | 0 | 0.027083
B-LAA | V | REPLACE 33600105-4/A3587D1/W282820 (ENGINE FIRE EXTINGUISHER) | D | 110 | 14.Feb.2026 | 2026-02-14 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 2 |  | 0.12917 | 33600105-4 / A3587D1
B-LAD | V | REPLACE 416526/202306662 (BATTERY) | H | 1192:11 | 11122:16 | 2026-02-14 |  | 0 |  | 2 |  | 0.0875 | 416526 / 202306662
B-LAC | Q | HE32-253400-01-1 (R0004) / CLEAN "CHILLED AIR IN" AND "CHILLED AIR OUT" GRILLES/FILTERS IN GALLEY CABINET | H | 1228:24 | 9256:56 | 2026-02-18 |  | 0 | 1'500 | 1 | 18 | 0.024306
B-LAC | Q | HE32-253400-02-1 (R0003) / CLEAN AIR CHILLER CONDENSER AIR FILTER | H | 1228:24 | 9256:56 | 2026-02-18 |  | 0 | 1'500 | 1 | 18 | 0.0083333
B-LAE | Q | HE32-321000-01-1-01 (R0002) / LUBRICATE LH MAIN LANDING GEAR AND DOOR | D | 115 | 19.Feb.2026 | 2026-02-19 |  | 0 | 121 D | 1 | 4 | 0.21458
B-LAE | Q | HE32-321000-01-1-02 (R0002) / LUBRICATE RH MAIN LANDING GEAR AND DOOR | D | 115 | 19.Feb.2026 | 2026-02-19 |  | 0 | 121 D | 1 | 4 | 0.21458
B-LAE | Q | HE32-322000-01-1 (R0002) / LUBRICATE NOSE LANDING GEAR AND DOORS | D | 115 | 19.Feb.2026 | 2026-02-19 |  | 0 | 121 D | 1 | 4 | 0.0875
B-LAC | Q | HE32-323000-26-1 (R0001) / LUBRICATE GEAR UPLOCK UNITS | D | 116 | 20.Feb.2026 | 2026-02-20 |  | 0 | 121 D | 1 | 4 | 0.0125
B-LAD | Q | HE32-291000-05-1 (R0003) / DRAIN THE WATER SEPARATOR | H | 1263:47 | 11193:52 | 2026-02-21 |  | 0 | 2'250 | 1 | 43 | 0.027778
B-LAD | V | REPLACE 3214-31/151572 (EPSU BATTERY) | D | 117 | 21.Feb.2026 | 2026-02-21 |  | 0 |  | 2 |  | 0.0625 | 3214-31 / 151572
B-LAA | D | EOI-72-0001/ANTI-IFSD KEY INSPECTION POINTS OF PW1100G ENGINE | H | 1277:35 | 16714:09 | 2026-02-22 |  | 0 | 1'500 | 2 | 14 | 0.16667 | PW1127GA-JM / P770440
B-LAE | Q | HE32-274451-01-1 (R0003) / LUBRICATE THS ACTUATOR BALL SCREW NUT | H | 1281:43 | 10355:19 | 2026-02-23 |  | 0 | 1'600 | 1 | 19 | 0.040278
B-LAB | Q | HE32-321000-01-1-01 (R0002) / LUBRICATE LH MAIN LANDING GEAR AND DOOR | D | 119 | 23.Feb.2026 | 2026-02-23 |  | 0 | 121 D | 1 | 1 | 0.21458
B-LAB | Q | HE32-321000-01-1-02 (R0002) / LUBRICATE RH MAIN LANDING GEAR AND DOOR | D | 119 | 23.Feb.2026 | 2026-02-23 |  | 0 | 121 D | 1 | 1 | 0.21458
B-LAB | Q | HE32-322000-01-1 (R0002) / LUBRICATE NOSE LANDING GEAR AND DOORS | D | 119 | 23.Feb.2026 | 2026-02-23 |  | 0 | 121 D | 1 | 1 | 0.0875
B-LAB | V | REPLACE 3552AAADAACXCD/P11070418 (CYLINDER ASSY-OXYGEN PORTABLE) | D | 121 | 25.Feb.2026 | 2026-02-25 |  | 0 |  | 2 |  | 0.016667 | 3552AAADAACXCD / P11070418
B-LAC | Q | HE32-383200-01-1 (R0003) / CLEAN FILTER ELEMENT OF WASHBASIN DRAIN VALVES | H | 1315:34 | 9344:06 | 2026-02-26 |  | 0 | 1'500 | 1 | 12 | 0.054167
B-LAA | Q | HE32-253400-01-1 (R0004) / CLEAN "CHILLED AIR IN" AND "CHILLED AIR OUT" GRILLES/FILTERS IN GALLEY CABINET | H | 1324:51 | 16761:25 | 2026-02-27 |  | 0 | 1'500 | 1 | 11 | 0.024306
B-LAA | Q | HE32-253400-02-1 (R0003) / CLEAN AIR CHILLER CONDENSER AIR FILTER | H | 1324:51 | 16761:25 | 2026-02-27 |  | 0 | 1'500 | 1 | 11 | 0.0083333
B-LAD | Q | HE32-290000-05-1 (R0004) / CHECK CLOGGING INDICATORS ON RETURN, CASE DRAIN, GROUND SERVICING, HP DELIVERY, BLEED AIR, WA | H | 1329:19 | 11259:24 | 2026-02-27 |  | 0 | 2'000 | 1 | 33 | 0.12083
B-LAA | Q | HE32-383200-01-1 (R0003) / CLEAN FILTER ELEMENT OF WASHBASIN DRAIN VALVES | H | 1324:51 | 16761:25 | 2026-02-27 |  | 0 | 1'500 | 1 | 11 | 0.054167
B-LAB | V | REPLACE 3552AAADAACXCD/P16071498 (CYLINDER ASSY-OXYGEN PORTABLE) | D | 124 | 28.Feb.2026 | 2026-02-28 |  | 0 |  | 2 |  | 0.016667 | 3552AAADAACXCD / P16071498
B-LAA | V | REPLACE MK-HKG-02/EMK-057 (MEDICAL KIT) | D | 124 | 28.Feb.2026 | 2026-02-28 |  | 0 |  | 2 |  | 0.0034722 | MK-HKG-02 / EMK-057
B-LAC | V | REPLACE MK-HKG-02/EMK-150 (MEDICAL KIT) | D | 124 | 28.Feb.2026 | 2026-02-28 |  | 0 |  | 2 |  | 0.0034722 | MK-HKG-02 / EMK-150
B-LAB | V | REPLACE MK-HKG-02/EMK-155 (MEDICAL KIT) | D | 124 | 28.Feb.2026 | 2026-02-28 |  | 0 |  | 2 |  | 0.0034722 | MK-HKG-02 / EMK-155
B-LAA | V | REPLACE 33600005-3/A3487D1/W282816 (APU FIRE EXTINGUISHER) | D | 125 | 01.Mar.2026 | 2026-03-01 | 2026-02-03 | B-LAA-PLN-010326-LM |  | 2 |  | 0.075 | 33600005-3 / A3487D1
B-LAA | V | REPLACE 33600105-4/A3095D1/W282818 (ENGINE FIRE EXTINGUISHER) | D | 125 | 01.Mar.2026 | 2026-03-01 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 2 |  | 0.12917 | 33600105-4 / A3095D1
B-LAB | V | REPLACE 33600105-4/A3586D1/W282649 (ENGINE FIRE EXTINGUISHER) | D | 125 | 01.Mar.2026 | 2026-03-01 | 2026-01-05 | B-LAB-PLN-310126-LM |  | 2 |  | 0.12917 | 33600105-4 / A3586D1
B-LAA | V | REPLACE 33600105-4/A3592D1/W282821 (ENGINE FIRE EXTINGUISHER) | D | 125 | 01.Mar.2026 | 2026-03-01 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 2 |  | 0.12917 | 33600105-4 / A3592D1
B-LAA | V | REPLACE 33600105-4/A3633D1/W282819 (ENGINE FIRE EXTINGUISHER) | D | 125 | 01.Mar.2026 | 2026-03-01 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 2 |  | 0.12917 | 33600105-4 / A3633D1
B-LAB | V | REPLACE 34600017/44763F1 (CARGO FIRE EXTINGUISHER) | D | 125 | 01.Mar.2026 | 2026-03-01 |  | 0 |  | 2 |  | 0.1 | 34600017 / 44763F1
B-LAE | V | REPLACE RCF6717/23593 (PRESSURE REGULATOR TRANSMITTER) | D | 125 | 01.Mar.2026 | 2026-03-01 |  | 0 |  | 2 |  | 0.083333 | RCF6717 / 23593
B-LAE | V | REPLACE RCF6717/23594 (PRESSURE REGULATOR TRANSMITTER) | D | 125 | 01.Mar.2026 | 2026-03-01 |  | 0 |  | 2 |  | 0.083333 | RCF6717 / 23594
B-LAE | Q | HE32-262441-01-1 (R0004) / CHECK OF THE PRESSURE GAUGE READING OF PORTABLE FIRE EXTINGUISHERS WITH PRESSURE GAUGE IS INS | H | 1396:54 | 10470:30 | 2026-03-05 |  | 0 | 2'000 | 1 | 30 | 0.016667
B-LAE | Q | HE32-525111-06-2 (R0002) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AN | D | 129 | 05.Mar.2026 | 2026-03-05 |  | 0 | 182 D | 1 | 29 | 0.052083
B-LAB | D | EO-PW-72-0152/INSPECTION OF THE AIR SEALASSEMBLIES THROUGH THE MAIN GEARBOXHOUSING B | H | 1408:39 | 13816:06 | 2026-03-06 |  | 0 | 1'875 | 2 | 24 | 0.16667 | PW1127GA-JM / P770220 | RH ENG
B-LAB | Q | HE32-262441-01-1 (R0004) / CHECK OF THE PRESSURE GAUGE READING OF PORTABLE FIRE EXTINGUISHERS WITH PRESSURE GAUGE IS INS | H | 1405:23 | 13812:50 | 2026-03-06 |  | 0 | 2'000 | 1 | 29 | 0.016667
B-LAA | V | REPLACE D31865-111/M14395 (SLIDE-OFF-WING) | D | 130 | 06.Mar.2026 | 2026-03-06 |  | 0 |  | 2 |  | 0.10417 | D31865-111 / M14395
B-LAE | D | EO-VSB-26-0001/FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 131 | 07.Mar.2026 | 2026-03-07 |  | 0 | 365 D | 1 | 64 | 0.020833 | P3APP003010A / 25783
B-LAE | D | EO-VSB-26-0001/FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 131 | 07.Mar.2026 | 2026-03-07 |  | 0 | 365 D | 1 | 64 | 0.020833 | P3APP003010A / 24370
B-LAE | D | EO-VSB-26-0001/FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 131 | 07.Mar.2026 | 2026-03-07 |  | 0 | 365 D | 1 | 64 | 0.020833 | P3APP003010A / 24386
B-LAE | D | EO-VSB-26-0001/FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 131 | 07.Mar.2026 | 2026-03-07 |  | 0 | 365 D | 1 | 64 | 0.020833 | P3APP003010A / 25613
B-LAA | D | EOA32-32-0045/CLEAN THE ELECTRICAL CONNECTOR OF MLG DOOR-UPLOCK PROXIMITY-SENSORS (2 | H | 1428:18 | 16864:52 | 2026-03-08 |  | 0 | 3'000 | 2 | 52 | 0.083333
B-LAA | Q | HE32-242000-25-1 (R0001) / OPERATIONAL CHECK OF NETWORK RECONFIGURATION IN CASE OF SINGLE GENERATOR FAILURE | H | 1428:18 | 16864:52 | 2026-03-08 |  | 0 | 3'000 | 1 | 52 | 0.125
B-LAA | Q | HE32-292000-05-1 (R0003) / OPERATIONAL CHECK OF RAM AIR TURBINE (RAT) AUTOMATIC DEPLOYMENT | H | 1430:22 | 16866:56 | 2026-03-08 |  | 0 | 4'000 | 1 | 64 | 0.051389
B-LAA | D | EO-AOT-A57N025-25/W1693874 /WING - PYLON SPIGOT FITTING - SLEEVE MIGRATION INSPECTION | D | 134 | 10.Mar.2026 | 2026-03-10 | 2025-11-05 | B-LAA-PLN-051125-LM | 365 D | 1 | 66 | 0.14583
B-LAB | D | EO-AOT-A57N025-25/W1693875 /WING - PYLON SPIGOT FITTING - SLEEVE MIGRATION INSPECTION | D | 134 | 10.Mar.2026 | 2026-03-10 | 2025-11-03 | B-LAB-PLN-100326-LM | 365 D | 1 | 66 | 0.14583
B-LAC | D | EO-AOT-A57N025-25/W1693876 /WING - PYLON SPIGOT FITTING - SLEEVE MIGRATION INSPECTION | D | 134 | 10.Mar.2026 | 2026-03-10 | 2025-12-15 | B-LAC-PLN-241225-LM1 | 365 D | 1 | 77 | 0.14583
B-LAA | D | EOI-72-0001/ANTI-IFSD KEY INSPECTION POINTS OF PW1100G ENGINE | H | 1460:13 | 16896:47 | 2026-03-11 |  | 0 | 1'500 | 2 | 2 | 0.16667 | PW1127GA-JM / P771230
B-LAD | Q | HE32-291000-23-1 (R0001) / DETAILED INSPECTION OF THE PYLON / ENGINE INTERFACE ROD ENDS, ROD ATTACHMENT FITTINGS, INTERF | H | 1455:56 | 11386:01 | 2026-03-11 |  | 0 | 2'500 | 1 | 41 | 0.16944
B-LAD | Q | HE32-291000-24-1 (R0001) / DETAILED INSPECTION OF THE PYLON / ENGINE INTERFACE ROD ENDS, ROD ATTACHMENT FITTINGS, INTERF | H | 1455:56 | 11386:01 | 2026-03-11 |  | 0 | 2'500 | 1 | 41 | 0.16944
B-LAC | Q | HE32-291000-18-1 (R0003) / DRAIN THE RECOVERY TANK | H | 1467:23 | 9495:55 | 2026-03-12 |  | 0 | 1'500 | 1 | 2 | 0.045833
B-LAA | Q | HE32-291000-18-1 (R0003) / DRAIN THE RECOVERY TANK | H | 1475:15 | 16911:49 | 2026-03-13 |  | 0 | 1'500 | 1 | 1 | 0.045833
B-LAB | Q | HE32-470000-01-1 (R0004) / REPLACE D-ULPA FILTER ELEMENT | H | 1479:09 | 13886:36 | 2026-03-13 |  | 0 | 7'000 | 1 | 78 | 0.091667
B-LAE | V | REPLACE 3214-31/960937/W1693611 (EPSU BATTERY) | D | 137 | 13.Mar.2026 | 2026-03-13 | 2026-02-13 | B-LAE-PLN-130326-LM |  | 2 |  | 0.0625 | 3214-31 / 960937
B-LAC | D | EO-A320-25-1BVT/INSPECTION OF GALLEY 4X FOR CORROSION OF TROLLEY RETAINER ALUMINIUM | D | 141 | 17.Mar.2026 | 2026-03-17 |  | 0 | 182 D | 1 | 22 | 0.041667 | 601888-002001 / 003
B-LAE | Q | HE32-261300-01-1 (R0003) / OPERATIONAL TEST OF THE APU FIRE AND OVERHEAT DETECTION SYSTEM | H | 1528:11 | 10601:47 | 2026-03-17 |  | 0 | 2'000 | 1 | 23 | 0.0125
B-LAE | Q | HE32-261600-03-1 (R0003) / OPERATIONAL CHECK OF CARGO COMPARTMENT SMOKE DETECTION BY PTT | H | 1528:11 | 10601:47 | 2026-03-17 |  | 0 | 2'000 | 1 | 23 | 0.025
B-LAE | Q | HE32-276400-01-1-01 (R0003) / LUBRICATE LH SPOILER NO 1 TO 5 ACTUATOR ATTACHMENTS | H | 1528:11 | 10601:47 | 2026-03-17 |  | 0 | 2'000 | 1 | 23 | 0.1
B-LAE | Q | HE32-331400-01-1 (R0003) / OPERATIONAL CHECK OF THE LIGHT TEST SYSTEM | H | 1528:11 | 10601:47 | 2026-03-17 |  | 0 | 2'000 | 1 | 23 | 0.023611
B-LAC | Q | HE32-344200-03-1 (R0002) / CLEAN THE EXTERNAL SURFACE OF THE RADIO ALTIMETER ANTENNAS | D | 141 | 17.Mar.2026 | 2026-03-17 |  | 0 | 182 D | 1 | 22 | 0.020833
B-LAA | Q | HE32-281100-05-1 (R0002) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS | D | 142 | 18.Mar.2026 | 2026-03-18 |  | 0 | 182 D | 1 | 21 | 0.016667
B-LAA | Q | HE32-344200-03-1 (R0002) / CLEAN THE EXTERNAL SURFACE OF THE RADIO ALTIMETER ANTENNAS | D | 142 | 18.Mar.2026 | 2026-03-18 |  | 0 | 182 D | 1 | 21 | 0.020833
B-LAE | Q | HE32-31-SCME-010 (R0005) / READOUT PROCEDURE FOR RECORDING INSPECTION OF FDR SYSTEM | D | 143 | 19.Mar.2026 | 2026-03-19 | 2025-12-19 | B-LAE-PLN-191225-LM | 365 D | 1 | 76 | 0.048611
B-LAB | Q | HE32-261300-01-1 (R0003) / OPERATIONAL TEST OF THE APU FIRE AND OVERHEAT DETECTION SYSTEM | H | 1570:41 | 13978:08 | 2026-03-21 |  | 0 | 2'000 | 1 | 21 | 0.0125
B-LAB | Q | HE32-261600-03-1 (R0003) / OPERATIONAL CHECK OF CARGO COMPARTMENT SMOKE DETECTION BY PTT | H | 1570:41 | 13978:08 | 2026-03-21 |  | 0 | 2'000 | 1 | 21 | 0.025
B-LAC | Q | HE32-274451-01-1 (R0003) / LUBRICATE THS ACTUATOR BALL SCREW NUT | H | 1567:23 | 9595:55 | 2026-03-21 |  | 0 | 1'600 | 1 | 2 | 0.040278
B-LAB | Q | HE32-276400-01-1-01 (R0003) / LUBRICATE LH SPOILER NO 1 TO 5 ACTUATOR ATTACHMENTS | H | 1570:41 | 13978:08 | 2026-03-21 |  | 0 | 2'000 | 1 | 21 | 0.1
B-LAB | Q | HE32-331400-01-1 (R0003) / OPERATIONAL CHECK OF THE LIGHT TEST SYSTEM | H | 1570:41 | 13978:08 | 2026-03-21 |  | 0 | 2'000 | 1 | 21 | 0.023611
B-LAD | V | REPLACE 3214-31/152159 (EPSU BATTERY) | D | 145 | 21.Mar.2026 | 2026-03-21 |  | 0 |  | 2 |  | 0.0625 | 3214-31 / 152159
B-LAD | V | REPLACE 3214-31/947202 (EPSU BATTERY) | D | 145 | 21.Mar.2026 | 2026-03-21 |  | 0 |  | 2 |  | 0.0625 | 3214-31 / 947202
B-LAB | Q | HE32-274451-01-1 (R0003) / LUBRICATE THS ACTUATOR BALL SCREW NUT | H | 1591:37 | 13999:04 | 2026-03-23 |  | 0 | 1'600 | 1 | 0 | 0.040278
B-LAA | Q | HE32-31-SCME-010 (R0005) / READOUT PROCEDURE FOR RECORDING INSPECTION OF FDR SYSTEM | D | 149 | 25.Mar.2026 | 2026-03-25 | 2025-12-25 | B-LAA-PLN-251225-LM | 365 D | 1 | 76 | 0.048611
B-LAA | D | EOCOM-32-0324/DETAILED VISUAL INSPECTION OF NLG TORQUE LINK APEX PIN AND NUT | D | 150 | 26.Mar.2026 | 2026-03-26 |  | 0 | 540 D | 2 | 72 | 0.25 |  | EOE: Align with AMS task HE32-322127-01-1 if possible
B-LAB | Q | HE32-212600-01-1 (R0003) / OPERATIONAL CHECK OF THE AVIONICS EQUIPMENT VENTILATION-SYSTEM VIA MCDU | H | 1619:17 | 14026:44 | 2026-03-26 |  | 0 | 3'000 | 1 | 46 | 0.029167
B-LAB | Q | HE32-212643-07-1 (R0002) / DISCARD THE FILTER CARTRIDGE | H | 1619:17 | 14026:44 | 2026-03-26 |  | 0 | 3'000 | 1 | 46 | 0.031944
B-LAB | Q | HE32-212643-09-1 (R0004) / OPERATIONAL CHECK OF NRV FOR FREE MOVEMENT | H | 1619:17 | 14026:44 | 2026-03-26 |  | 0 | 3'000 | 1 | 46 | 0.036111
B-LAB | Q | HE32-212643-10-1 (R0004) / CLEAN THE SYPHON ASSEMBLY (STRAINER) | H | 1619:17 | 14026:44 | 2026-03-26 |  | 0 | 3'000 | 1 | 46 | 0.027778
B-LAB | Q | HE32-261700-03-1 (R0003) / OPERATIONAL CHECK OF LAVATORY SMOKE DETECTION BY CFDS TO CONFIRM WARNINGS CAN BE DISPLAYED | H | 1619:17 | 14026:44 | 2026-03-26 |  | 0 | 3'000 | 1 | 46 | 0.0083333
B-LAB | Q | HE32-262200-02-1 (R0004) / OPERATIONAL CHECK OF AUTOMATIC FIRE EXTINGUISHING CIRCUIT AND TEST APU LP FUEL VALVE OPERATIO | H | 1619:17 | 14026:44 | 2026-03-26 |  | 0 | 3'000 | 1 | 46 | 0.0125
B-LAC | Q | HE32-276400-01-1-02 (R0003) / LUBRICATE SPOILER NO 1 TO 5 ACTUATOR ATTACHMENTS - RH | H | 1633:02 | 9661:34 | 2026-03-27 |  | 0 | 2'000 | 1 | 18 | 0.1
B-LAC | Q | HE32-281200-01-1-01 (R0003) / VISUAL CHECK OF LH VENT SURGE TANK BURST DISC (EXTERNAL) | H | 1633:02 | 9661:34 | 2026-03-27 |  | 0 | 2'000 | 1 | 18 | 0.025
B-LAC | Q | HE32-281200-01-1-02 (R0003) / VISUAL CHECK OF RH VENT SURGE TANK BURST DISC (EXTERNAL) | H | 1633:02 | 9661:34 | 2026-03-27 |  | 0 | 2'000 | 1 | 18 | 0.025
B-LAA | V | REPLACE 3552AAADAACXCD/P11080290 (CYLINDER ASSY-OXYGEN PORTABLE) | D | 152 | 28.Mar.2026 | 2026-03-28 |  | 0 |  | 2 |  | 0.016667 | 3552AAADAACXCD / P11080290
B-LAE | D | EOA32-32-0045/CLEAN THE ELECTRICAL CONNECTOR OF MLG DOOR-UPLOCK PROXIMITY-SENSORS (2 | H | 1667:32 | 10741:08 | 2026-03-30 |  | 0 | 3'000 | 2 | 44 | 0.083333
B-LAA | Q | HE32-281200-01-1-01 (R0003) / VISUAL CHECK OF LH VENT SURGE TANK BURST DISC (EXTERNAL) | H | 1658:35 | 17095:09 | 2026-03-30 |  | 0 | 2'000 | 1 | 17 | 0.025
B-LAA | Q | HE32-281200-01-1-02 (R0003) / VISUAL CHECK OF RH VENT SURGE TANK BURST DISC (EXTERNAL) | H | 1658:35 | 17095:09 | 2026-03-30 |  | 0 | 2'000 | 1 | 17 | 0.025
B-LAA | D | EO-PW-73-0020/REPETITIVE REPLACEMENT OF THE MAIN FUEL FILTER (PW1100G) | H | 1668:40 | 17105:14 | 2026-03-31 |  | 0 | 1'700 | 3 | 1 | 0.16667 | PW1127GA-JM / P770440 | EOE: DO NOT replace fuel filters on both engine in the same ground
B-LAA | Q | HE32-281100-06-1 (R0002) / OPERATIONAL CHECK OF WATER DRAIN VALVES | D | 155 | 31.Mar.2026 | 2026-03-31 |  | 0 | 182 D | 1 | 14 | 0.030556
B-LAB | V | REPLACE 34600017/44872F1 (CARGO FIRE EXTINGUISHER) | D | 155 | 31.Mar.2026 | 2026-03-31 |  | 0 |  | 2 |  | 0.1 | 34600017 / 44872F1
B-LAE | Q | HE32-470000-01-1 (R0004) / REPLACE D-ULPA FILTER ELEMENT | H | 1683:30 | 10757:06 | 2026-04-01 |  | 0 | 7'000 | 1 | 75 | 0.091667 |  | OPS CONTROL PH TASK
B-LAB | V | REPLACE 15-40F80/76004030 (PBE) | D | 156 | 01.Apr.2026 | 2026-04-01 |  | 0 |  | 2 |  | 0.016667 | 15-40F80 / 76004030
B-LAB | V | REPLACE 15-40F80/76004053 (PBE) | D | 156 | 01.Apr.2026 | 2026-04-01 |  | 0 |  | 2 |  | 0.016667 | 15-40F80 / 76004053
B-LAB | V | REPLACE 15-40F80/76004059 (PBE) | D | 156 | 01.Apr.2026 | 2026-04-01 |  | 0 |  | 2 |  | 0.016667 | 15-40F80 / 76004059
B-LAA | V | REPLACE 30903827/2374UD/W282811 (CARTRIDGE) | D | 156 | 01.Apr.2026 | 2026-04-01 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 2 |  | 0.020833 | 30903827 / 2374UD
B-LAB | V | REPLACE 30903886/2050UD/W1588741 (CARTRIDGE) | D | 156 | 01.Apr.2026 | 2026-04-01 | 2026-03-01 | B-LAB-PLN-010426-LM |  | 2 |  | 0.091667 | 30903886 / 2050UD
B-LAB | V | REPLACE 30903886/2122UD/W1588758 (CARTRIDGE) | D | 156 | 01.Apr.2026 | 2026-04-01 | 2026-03-01 | B-LAB-PLN-010426-LM |  | 2 |  | 0.091667 | 30903886 / 2122UD
B-LAB | V | REPLACE D30665-709/L25656 (RAFT-SLIDE,AFT) | D | 156 | 01.Apr.2026 | 2026-04-01 |  | 0 |  | 2 |  | 0.125 | D30665-709 / L25656
B-LAC | D | EO-PW-72-0152/INSPECTION OF THE AIR SEALASSEMBLIES THROUGH THE MAIN GEARBOXHOUSING B | H | 1690:34 | 9719:06 | 2026-04-02 |  | 0 | 1'875 | 2 | 9 | 0.16667 | PW1127GA-JM / P772359 | RH ENG
B-LAC | Q | HE32-353000-01-1 (R0003) / CHECK OF CONNECTING HOSE, MASK AND PRESSURE ON CYLINDER PRESSURE GAUGE | D | 159 | 04.Apr.2026 | 2026-04-04 |  | 0 | 182 D | 1 | 12 | 0.029167
B-LAC | Q | HE32-353000-05-1 (R0003) / VISUAL CHECK OF THE TAMPER SEAL/SERVICEABILITY INDICATION OF THE PROTECTIVE BREATHING EQUIPME | D | 159 | 04.Apr.2026 | 2026-04-04 |  | 0 | 182 D | 1 | 12 | 0.020833
B-LAC | Q | HE32-525111-06-2 (R0002) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AN | D | 159 | 04.Apr.2026 | 2026-04-04 |  | 0 | 182 D | 1 | 12 | 0.052083
B-LAA | D | EOCOM-72-0225/VISUAL INSPECTION OF FAN BLADE COVER TRANSITION AREA (PW1100G-JM) | C | 557 | 6'253 | 2026-04-05 |  | 0 | 1'000 | 2 | 44 | 0.0625 | PW1127GA-JM / P771230
B-LAC | Q | HE32-262441-01-1 (R0004) / CHECK OF THE PRESSURE GAUGE READING OF PORTABLE FIRE EXTINGUISHERS WITH PRESSURE GAUGE IS INS | H | 1728:24 | 9756:56 | 2026-04-05 |  | 0 | 2'000 | 1 | 13 | 0.016667
B-LAA | D | EO-A320-25-1BVT/INSPECTION OF GALLEY 4X FOR CORROSION OF TROLLEY RETAINER ALUMINIUM | D | 161 | 06.Apr.2026 | 2026-04-06 |  | 0 | 182 D | 1 | 11 | 0.041667 | 601888-002001 / 002
B-LAD | D | EOA32-32-0045/CLEAN THE ELECTRICAL CONNECTOR OF MLG DOOR-UPLOCK PROXIMITY-SENSORS (2 | H | 1737:38 | 11667:43 | 2026-04-06 |  | 0 | 3'000 | 2 | 42 | 0.083333
B-LAD | Q | HE32-242000-25-1 (R0001) / OPERATIONAL CHECK OF NETWORK RECONFIGURATION IN CASE OF SINGLE GENERATOR FAILURE | H | 1737:38 | 11667:43 | 2026-04-06 |  | 0 | 3'000 | 1 | 42 | 0.125
B-LAA | Q | HE32-353000-01-1 (R0003) / CHECK OF CONNECTING HOSE, MASK AND PRESSURE ON CYLINDER PRESSURE GAUGE | D | 161 | 06.Apr.2026 | 2026-04-06 |  | 0 | 182 D | 1 | 11 | 0.029167
B-LAA | Q | HE32-353000-05-1 (R0003) / VISUAL CHECK OF THE TAMPER SEAL/SERVICEABILITY INDICATION OF THE PROTECTIVE BREATHING EQUIPME | D | 161 | 06.Apr.2026 | 2026-04-06 |  | 0 | 182 D | 1 | 11 | 0.020833
B-LAA | Q | HE32-ZL-147-02-1 (R0002) / GENERAL VISUAL INSPECTION OF MLG-WELL AND HYDRAULIC COMPARTMENT (EWIS) | D | 161 | 06.Apr.2026 | 2026-04-06 |  | 0 | 365 D | 1 | 55 | 0.038889
B-LAA | Q | HE32-ZL-711-01-1 (R0002) / GENERAL VISUAL INSPECTION OF NOSE GEAR AND NOSE GEAR DOORS (EWIS) | D | 161 | 06.Apr.2026 | 2026-04-06 |  | 0 | 365 D | 1 | 55 | 0.023611
B-LAA | Q | HE32-ZL-731-01-1 (R0002) / GENERAL VISUAL INSPECTION OF LH/RH MAIN LANDING GEAR INCLUDING CYLINDER AND SECONDARY DOORS ( | D | 161 | 06.Apr.2026 | 2026-04-06 |  | 0 | 365 D | 1 | 55 | 0.034028
B-LAD | Q | HE32-292000-05-1 (R0003) / OPERATIONAL CHECK OF RAM AIR TURBINE (RAT) AUTOMATIC DEPLOYMENT | H | 1759:57 | 11690:02 | 2026-04-08 |  | 0 | 4'000 | 1 | 56 | 0.051389
B-LAC | D | EOCOM-72-0225/VISUAL INSPECTION OF FAN BLADE COVER TRANSITION AREA (PW1100G-JM) | C | 570 | 3'344 | 2026-04-09 |  | 0 | 1'000 | 2 | 43 | 0.0625 | PW1127GA-JM / P772359
B-LAB | Q | HE32-344200-03-1 (R0002) / CLEAN THE EXTERNAL SURFACE OF THE RADIO ALTIMETER ANTENNAS | D | 164 | 09.Apr.2026 | 2026-04-09 |  | 0 | 182 D | 1 | 9 | 0.020833
B-LAD | D | EOCOM-32-0324/DETAILED VISUAL INSPECTION OF NLG TORQUE LINK APEX PIN AND NUT | D | 165 | 10.Apr.2026 | 2026-04-10 |  | 0 | 540 D | 2 | 69 | 0.25 |  | EOE: Align with AMS task HE32-322127-01-1 if possible
B-LAB | Q | HE32-344200-01-1 (R0004) / OPERATIONAL CHECK AND DETAILED INSPECTION FOR CONTAMINATION OF RADIO ALTIMETER FAN | H | 1778:17 | 14185:44 | 2026-04-10 |  | 0 | 4'000 | 1 | 55 | 0.068056
B-LAD | Q | HE32-281100-05-1 (R0002) / GENERAL VISUAL INSPECTION OF FUEL TANKS FOR MINOR EXTERNAL LEAKS | D | 166 | 11.Apr.2026 | 2026-04-11 |  | 0 | 182 D | 1 | 8 | 0.016667
B-LAD | Q | HE32-281100-06-1 (R0002) / OPERATIONAL CHECK OF WATER DRAIN VALVES | D | 166 | 11.Apr.2026 | 2026-04-11 |  | 0 | 182 D | 1 | 8 | 0.030556
B-LAD | Q | HE32-344200-03-1 (R0002) / CLEAN THE EXTERNAL SURFACE OF THE RADIO ALTIMETER ANTENNAS | D | 166 | 11.Apr.2026 | 2026-04-11 |  | 0 | 182 D | 1 | 8 | 0.020833
B-LAC | Q | HE32-261300-01-1 (R0003) / OPERATIONAL TEST OF THE APU FIRE AND OVERHEAT DETECTION SYSTEM | H | 1815:34 | 9844:06 | 2026-04-13 |  | 0 | 2'000 | 1 | 9 | 0.0125
B-LAC | Q | HE32-261600-03-1 (R0003) / OPERATIONAL CHECK OF CARGO COMPARTMENT SMOKE DETECTION BY PTT | H | 1815:34 | 9844:06 | 2026-04-13 |  | 0 | 2'000 | 1 | 9 | 0.025
B-LAC | Q | HE32-276400-01-1-01 (R0003) / LUBRICATE LH SPOILER NO 1 TO 5 ACTUATOR ATTACHMENTS | H | 1815:34 | 9844:06 | 2026-04-13 |  | 0 | 2'000 | 1 | 9 | 0.1
B-LAC | Q | HE32-331400-01-1 (R0003) / OPERATIONAL CHECK OF THE LIGHT TEST SYSTEM | H | 1815:34 | 9844:06 | 2026-04-13 |  | 0 | 2'000 | 1 | 9 | 0.023611
B-LAB | D | EOI-11-0001/INSPECT THE CONDITON OF INTERNAL PLACARDS | H | 1824:25 | 14231:52 | 2026-04-14 |  | 0 | 6'000 | 2 | 69 | 0.075
B-LAA | Q | HE32-276400-01-1-02 (R0003) / LUBRICATE SPOILER NO 1 TO 5 ACTUATOR ATTACHMENTS - RH | H | 1824:51 | 17261:25 | 2026-04-14 |  | 0 | 2'000 | 1 | 8 | 0.1
B-LAC | D | EO-PW-72-0152/INSPECTION OF THE AIR SEALASSEMBLIES THROUGH THE MAIN GEARBOXHOUSING B | H | 1842:23 | 9870:55 | 2026-04-16 |  | 0 | 1'875 | 2 | 1 | 0.16667 | PW1127GA-JM / P772061
B-LAB | D | EO-A320-53-1325/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR ACTUATOR FITTING ON KEEL | C | 650 | 5'207 | 2026-04-18 |  | 0 | 2'250 | 1 | 71 | 0.8125 |  | EOE : Accomplishment of this EO is acceptable means to HKE AMS
B-LAD | Q | HE32-276400-01-1-02 (R0003) / LUBRICATE SPOILER NO 1 TO 5 ACTUATOR ATTACHMENTS - RH | H | 1860:18 | 11790:23 | 2026-04-18 |  | 0 | 2'000 | 1 | 6 | 0.1
B-LAD | Q | HE32-281200-01-1-01 (R0003) / VISUAL CHECK OF LH VENT SURGE TANK BURST DISC (EXTERNAL) | H | 1860:18 | 11790:23 | 2026-04-18 |  | 0 | 2'000 | 1 | 6 | 0.025
B-LAD | Q | HE32-281200-01-1-02 (R0003) / VISUAL CHECK OF RH VENT SURGE TANK BURST DISC (EXTERNAL) | H | 1860:18 | 11790:23 | 2026-04-18 |  | 0 | 2'000 | 1 | 6 | 0.025
B-LAD | Q | HE32-291000-15-1 (R0003) / ANALYZE HYDRAULIC FLUID (HYDRAULIC FLUID SAMPLING) | D | 174 | 19.Apr.2026 | 2026-04-19 |  | 0 | 730 D | 1 | 76 | 0.10972
B-LAB | V | REPLACE 3552AAADAACXCD/P17062497 (CYLINDER ASSY-OXYGEN PORTABLE) | D | 174 | 19.Apr.2026 | 2026-04-19 |  | 0 |  | 2 |  | 0.016667 | 3552AAADAACXCD / P17062497
B-LAB | Q | HE32-291000-05-1 (R0003) / DRAIN THE WATER SEPARATOR | H | 1908:26 | 14315:53 | 2026-04-22 |  | 0 | 2'250 | 1 | 15 | 0.027778
B-LAA | Q | HE32-525111-06-2 (R0002) / FUNCTIONAL CHECK OF THE CORRECT ADJUSTMENT OF THE COCKPIT DOOR, ELECTRICAL RELEASE STRIKES AN | D | 178 | 23.Apr.2026 | 2026-04-23 |  | 0 | 182 D | 1 | 2 | 0.052083
B-LAE | Q | HE32-242000-25-1 (R0001) / OPERATIONAL CHECK OF NETWORK RECONFIGURATION IN CASE OF SINGLE GENERATOR FAILURE | H | 1933:57 | 11007:33 | 2026-04-24 |  | 0 | 3'000 | 1 | 35 | 0.125
B-LAE | Q | HE32-291000-05-1 (R0003) / DRAIN THE WATER SEPARATOR | H | 1931:43 | 11005:19 | 2026-04-24 |  | 0 | 2'250 | 1 | 14 | 0.027778
B-LAB | Q | HE32-323100-01-1 (R0003) / BITE CHECK OF LANDING-GEAR CONTROL INTERFACE-UNIT (LGCIU) WITH USE OF MCDU TO ENSURE THAT CON | H | 1946:21 | 14353:48 | 2026-04-25 |  | 0 | 4'000 | 1 | 51 | 0.016667
B-LAE | Q | HE32-290000-05-1 (R0004) / CHECK CLOGGING INDICATORS ON RETURN, CASE DRAIN, GROUND SERVICING, HP DELIVERY, BLEED AIR, WA | H | 1952:00 | 11025:36 | 2026-04-26 |  | 0 | 2'000 | 1 | 2 | 0.12083
B-LAC | D | EOI-49-0006/[131-9A] REMOVE AND DISCARD OIL FILTER ELEMENTS (8069KM) AND (8076KM) | D | 183 | 28.Apr.2026 | 2026-04-28 |  | 0 | 730 D | 2 | 74 | 0.041667 | 3800708-1 / P-7062
B-LAA | Q | HE32-262441-01-1 (R0004) / CHECK OF THE PRESSURE GAUGE READING OF PORTABLE FIRE EXTINGUISHERS WITH PRESSURE GAUGE IS INS | H | 1975:15 | 17411:49 | 2026-04-28 |  | 0 | 2'000 | 1 | 1 | 0.016667
B-LAD | D | EOCOM-72-0225/VISUAL INSPECTION OF FAN BLADE COVER TRANSITION AREA (PW1100G-JM) | C | 660 | 4'546 | 2026-04-30 |  | 0 | 1'000 | 2 | 34 | 0.0625 | PW1127GA-JM / P770277
B-LAB | Q | HE32-290000-05-1 (R0004) / CHECK CLOGGING INDICATORS ON RETURN, CASE DRAIN, GROUND SERVICING, HP DELIVERY, BLEED AIR, WA | H | 1991:37 | 14399:04 | 2026-04-30 |  | 0 | 2'000 | 1 | 0 | 0.12083
B-LAE | V | REPLACE 21435-00/SD111740 (LF-ULB) | D | 185 | 30.Apr.2026 | 2026-04-30 |  | 0 |  | 2 |  | 0.05 | 21435-00 / SD111740
B-LAA | V | REPLACE 34600017/45084F1/W406805 (CARGO FIRE EXTINGUISHER) | D | 185 | 30.Apr.2026 | 2026-04-30 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 2 |  | 0.1 | 34600017 / 45084F1
B-LAA | V | REPLACE 34600017/45091F1/W406803 (CARGO FIRE EXTINGUISHER) | D | 185 | 30.Apr.2026 | 2026-04-30 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 2 |  | 0.1 | 34600017 / 45091F1
B-LAE | V | REPLACE 3552AAADAACXCD/P16072978 (CYLINDER ASSY-OXYGEN PORTABLE) | D | 185 | 30.Apr.2026 | 2026-04-30 |  | 0 |  | 2 |  | 0.016667 | 3552AAADAACXCD / P16072978
B-LAB | V | REPLACE UPK-HKG-01/EUK-034N (UNIVERAL PRECAUTION KIT) | D | 185 | 30.Apr.2026 | 2026-04-30 |  | 0 |  | 2 |  | 0.0125 | UPK-HKG-01 / EUK-034N
B-LAD | V | REPLACE UPK-HKG-01/EUK-201 (UNIVERAL PRECAUTION KIT) | D | 185 | 30.Apr.2026 | 2026-04-30 |  | 0 |  | 2 |  | 0.0125 | UPK-HKG-01 / EUK-201
B-LAA | V | REPLACE 30903886/0102UE/W282813 (CARTRIDGE) | D | 186 | 01.May.2026 | 2026-05-01 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 2 |  | 0.091667 | 30903886 / 0102UE
B-LAA | V | REPLACE 30903886/0103UE/W282815 (CARTRIDGE) | D | 186 | 01.May.2026 | 2026-05-01 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 2 |  | 0.091667 | 30903886 / 0103UE
B-LAA | V | REPLACE 30903886/0104UE/W282814 (CARTRIDGE) | D | 186 | 01.May.2026 | 2026-05-01 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 2 |  | 0.091667 | 30903886 / 0104UE
B-LAA | V | REPLACE 30903886/0106UE/W282817 (CARTRIDGE) | D | 186 | 01.May.2026 | 2026-05-01 | 2025-11-01 | B-LAA-PLN-7.5K-OOP_2025 |  | 2 |  | 0.091667 | 30903886 / 0106UE
B-LAB | V | REPLACE 30903886/0239UE/W1588740 (CARTRIDGE) | D | 186 | 01.May.2026 | 2026-05-01 | 2026-04-03 | B-LAB-PLN-010526-LM |  | 2 |  | 0.091667 | 30903886 / 0239UE
B-LAB | V | REPLACE 30903886/0248UE/W1588727 (CARTRIDGE) | D | 186 | 01.May.2026 | 2026-05-01 | 2026-04-03 | B-LAB-PLN-010526-LM |  | 2 |  | 0.091667 | 30903886 / 0248UE
B-LAD | D | EO-A320-53-1484/W487973 /FUSELAGE - FUSELAGE GENERAL - APPLY PROTECTIVE ADHESIVE ABS5631 ON CAR | D | 192 | 07.May.2026 | 2026-05-07 | 2026-05-23 | B-LAD-PLN-MOD_2026 | Before 31.Dec.2025 | 2 | 101 |  |  | TS agree bridging to next C / structure check
B-LAD | Q | HE32-ZL-147-02-1 (R0002) / GENERAL VISUAL INSPECTION OF MLG-WELL AND HYDRAULIC COMPARTMENT (EWIS) | D | 192 | 07.May.2026 | 2026-05-07 |  | 0 | 365 D | 1 | 47 | 0.038889
B-LAD | Q | HE32-ZL-711-01-1 (R0002) / GENERAL VISUAL INSPECTION OF NOSE GEAR AND NOSE GEAR DOORS (EWIS) | D | 192 | 07.May.2026 | 2026-05-07 |  | 0 | 365 D | 1 | 47 | 0.023611
B-LAD | Q | HE32-ZL-731-01-1 (R0002) / GENERAL VISUAL INSPECTION OF LH/RH MAIN LANDING GEAR INCLUDING CYLINDER AND SECONDARY DOORS ( | D | 192 | 07.May.2026 | 2026-05-07 |  | 0 | 365 D | 1 | 47 | 0.034028
B-LAA | V | REPLACE FAKHKG02SW/EFK-160 (FIRST AID KIT) | ID | 192 | 637 | 2026-05-07 |  | 0 |  | 2 |  | 0.0125 | FAKHKG02SW / EFK-160 | PLN: Please double check if the expiry day of the sad kit is correct.
B-LAE | Q | HE32-ZL-147-02-1 (R0002) / GENERAL VISUAL INSPECTION OF MLG-WELL AND HYDRAULIC COMPARTMENT (EWIS) | D | 193 | 08.May.2026 | 2026-05-08 |  | 0 | 365 D | 1 | 47 | 0.038889
B-LAE | Q | HE32-ZL-711-01-1 (R0002) / GENERAL VISUAL INSPECTION OF NOSE GEAR AND NOSE GEAR DOORS (EWIS) | D | 193 | 08.May.2026 | 2026-05-08 |  | 0 | 365 D | 1 | 47 | 0.023611
B-LAE | Q | HE32-ZL-731-01-1 (R0002) / GENERAL VISUAL INSPECTION OF LH/RH MAIN LANDING GEAR INCLUDING CYLINDER AND SECONDARY DOORS ( | D | 193 | 08.May.2026 | 2026-05-08 |  | 0 | 365 D | 1 | 47 | 0.034028
B-LAB | Q | HE32-256241-05-1 (R0003) / CLEAN DOOR GIRT BAR FITTING STOP LEVERS | C | 738 | 5'295 | 2026-05-11 |  | 0 | 1'110 | 1 | 33 | 0.05
B-LAE | D | EO-A320-53-1325/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR ACTUATOR FITTING ON KEEL | C | 687 | 4'197 | 2026-05-12 |  | 0 | 2'250 | 1 | 69 | 0.8125 |  | EOE : Accomplishment of this EO is acceptable means to HKE AMS
B-LAC | Q | HE32-291000-23-1 (R0001) / DETAILED INSPECTION OF THE PYLON / ENGINE INTERFACE ROD ENDS, ROD ATTACHMENT FITTINGS, INTERF | H | 2133:02 | 10161:34 | 2026-05-13 |  | 0 | 2'500 | 1 | 14 | 0.16944
B-LAC | Q | HE32-291000-24-1 (R0001) / DETAILED INSPECTION OF THE PYLON / ENGINE INTERFACE ROD ENDS, ROD ATTACHMENT FITTINGS, INTERF | H | 2133:02 | 10161:34 | 2026-05-13 |  | 0 | 2'500 | 1 | 14 | 0.16944
B-LAA | V | REPLACE 60592-201/A11275RP (RESERVOIR ASSY) | D | 199 | 14.May.2026 | 2026-05-14 |  | 0 |  | 2 |  | 0.10417 | 60592-201 / A11275RP
B-LAA | Q | HE32-274451-11-1 (R0004) / DETAILED INSPECTION OF THSA UPPER ATTACHMENTS FOR PRIMARY AND SECONDARY LOAD PATH | D | 201 | 16.May.2026 | 2026-05-16 |  | 0 | 304 D | 1 | 33 | 0.086111
B-LAC | V | REPLACE 33600105-4/A5413D1/W282618 (ENGINE FIRE EXTINGUISHER) | D | 201 | 16.May.2026 | 2026-05-16 | 2026-04-16 | B-LAC-PLN-160526-LM |  | 2 |  | 0.12917 | 33600105-4 / A5413D1
B-LAA | Q | HE32-212600-01-1 (R0003) / OPERATIONAL CHECK OF THE AVIONICS EQUIPMENT VENTILATION-SYSTEM VIA MCDU | H | 2184:33 | 17621:07 | 2026-05-18 |  | 0 | 3'000 | 1 | 27 | 0.029167
B-LAA | Q | HE32-212643-07-1 (R0002) / DISCARD THE FILTER CARTRIDGE | H | 2184:33 | 17621:07 | 2026-05-18 |  | 0 | 3'000 | 1 | 27 | 0.031944
B-LAA | Q | HE32-212643-09-1 (R0004) / OPERATIONAL CHECK OF NRV FOR FREE MOVEMENT | H | 2184:33 | 17621:07 | 2026-05-18 |  | 0 | 3'000 | 1 | 27 | 0.036111
B-LAA | Q | HE32-212643-10-1 (R0004) / CLEAN THE SYPHON ASSEMBLY (STRAINER) | H | 2184:33 | 17621:07 | 2026-05-18 |  | 0 | 3'000 | 1 | 27 | 0.027778
B-LAA | Q | HE32-261700-03-1 (R0003) / OPERATIONAL CHECK OF LAVATORY SMOKE DETECTION BY CFDS TO CONFIRM WARNINGS CAN BE DISPLAYED | H | 2184:33 | 17621:07 | 2026-05-18 |  | 0 | 3'000 | 1 | 27 | 0.0083333
B-LAA | Q | HE32-262200-02-1 (R0004) / OPERATIONAL CHECK OF AUTOMATIC FIRE EXTINGUISHING CIRCUIT AND TEST APU LP FUEL VALVE OPERATIO | H | 2184:33 | 17621:07 | 2026-05-18 |  | 0 | 3'000 | 1 | 27 | 0.0125
B-LAB | Q | HE32-256551-01-1 (R0002) / DISCARD AND REPLACE MEGAPHONE BATTERIES | D | 204 | 19.May.2026 | 2026-05-19 |  | 0 | 365 D | 1 | 44 | 0.020833
B-LAB | Q | HE32-561000-02-1 (R0003) / DETAILED INSPECTION OF ALL COCKPIT WINDOWS FROM OUTSIDE INCLUDING SEALS | D | 204 | 19.May.2026 | 2026-05-19 |  | 0 | 365 D | 1 | 44 | 0.054167
B-LAB | Q | HE32-ZL-400-02-4 (R0003) / GENERAL VISUAL INSPECTION OF POWERPLANTS, NACELLES AND PYLONS | D | 204 | 19.May.2026 | 2026-05-19 |  | 0 | 365 D | 1 | 44 | 0.011111
B-LAB | V | REPLACE FAKHKG02SW/EFK-169 (FIRST AID KIT) | ID | 204 | 502 | 2026-05-19 |  | 0 |  | 2 |  | 0.0125 | FAKHKG02SW / EFK-169 | PLN: Please double check if the expiry day of the sad kit is correct.
B-LAC | Q | HE32-291000-05-1 (R0003) / DRAIN THE WATER SEPARATOR | H | 2217:23 | 10245:55 | 2026-05-21 |  | 0 | 2'250 | 1 | 1 | 0.027778
B-LAA | V | REPLACE 3552AAADAACXCD/P11120667 (CYLINDER ASSY-OXYGEN PORTABLE) | D | 206 | 21.May.2026 | 2026-05-21 |  | 0 |  | 2 |  | 0.016667 | 3552AAADAACXCD / P11120667
B-LAC | D | EO-VSB-26-0001/FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 210 | 25.May.2026 | 2026-05-25 |  | 0 | 365 D | 1 | 42 | 0.020833 | P3APP003010A / 000428
B-LAC | D | EO-VSB-26-0001/FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 210 | 25.May.2026 | 2026-05-25 |  | 0 | 365 D | 1 | 42 | 0.020833 | P3APP003010A / 000331
B-LAC | D | EO-VSB-26-0001/FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 210 | 25.May.2026 | 2026-05-25 |  | 0 | 365 D | 1 | 42 | 0.020833 | P3APP003010A / 000146
B-LAC | D | EO-VSB-26-0001/FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 210 | 25.May.2026 | 2026-05-25 |  | 0 | 365 D | 1 | 42 | 0.020833 | P3APP003010A / 000309
B-LAE | Q | HE32-256241-05-1 (R0003) / CLEAN DOOR GIRT BAR FITTING STOP LEVERS | C | 742 | 4'252 | 2026-05-27 |  | 0 | 1'110 | 1 | 33 | 0.05
B-LAD | Q | HE32-274451-11-1 (R0004) / DETAILED INSPECTION OF THSA UPPER ATTACHMENTS FOR PRIMARY AND SECONDARY LOAD PATH | D | 214 | 29.May.2026 | 2026-05-29 |  | 0 | 304 D | 1 | 29 | 0.086111
B-LAC | D | EO-A320-31-1718/INTRODUCE FDIU SOFTWARE STD DFDRS FS3.1 (TELEDYNE) | D | 215 | 30.May.2026 | 2026-05-30 |  | 0 | Before 30.May.2026 | 2 | 98 | 0.0625
B-LAE | D | EO-A320-31-1718/W1574418 /INTRODUCE FDIU SOFTWARE STD DFDRS FS3.1 (TELEDYNE) | D | 215 | 30.May.2026 | 2026-05-30 |  | 0 | Before 30.May.2026 | 2 | 98
B-LAD | V | REPLACE UPK-HKG-01/EUK-017 (UNIVERAL PRECAUTION KIT) | D | 216 | 31.May.2026 | 2026-05-31 |  | 0 |  | 2 |  | 0.0125 | UPK-HKG-01 / EUK-017
B-LAA | D | EOCOM-72-0225/VISUAL INSPECTION OF FAN BLADE COVER TRANSITION AREA (PW1100G-JM) | C | 752 | 6'448 | 2026-06-01 |  | 0 | 1'000 | 2 | 24 | 0.0625 | PW1127GA-JM / P770440
B-LAA | V | REPLACE 74-20/B050510 (HAND FIRE EXTINGUISHER) | D | 217 | 01.Jun.2026 | 2026-06-01 |  | 0 |  | 2 |  | 0.016667 | 74-20 / B050510
B-LAE | V | REPLACE MF20-534/B161841 (MASK-FULL FACE QUICK DONNING) | D | 217 | 01.Jun.2026 | 2026-06-01 |  | 0 |  | 2 |  | 0.083333 | MF20-534 / B161841
B-LAE | V | REPLACE MF20-534/B161938 (MASK-FULL FACE QUICK DONNING) | D | 217 | 01.Jun.2026 | 2026-06-01 |  | 0 |  | 2 |  | 0.083333 | MF20-534 / B161938
B-LAE | V | REPLACE MF20-534/B161941 (MASK-FULL FACE QUICK DONNING) | D | 217 | 01.Jun.2026 | 2026-06-01 |  | 0 |  | 2 |  | 0.083333 | MF20-534 / B161941
B-LAE | V | REPLACE MF20-534/B162002 (MASK-FULL FACE QUICK DONNING) | D | 217 | 01.Jun.2026 | 2026-06-01 |  | 0 |  | 2 |  | 0.083333 | MF20-534 / B162002
B-LAA | D | EOI-57-0002/DETAILED VISUAL INSPECTIONS OF LH/RH WING SLAT TRACK CLOSING PLATES | D | 218 | 02.Jun.2026 | 2026-06-02 |  | 0 | 608 D | 2 | 64 | 0.10417
B-LAB | Q | HE32-31-SCME-010 (R0005) / READOUT PROCEDURE FOR RECORDING INSPECTION OF FDR SYSTEM | D | 220 | 04.Jun.2026 | 2026-06-04 | 2026-03-04 | B-LAB-PLN-040326-LM | 365 D | 1 | 75 | 0.048611
B-LAC | V | REPLACE D31865-112/A12566 (SLIDE-OFF-WING) | D | 220 | 04.Jun.2026 | 2026-06-04 |  | 0 |  | 2 |  | 0.10417 | D31865-112 / A12566
B-LAD | D | EOA32-20-0006/W547274 /DETAILED INSPECTION OF BONDING LEADS LOCATED ON THE MOVABLE SURFACES | D | 221 | 05.Jun.2026 | 2026-06-05 | 2026-05-23 | B-LAD-PLN-2C_2026 | 1'095 D | 2 | 99 | 0.75 |  | 1C
B-LAB | D | EOCOM-72-0225/VISUAL INSPECTION OF FAN BLADE COVER TRANSITION AREA (PW1100G-JM) | C | 830 | 5'387 | 2026-06-05 |  | 0 | 1'000 | 2 | 17 | 0.0625 | PW1127GA-JM / P770214
B-LAE | Q | HE32-212600-01-1 (R0003) / OPERATIONAL CHECK OF THE AVIONICS EQUIPMENT VENTILATION-SYSTEM VIA MCDU | H | 2396:54 | 11470:30 | 2026-06-06 |  | 0 | 3'000 | 1 | 20 | 0.029167
B-LAE | Q | HE32-212643-07-1 (R0002) / DISCARD THE FILTER CARTRIDGE | H | 2396:54 | 11470:30 | 2026-06-06 |  | 0 | 3'000 | 1 | 20 | 0.031944
B-LAE | Q | HE32-212643-09-1 (R0004) / OPERATIONAL CHECK OF NRV FOR FREE MOVEMENT | H | 2396:54 | 11470:30 | 2026-06-06 |  | 0 | 3'000 | 1 | 20 | 0.036111
B-LAE | Q | HE32-212643-10-1 (R0004) / CLEAN THE SYPHON ASSEMBLY (STRAINER) | H | 2396:54 | 11470:30 | 2026-06-06 |  | 0 | 3'000 | 1 | 20 | 0.027778
B-LAE | Q | HE32-261700-03-1 (R0003) / OPERATIONAL CHECK OF LAVATORY SMOKE DETECTION BY CFDS TO CONFIRM WARNINGS CAN BE DISPLAYED | H | 2396:54 | 11470:30 | 2026-06-06 |  | 0 | 3'000 | 1 | 20 | 0.0083333
B-LAE | Q | HE32-262200-02-1 (R0004) / OPERATIONAL CHECK OF AUTOMATIC FIRE EXTINGUISHING CIRCUIT AND TEST APU LP FUEL VALVE OPERATIO | H | 2396:54 | 11470:30 | 2026-06-06 |  | 0 | 3'000 | 1 | 20 | 0.0125
B-LAD | D | EOA32-24-0010/OPENING AND CLOSING ALL CIRCUIT BREAKERS OF A32 SERIES AIRCRAFT | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 2 | 79 | 0.020833
B-LAD | D | EOD-25-0016/W1510657 /A320-271N FLEET CARPETS REPLACEMENT | D | 223 | 07.Jun.2026 | 2026-06-07 | 2026-05-23 | B-LAD-PLN-1C_2026_PT | 1'095 D | 2 | 99 | 0.1875 |  | EOE: Assign either EOD-25-0016 / EOA32-25-0141 but not both
B-LAD | D | EOI-57-0002/DETAILED VISUAL INSPECTIONS OF LH/RH WING SLAT TRACK CLOSING PLATES | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | Before 31.Dec.2023 | 2 | 98 | 0.10417
B-LAD | Q | HE32-200002-01-1-01 (R0002) / GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON HARNESSES 405VB TO 409VB FOR LH THS | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.041667
B-LAD | Q | HE32-200002-01-1-02 (R0002) / GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON HARNESSES 400VB TO 404VB FOR RH THS | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.041667
B-LAD | Q | HE32-237100-01-1 (R0002) / OPERATIONAL CHECK OF CVR AND CVR-CHANNEL RECORDING | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.033333
B-LAD | Q | HE32-243000-13-1 (R0001) / CLEAN THE TRANSFORMER RECTIFIER (TR) 1 AND 2 | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'461 D | 1 | 84 | 0.044444
B-LAD | Q | HE32-243000-14-1 (R0001) / CLEANING OF THE ESSENTIAL TRANSFORMER RECTIFIER | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'461 D | 1 | 84 | 0.041667
B-LAD | Q | HE32-256535-01-1 (R0006) / OPERATIONAL CHECK OF ELT SYSTEM BY MANUAL ACTIVATION | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.10694
B-LAD | Q | HE32-256535-04-1 (R0005) / GENERAL VISUAL INSPECTION OF EXTERNAL ELT ANTENNA | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.041667
B-LAD | Q | HE32-256536-01-1 (R0002) / OPERATIONAL CHECK OF THE LOW-FREQUENCY UNDERWATER LOCATOR BEACON (ULB) | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.047222
B-LAD | Q | HE32-262541-04-1 (R0002) / VISUAL CHECK OF FIRE EXTINGUISHER BOTTLE PRESSURE READING | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.013889
B-LAD | Q | HE32-272100-12-1 (R0001) / LUBRICATE RUDDER CONTROL CABLES IN REAR PART (ZONE 310) | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.027778
B-LAD | Q | HE32-275451-01-1 (R0002) / REPLENISH FLAP PCU GEARBOX TO CONFIRM FLUID LEVEL | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.077778
B-LAD | Q | HE32-278451-01-1 (R0002) / REPLENISH SLAT PCU GEARBOX TO CONFIRM FLUID LEVEL | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.011111
B-LAD | Q | HE32-281247-01-1-01 (R0002) / VISUAL CHECK OF LHW NACA INTAKE FOR SIGNS OF BLOCKAGE | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.011111
B-LAD | Q | HE32-281247-01-1-02 (R0002) / VISUAL CHECK OF RHW NACA INTAKE FOR SIGNS OF BLOCKAGE | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.0097222
B-LAD | Q | HE32-291000-06-1 (R0002) / FUNCTIONAL CHECK OF THE POWER TRANSFER UNIT (PTU) YELLOW TO GREEN | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.0083333
B-LAD | Q | HE32-291000-20-1 (R0002) / OPERATIONAL CHECK OF EDP DEPRESSURIZATION | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.083333
B-LAD | Q | HE32-321113-04-1-01 (R0002) / FUNCTIONAL CHECK OF LEFT MLG SHOCK ABSORBER CHARGE PRESSURE | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.033333
B-LAD | Q | HE32-321113-04-1-02 (R0002) / FUNCTIONAL CHECK OF RIGHT MLG SHOCK ABSORBER CHARGE PRESSURE | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.033333
B-LAD | Q | HE32-323100-05-1 (R0002) / DETAILED INSPECTION OF NOSE GEAR DOOR OPERATING MECHANISM | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.030556
B-LAD | Q | HE32-353000-07-1 (R0003) / DETAILED INSPECTION OF PORTABLE OXYGEN MASK | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.016667
B-LAD | Q | HE32-491200-B2-1 (R0003) / GENERAL VISUAL INSPECTION OF APU SUSPENSION SYSTEM FOR CONDITION AND SECURITY | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.034028
B-LAD | Q | HE32-491300-B1-1 (R0004) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.086111
B-LAD | Q | HE32-498000-B1-1 (R0003) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.013889
B-LAD | Q | HE32-521000-02-1 (R0002) / FUNCTIONAL CHECK OF DOOR SUSPENSION | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.05
B-LAD | Q | HE32-521000-04-1 (R0002) / DETAILED INSPECTION OF PASSENGER/CREW DOOR FOR INTEGRITY AND GOOD ADJUSTMENT OF MECHANISMS (I | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.13611
B-LAD | Q | HE32-521121-02-1-01 (R0004) / LUBRICATE THE SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM OF LH FWD DOOR | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.30556
B-LAD | Q | HE32-521121-02-1-02 (R0004) / LUBRICATE THE SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM OF RH FWD DOOR | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.30556
B-LAD | Q | HE32-521121-02-1-03 (R0004) / LUBRICATE THE SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM OF LH AFT DOOR | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.30556
B-LAD | Q | HE32-521121-02-1-04 (R0004) / LUBRICATE THE SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM OF RH AFT DOOR | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.30556
B-LAD | Q | HE32-524100-02-1 (R0002) / LUBRICATE EXTERIOR AVIONIC COMPARTMENT DOOR HANDLE | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.016667
B-LAD | Q | HE32-531151-02-1 (R0001) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.040278
B-LAD | Q | HE32-531176-02-1 (R0001) / GENERAL VISUAL INSPECTION OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BET | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.0041667
B-LAD | Q | HE32-531178-02-1 (R0003) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF FRAMEWORK AND EX | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.0041667
B-LAD | Q | HE32-531182-02-1 (R0001) / DETAILED INSPECTION OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 AND FR8 FRAMES, I | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.17222
B-LAD | Q | HE32-531900-03-1 (R0002) / OPERATIONAL CHECK OF PISTON TYPE DRAIN VALVES IN LOWER FUSELAGE SHELL FROM OUTSIDE | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.05
B-LAD | Q | HE32-533900-01-1 (R0002) / OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE HOLES IN PRESSURE FLOOR FROM MLG BAY | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.0083333
B-LAD | Q | HE32-534134-02-1 (R0001) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.026389
B-LAD | Q | HE32-535900-02-1 (R0002) / OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE AT BULK CARGO COMPARTMENT DOOR FROM OUTSIDE | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.013889
B-LAD | Q | HE32-561200-02-1 (R0002) / LUBRICATE THE COCKPIT SLIDING WINDOW TRACKS | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.016667
B-LAD | Q | HE32-783200-W6-1-01 (R0002) / FUNCTIONAL CHECK OF PRESSURE RELIEF DOOR LATCH TENSION OF NO.1 ENG | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.025
B-LAD | Q | HE32-783200-W6-1-02 (R0002) / FUNCTIONAL CHECK OF PRESSURE RELIEF DOOR LATCH TENSION OF NO.2 ENG | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.025
B-LAD | Q | HE32-ZL-131-01-1 (R0004) / GENERAL VISUAL INSPECTION OF FORWARD CARGO COMPARTMENT (EWIS) | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.044444
B-LAD | Q | HE32-ZL-151-01-1 (R0004) / GENERAL VISUAL INSPECTION OF AFT CARGO COMPARTMENT (AS FAR AS VISIBLE, IF ACT IS INSTALLED) ( | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.044444
B-LAD | Q | HE32-ZL-161-01-1 (R0002) / GENERAL VISUAL INSPECTION OF BULK CARGO COMPARTMENT (EWIS) | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.023611
B-LAD | Q | HE32-ZL-315-01-1 (R0003) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.019444
B-LAD | Q | HE32-ZL-437-01-4-01 (R0003) / GENERAL VISUAL INSPECTION OF FAN COWL OF NO.1 ENG (EWIS) | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.027778
B-LAD | Q | HE32-ZL-437-01-4-02 (R0003) / GENERAL VISUAL INSPECTION OF FAN COWL OF NO.2 ENG (EWIS) | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.027778
B-LAD | Q | HE32-ZL-734-01-1 (R0002) / GENERAL VISUAL INSPECTION OF MAIN LANDING GEAR MAIN DOORS (EWIS) | D | 223 | 07.Jun.2026 | 2026-06-07 |  | 0 | 1'095 D | 1 | 79 | 0.022222
B-LAA | Q | HE32-344200-01-1 (R0004) / OPERATIONAL CHECK AND DETAILED INSPECTION FOR CONTAMINATION OF RADIO ALTIMETER FAN | H | 2428:18 | 17864:52 | 2026-06-09 |  | 0 | 4'000 | 1 | 39 | 0.068056
B-LAD | Q | HE32-212600-01-1 (R0003) / OPERATIONAL CHECK OF THE AVIONICS EQUIPMENT VENTILATION-SYSTEM VIA MCDU | H | 2437:31 | 12367:36 | 2026-06-10 |  | 0 | 3'000 | 1 | 18 | 0.029167
B-LAD | Q | HE32-212643-07-1 (R0002) / DISCARD THE FILTER CARTRIDGE | H | 2437:31 | 12367:36 | 2026-06-10 |  | 0 | 3'000 | 1 | 18 | 0.031944
B-LAD | Q | HE32-212643-09-1 (R0004) / OPERATIONAL CHECK OF NRV FOR FREE MOVEMENT | H | 2437:31 | 12367:36 | 2026-06-10 |  | 0 | 3'000 | 1 | 18 | 0.036111
B-LAD | Q | HE32-212643-10-1 (R0004) / CLEAN THE SYPHON ASSEMBLY (STRAINER) | H | 2437:31 | 12367:36 | 2026-06-10 |  | 0 | 3'000 | 1 | 18 | 0.027778
B-LAD | Q | HE32-261700-03-1 (R0003) / OPERATIONAL CHECK OF LAVATORY SMOKE DETECTION BY CFDS TO CONFIRM WARNINGS CAN BE DISPLAYED | H | 2437:31 | 12367:36 | 2026-06-10 |  | 0 | 3'000 | 1 | 18 | 0.0083333
B-LAD | Q | HE32-262200-02-1 (R0004) / OPERATIONAL CHECK OF AUTOMATIC FIRE EXTINGUISHING CIRCUIT AND TEST APU LP FUEL VALVE OPERATIO | H | 2437:31 | 12367:36 | 2026-06-10 |  | 0 | 3'000 | 1 | 18 | 0.0125
B-LAB | Q | HE32-275446-01-1-01 (R0002) / LUBRICATE FLAP TRACK 1 DRIVE LEVER ARM AND ALL CARRIAGE ROLLERS ON ALL FLAP TRACKS OF THE | D | 229 | 13.Jun.2026 | 2026-06-13 |  | 0 | 304 D | 1 | 24 | 0.055556
B-LAD | D | EOA32-24-0016/APPLY TEMPORARY PROTECTION TO END FITTINGS OF A32 SERIES AIRCRAFT OF E | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 36 MT | 2 | 78 | 0.055556 |  | EOE: Plan with HE32-ZL-575-01-1 with standard C CHK package
B-LAD | Q | HE32-200435-02-1-01 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE FAN COMPARTMENT OF NO.1 ENG (EWIS) | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.027778
B-LAD | Q | HE32-200435-02-1-02 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE FAN COMPARTMENT OF NO.2 ENG (EWIS) | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.027778
B-LAD | Q | HE32-200453-02-1-01 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE CORE COMPARTMENT OF NO.1 ENG (EWIS) | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.05
B-LAD | Q | HE32-200453-02-1-02 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE CORE COMPARTMENT OF NO.2 ENG (EWIS) | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.05
B-LAD | Q | HE32-212600-08-1 (R0003) / OPERATIONAL CHECK OF AIR INLET CHECK VALVE 2150HM | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.027083
B-LAD | Q | HE32-272100-08-1 (R0002) / LUBRICATE THE RUDDER PEDAL ADJUSTMENT MECHANISM | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.077778
B-LAD | Q | HE32-272400-03-1 (R0001) / LUBRICATE RUDDER HINGE BEARING NO. 6 | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.088889
B-LAD | Q | HE32-272400-06-1 (R0002) / LUBRICATE THE RUDDER SERVOCONTROL ROD EYE END BEARING | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.077778
B-LAD | Q | HE32-273400-02-2-01 (R0002) / FUNCTIONAL CHECK OF THE LH ELEVATOR SERVOCONTROL BEARINGS FOR EXCESSIVE PLAY AND CONDITION | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.047222
B-LAD | Q | HE32-273400-02-2-02 (R0002) / FUNCTIONAL CHECK OF THE RH ELEVATOR SERVOCONTROL BEARINGS FOR EXCESSIVE PLAY AND CONDITION | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.047222
B-LAD | Q | HE32-273400-08-1 (R0002) / LUBRICATE THE ELEVATOR SERVOCONTROL ROD EYE END BEARING | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.11389
B-LAD | Q | HE32-274000-01-1 (R0001) / LUBRICATE THE THS BEARINGS AND ATTACHMENT FITTINGS | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.089583
B-LAD | Q | HE32-274100-03-1 (R0001) / LUBRICATE THE THS MECHANICAL CONTROL CHAINS AND REAR CABLE (AREA OF TENSION REGULATOR) | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.2875
B-LAD | Q | HE32-291000-25-1 (R0001) / OPERATIONAL CHECK OF PORT D CHECK VALVE OF PTU MANIFOLD IN GREEN AND YELLOW HYDRAULIC SYSTEM | D | 230 | 14.Jun.2026 | 2026-06-14 | 2026-05-23 | B-LAD-PLN-MOD_2026 |  | 1 |  | 0.22917 |  | MR info: AMS I5R0 Bridging applied. Do not defer this task.
B-LAD | Q | HE32-303100-01-1-01 (R0001) / FUNCTIONAL CHECK OF THE INSULATION RESISTANCE OF NO.1 PITOT PROBE HEATER | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.066667
B-LAD | Q | HE32-303100-01-1-02 (R0001) / FUNCTIONAL CHECK OF THE INSULATION RESISTANCE OF NO.2 PITOT PROBE HEATER | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.066667
B-LAD | Q | HE32-303100-01-1-03 (R0001) / FUNCTIONAL CHECK OF THE INSULATION RESISTANCE OF NO.3 PITOT PROBE HEATER | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.066667
B-LAD | Q | HE32-322113-01-1 (R0002) / FUNCTIONAL CHECK OF NLG SHOCK ABSORBER CHARGE PRESSURE AND FLUID LEVEL | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.25
B-LAD | Q | HE32-323100-02-1 (R0003) / DETAILED INSPECTION OF GEAR UPLOCK AND DOOR UPLOCK UNITS AND ROLLERS/PINS | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.1
B-LAD | Q | HE32-34-SCME-010 (R0002) / FUNCTIONAL TEST OF THE ATC/MODE S TRANSPONDER AND VERIFICATION OF THE MODE S ADDRESS | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.095833
B-LAD | Q | HE32-351000-01-1 (R0002) / OPERATIONAL CHECK OF FLIGHT CREW OXYGEN SYSTEM | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.05
B-LAD | Q | HE32-351241-01-1 (R0002) / DETAILED INSPECTION OF OXYGEN MASKS (OUT OF BOX) WITH HARNESS INFLATED | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.0625
B-LAD | Q | HE32-383100-02-1 (R0002) / CLEAN AND DO AN INSPECTION OF THE WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.1875
B-LAD | Q | HE32-383100-05-1 (R0002) / DETAILED INSPECTION OF CLEANLINESS INSIDE THE WASTE TANK | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.28472
B-LAD | Q | HE32-521000-14-1 (R0003) / LUBRICATE THE HINGE ARM SUPPORT FITTING BEARINGS OF PASSENGER DOORS | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.052778
B-LAD | Q | HE32-521121-01-1 (R0003) / LUBRICATE THE EXTERIOR CONTROL HANDLES AND TELESCOPIC ARMS OF PASSENGER DOORS | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.083333
B-LAD | Q | HE32-523000-01-1 (R0002) / LUBRICATIE THE CARGO DOORS | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.15833
B-LAD | Q | HE32-523000-03-1 (R0002) / LUBRICATE EXTERIOR CARGO DOOR HANDLE | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.066667
B-LAD | Q | HE32-523300-01-1 (R0002) / LUBRICATE THE BULK CARGO COMPARTMENT DOOR HANDLE AND HINGE ARM BEARINGS | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.033333
B-LAD | Q | HE32-ZL-100-02-1 (R0002) / GENERAL VISUAL INSPECTION OF THE LOWER HALF OF THE FUSELAGE | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.034028
B-LAD | Q | HE32-ZL-123-02-1 (R0002) / GENERAL VISUAL INSPECTION OF NOSE GEAR WELL (EWIS) | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.013194
B-LAD | Q | HE32-ZL-191-01-2 (R0004) / GENERAL VISUAL INSPECTION OF AIR CONDITIONING COMPARTMENT AND FAIRINGS (EWIS) | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.15833
B-LAD | Q | HE32-ZL-435-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF FAN COMPARTMENT OF NO.1 ENG (EWIS) | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.017361
B-LAD | Q | HE32-ZL-435-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF FAN COMPARTMENT OF NO.2 ENG (EWIS) | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.017361
B-LAD | Q | HE32-ZL-831-01-1 (R0002) / GENERAL VISUAL INSPECTION OF AFT PASSENGER/CREW DOORS INCLUDING DOOR STOPS ON FUSELAGE DOOR F | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.050694
B-LAD | Q | HE32-ZL-831-04-1 (R0002) / GENERAL VISUAL INSPECTION OF FWD PASSENGER/CREW DOORS INCLUDING DOOR STOPS ON FUSELAGE DOOR F | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 | 730 D | 1 | 68 | 0.050694
B-LAA | V | REPLACE 74-20/B050027 (HAND FIRE EXTINGUISHER) | D | 230 | 14.Jun.2026 | 2026-06-14 |  | 0 |  | 2 |  | 0.016667 | 74-20 / B050027
B-LAC | V | REPLACE 33600105-4/A5856D1/W282620 (ENGINE FIRE EXTINGUISHER) | D | 231 | 15.Jun.2026 | 2026-06-15 | 2026-04-16 | B-LAC-PLN-160526-LM |  | 2 |  | 0.12917 | 33600105-4 / A5856D1
B-LAC | V | REPLACE 33600105-4/A5857D1/W282619 (ENGINE FIRE EXTINGUISHER) | D | 231 | 15.Jun.2026 | 2026-06-15 | 2026-04-16 | B-LAC-PLN-160526-LM |  | 2 |  | 0.12917 | 33600105-4 / A5857D1
B-LAA | D | EO-A320-53-1325/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR ACTUATOR FITTING ON KEEL | C | 816 | 6'512 | 2026-06-19 |  | 0 | 2'250 | 1 | 63 | 0.8125 |  | EOE : Accomplishment of this EO is acceptable means to HKE AMS
B-LAA | Q | HE32-275446-01-1-02 (R0002) / LUBRICATE FLAP TRACK 1 DRIVE LEVER ARM AND ALL CARRIAGE ROLLERS ON ALL FLAP TRACKS OF THE | D | 237 | 21.Jun.2026 | 2026-06-21 |  | 0 | 304 D | 1 | 22 | 0.055556
B-LAE | V | REPLACE 34600017/54358F1 (CARGO FIRE EXTINGUISHER) | D | 237 | 21.Jun.2026 | 2026-06-21 |  | 0 |  | 2 |  | 0.1 | 34600017 / 54358F1
B-LAE | V | REPLACE 34600017/54363F1 (CARGO FIRE EXTINGUISHER) | D | 237 | 21.Jun.2026 | 2026-06-21 |  | 0 |  | 2 |  | 0.1 | 34600017 / 54363F1
B-LAA | Q | HE32-323100-01-1 (R0003) / BITE CHECK OF LANDING-GEAR CONTROL INTERFACE-UNIT (LGCIU) WITH USE OF MCDU TO ENSURE THAT CON | H | 2564:14 | 18000:48 | 2026-06-22 |  | 0 | 4'000 | 1 | 35 | 0.016667
B-LAB | D | EOA32-11-0029/INSPECT AIRPLANE EXTERIOR PLACARDS/MARKINGS` CONDITION | H | 2577:15 | 14984:42 | 2026-06-23 |  | 0 | 3'000 | 2 | 14 | 0.034722
B-LAC | Q | HE32-275446-01-1-01 (R0002) / LUBRICATE FLAP TRACK 1 DRIVE LEVER ARM AND ALL CARRIAGE ROLLERS ON ALL FLAP TRACKS OF THE | D | 240 | 24.Jun.2026 | 2026-06-24 |  | 0 | 304 D | 1 | 21 | 0.055556
B-LAB | Q | HE32-282400-01-1-01 (R0004) / OPERATIONAL CHECK OF LH LP SHUT OFF VALVE AND ITS CONTROL TO ENSURE NO FLOW WHEN SELECTED | H | 2592:33 | 15000:00 | 2026-06-25 | 2027-06-18 | B-LAB-PLN-1C_2027 | Thr. 15'000 | 1 | 126 | 0.038889
B-LAB | Q | HE32-282400-01-1-02 (R0004) / OPERATIONAL CHECK OF RH LP SHUT OFF VALVE AND ITS CONTROL TO ENSURE NO FLOW WHEN SELECTED | H | 2592:33 | 15000:00 | 2026-06-25 | 2027-06-18 | B-LAB-PLN-1C_2027 | Thr. 15'000 | 1 | 126 | 0.038889
B-LAD | Q | HE32-275446-01-1-02 (R0002) / LUBRICATE FLAP TRACK 1 DRIVE LEVER ARM AND ALL CARRIAGE ROLLERS ON ALL FLAP TRACKS OF THE | D | 243 | 27.Jun.2026 | 2026-06-27 |  | 0 | 304 D | 1 | 20 | 0.055556
B-LAC | D | EOA32-11-0029/INSPECT AIRPLANE EXTERIOR PLACARDS/MARKINGS` CONDITION | H | 2633:02 | 10661:34 | 2026-06-28 |  | 0 | 3'000 | 2 | 12 | 0.034722
B-LAC | D | EOA32-32-0045/CLEAN THE ELECTRICAL CONNECTOR OF MLG DOOR-UPLOCK PROXIMITY-SENSORS (2 | H | 2633:02 | 10661:34 | 2026-06-28 |  | 0 | 3'000 | 2 | 12 | 0.083333
B-LAC | Q | HE32-242000-25-1 (R0001) / OPERATIONAL CHECK OF NETWORK RECONFIGURATION IN CASE OF SINGLE GENERATOR FAILURE | H | 2633:02 | 10661:34 | 2026-06-28 |  | 0 | 3'000 | 1 | 12 | 0.125
B-LAC | D | EOCOM-72-0225/VISUAL INSPECTION OF FAN BLADE COVER TRANSITION AREA (PW1100G-JM) | C | 853 | 3'627 | 2026-06-30 |  | 0 | 1'000 | 2 | 14 | 0.0625 | PW1127GA-JM / P772061
B-LAC | V | REPLACE UPK-HKG-01/EUK-626 (UNIVERAL PRECAUTION KIT) | D | 246 | 30.Jun.2026 | 2026-06-30 |  | 0 |  | 2 |  | 0.0125 | UPK-HKG-01 / EUK-626
B-LAB | Q | HE32-278468-01-1-02 (R0002) / LUBRICATE ALL TRACK ROLLERS AND PINIONS OF RH WING | D | 247 | 01.Jul.2026 | 2026-07-01 |  | 0 | 608 D | 1 | 59 | 0.51944
B-LAC | V | REPLACE 30903827/1648UG (CARTRIDGE) | D | 247 | 01.Jul.2026 | 2026-07-01 |  | 0 |  | 2 |  | 0.020833 | 30903827 / 1648UG
B-LAD | V | REPLACE D30665-915/M30984 (RAFT-SLIDE,AFT) | D | 247 | 01.Jul.2026 | 2026-07-01 |  | 0 |  | 2 |  | 0.125 | D30665-915 / M30984
B-LAA | Q | HE32-262300-09-1 (R0003) / DISCARD WATER ADSORBING FILTER | D | 252 | 06.Jul.2026 | 2026-07-06 |  | 0 | 456 D | 1 | 44 | 0.059722
B-LAE | Q | HE32-341300-07-1-01 (R0002) / FLUSH THE LH TOTAL PRESSURE LINE | H | 2715:32 | 11789:08 | 2026-07-06 |  | 0 | 6'000 | 1 | 54 | 0.086111
B-LAE | Q | HE32-783200-W3-1-01 (R0003) / GENERAL VISUAL INSPECTION OF THE THRUST REVERSER FIRE SEALS AND VAPOR BARRIER SEALS OF NO. | H | 2715:32 | 11789:08 | 2026-07-06 |  | 0 | 6'000 | 1 | 54 | 0.063889
B-LAC | Q | HE32-212600-01-1 (R0003) / OPERATIONAL CHECK OF THE AVIONICS EQUIPMENT VENTILATION-SYSTEM VIA MCDU | H | 2728:24 | 10756:56 | 2026-07-07 |  | 0 | 3'000 | 1 | 9 | 0.029167
B-LAC | Q | HE32-212643-07-1 (R0002) / DISCARD THE FILTER CARTRIDGE | H | 2728:24 | 10756:56 | 2026-07-07 |  | 0 | 3'000 | 1 | 9 | 0.031944
B-LAC | Q | HE32-212643-09-1 (R0004) / OPERATIONAL CHECK OF NRV FOR FREE MOVEMENT | H | 2728:24 | 10756:56 | 2026-07-07 |  | 0 | 3'000 | 1 | 9 | 0.036111
B-LAC | Q | HE32-212643-10-1 (R0004) / CLEAN THE SYPHON ASSEMBLY (STRAINER) | H | 2728:24 | 10756:56 | 2026-07-07 |  | 0 | 3'000 | 1 | 9 | 0.027778
B-LAC | Q | HE32-261700-03-1 (R0003) / OPERATIONAL CHECK OF LAVATORY SMOKE DETECTION BY CFDS TO CONFIRM WARNINGS CAN BE DISPLAYED | H | 2728:24 | 10756:56 | 2026-07-07 |  | 0 | 3'000 | 1 | 9 | 0.0083333
B-LAC | Q | HE32-262200-02-1 (R0004) / OPERATIONAL CHECK OF AUTOMATIC FIRE EXTINGUISHING CIRCUIT AND TEST APU LP FUEL VALVE OPERATIO | H | 2728:24 | 10756:56 | 2026-07-07 |  | 0 | 3'000 | 1 | 9 | 0.0125
B-LAD | Q | HE32-344200-01-1 (R0004) / OPERATIONAL CHECK AND DETAILED INSPECTION FOR CONTAMINATION OF RADIO ALTIMETER FAN | H | 2737:38 | 12667:43 | 2026-07-08 |  | 0 | 4'000 | 1 | 31 | 0.068056
B-LAA | V | REPLACE PW1127GA-JM/P771230 (ENGINE FOR 320NEO) | C | 880 | 6'576 | 2026-07-08 |  | 0 |  | 2 |  |  | PW1127GA-JM / P771230
B-LAE | D | EOCOM-72-0225/VISUAL INSPECTION OF FAN BLADE COVER TRANSITION AREA (PW1100G-JM) | C | 920 | 4'430 | 2026-07-17 |  | 0 | 1'000 | 2 | 8 | 0.0625 | PW1127GA-JM / P772225
B-LAB | Q | HE32-292000-04-1 (R0003) / OPERATIONAL CHECK OF RAT MANUAL DEPLOYMENT AND FUNCTIONAL CHECK OF RAT USING GROUND TEST UNIT | H | 2847:39 | 15255:06 | 2026-07-18 |  | 0 | 4'000 | 1 | 28 | 0.38611
B-LAB | Q | HE32-291000-15-1 (R0003) / ANALYZE HYDRAULIC FLUID (HYDRAULIC FLUID SAMPLING) | D | 266 | 20.Jul.2026 | 2026-07-20 |  | 0 | 730 D | 1 | 63 | 0.10972
B-LAD | Q | HE32-323100-01-1 (R0003) / BITE CHECK OF LANDING-GEAR CONTROL INTERFACE-UNIT (LGCIU) WITH USE OF MCDU TO ENSURE THAT CON | H | 2865:51 | 12795:56 | 2026-07-20 |  | 0 | 4'000 | 1 | 28 | 0.016667
B-LAE | Q | HE32-275446-01-1-02 (R0002) / LUBRICATE FLAP TRACK 1 DRIVE LEVER ARM AND ALL CARRIAGE ROLLERS ON ALL FLAP TRACKS OF THE | D | 267 | 21.Jul.2026 | 2026-07-21 |  | 0 | 304 D | 1 | 12 | 0.055556
B-LAC | V | REPLACE FAKHKG02SW/EFK-330F001 (FIRST AID KIT) | ID | 268 | 1'767 | 2026-07-22 |  | 0 |  | 2 |  | 0.0125 | FAKHKG02SW / EFK-330F001 | PLN: Please double check if the expiry day of the sad kit is correct.
B-LAA | V | REPLACE 3552AAADAACXCD/P16050752 (CYLINDER ASSY-OXYGEN PORTABLE) | D | 269 | 23.Jul.2026 | 2026-07-23 |  | 0 |  | 2 |  | 0.016667 | 3552AAADAACXCD / P16050752
B-LAD | V | REPLACE FAKHKG02SW/EFK-108 (FIRST AID KIT) | ID | 269 | 2'444 | 2026-07-23 |  | 0 |  | 2 |  | 0.0125 | FAKHKG02SW / EFK-108 | PLN: Please double check if the expiry day of the sad kit is correct.
B-LAE | Q | HE32-212600-03-1 (R0003) / OPERATIONAL CHECK OF SMOKE CONFIGURATION CONTROL CIRCUIT | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | 12'000 | 1 | 75 | 0.013889
B-LAE | Q | HE32-213100-01-1 (R0003) / OPERATIONAL TEST OF THE PRESSURE CONTROL AND MONITORING | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | 12'000 | 1 | 75 | 0.013889
B-LAE | Q | HE32-213100-02-1 (R0004) / OPERATIONAL TEST OF MANUAL MODE SELECTION AND MANUAL MODE PRESSURE CONTROL AND FUNCTIONAL TES | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | 12'000 | 1 | 75 | 0.013889
B-LAE | Q | HE32-215000-03-2 (R0003) / DETAILED INSPECTION OF ACTUATOR MECHANISM AND INLET FLAP FOR EXCESSIVE PLAY AND CHECK GAP BET | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | 12'000 | 1 | 75 | 0.083333
B-LAE | Q | HE32-215200-01-1-01 (R0004) / REMOVE LH PRIMARY AND MAIN HEAT EXCHANGERS FOR IN SHOP CLEANING | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | 12'000 | 1 | 75 | 0.27778
B-LAE | Q | HE32-215200-01-1-02 (R0004) / REMOVE RH PRIMARY AND MAIN HEAT EXCHANGERS FOR IN SHOP CLEANING | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | 12'000 | 1 | 75 | 0.27917
B-LAE | Q | HE32-215200-02-2-01 (R0004) / REMOVE LH REHEATER FOR IN SHOP CLEANING | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | 12'000 | 1 | 75 | 0.19444
B-LAE | Q | HE32-215200-02-2-02 (R0004) / REMOVE RH REHEATER FOR IN SHOP CLEANING | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | 12'000 | 1 | 75 | 0.19583
B-LAE | Q | HE32-215222-01-1 (R0004) / DETAILED INSPECTION OF INTERIOR AND EXTERIOR OF PLENUM CHAMBER (10HM5 AND 11HM5) FOR SIGNS OF | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | 12'000 | 1 | 75 | 0.065278
B-LAE | Q | HE32-215800-02-1 (R0004) / REMOVE CSAS HEAT EXCHANGER FOR IN SHOP CLEANING | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.175
B-LAE | Q | HE32-216242-01-1 (R0003) / DETAILED INSPECTION OF TRIM AIR CHECK VALVES FLAPPERS FOR CONDITION AND OPERATION | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | 12'000 | 1 | 75 | 0.10833
B-LAE | Q | HE32-242200-01-1 (R0003) / OPERATIONAL TEST OF THE TRANSFER INHIBITION | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.0083333
B-LAE | Q | HE32-243400-01-1 (R0003) / OPERATIONAL TEST OF THE "DC EMER CONFIG" CAUTION | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.011111
B-LAE | Q | HE32-254000-04-2 (R0003) / DETAILED INSPECTION OF LAVATORY FLOOR PAN | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.0625
B-LAE | Q | HE32-261700-04-1 (R0003) / REMOVE SMOKE DETECTOR FOR CLEANING | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.025
B-LAE | Q | HE32-262100-02-1-01 (R0004) / OPERATIONAL CHECK OF LOW-PRESSURE INDICATING CIRCUIT OF ENGINE FIRE-EXTINGUISHER BOTTLES I | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.023611
B-LAE | Q | HE32-262100-02-1-02 (R0004) / OPERATIONAL CHECK OF LOW-PRESSURE INDICATING CIRCUIT OF ENGINE FIRE-EXTINGUISHER BOTTLES I | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.022222
B-LAE | Q | HE32-262100-06-1-01 (R0004) / CHECK OF DISTRIBUTION PIPING OF NO.1 ENG TO DETECT LEAKAGE AND OBSTRUCTION | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.20694
B-LAE | Q | HE32-262100-06-1-02 (R0004) / CHECK OF DISTRIBUTION PIPING OF NO.2 ENG TO DETECT LEAKAGE AND OBSTRUCTION | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.20556
B-LAE | Q | HE32-274451-04-1 (R0003) / DETAILED INSPECTION OF THS ACTUATOR BALL SCREW NUT BODY AND SCREW AND CLAW STOPS | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.015278
B-LAE | Q | HE32-274451-06-1 (R0003) / VISUAL CHECK OF THS ACTUATOR THREADED NUT (FAIL-SAFE NUT) | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.0069444
B-LAE | Q | HE32-274451-08-1 (R0003) / INTEGRITY CHECK OF THE THS ACTUATOR BALL SCREW SHAFT (PRIMARY AND SECONDARY LOAD PATH) | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.011111
B-LAE | Q | HE32-275100-01-2 (R0003) / OPERATIONAL TEST OF THE WING TIP BRAKE AND THE PRESSURE OFF BRAKE | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.020833
B-LAE | Q | HE32-275100-02-1 (R0003) / OPERATIONAL TEST OF THE FLAP INTERCONNECTING STRUT AND THE FLAP-ATTACHMENT FAILURE-DETECTION | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.0083333
B-LAE | Q | HE32-275100-03-1-01 (R0003) / CHECK OF LH FLAPS SHAFTING INTEGRITY, INCLUDING INSPECTION OF THE SEAL WITNESS DRAINS | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.025
B-LAE | Q | HE32-275100-03-1-02 (R0003) / CHECK OF RH FLAPS SHAFTING INTEGRITY, INCLUDING INSPECTION OF THE SEAL WITNESS DRAINS | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.025
B-LAE | Q | HE32-275144-01-1-01 (R0003) / DETAILED INSPECTION OF THE INTERCONNECTING STRUT AND ATTACHMENTS OF LH WING | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.0125
B-LAE | Q | HE32-275144-01-1-02 (R0003) / DETAILED INSPECTION OF THE INTERCONNECTING STRUT AND ATTACHMENTS OF RH WING | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.0125
B-LAE | Q | HE32-281600-01-1-01 (R0003) / OPERATIONAL CHECK OF THE PYLON CHECK VALVE OF NO.1 ENG TO ENSURE VALVE NOT FAILED OPEN | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.0083333
B-LAE | Q | HE32-281600-01-1-02 (R0003) / OPERATIONAL CHECK OF THE PYLON CHECK VALVE OF NO.2 ENG TO ENSURE VALVE NOT FAILED OPEN | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.0083333
B-LAE | Q | HE32-281600-04-1-01 (R0004) / VISUAL CHECK OF RECIRCULATION RETURN-LINE SHROUD OF LH PYLON | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.039583
B-LAE | Q | HE32-281600-04-1-02 (R0004) / VISUAL CHECK OF RECIRCULATION RETURN-LINE SHROUD OF RH PYLON | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.039583
B-LAE | Q | HE32-282100-05-1-01 (R0003) / VISUAL CHECK OF NO.1 ENG PIPES, COUPLINGS AND LP VALVE EXTERNAL TO TANK FROM FRONT SPAR TO | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.091667
B-LAE | Q | HE32-282100-05-1-02 (R0003) / VISUAL CHECK OF NO.2 ENG PIPES, COUPLINGS AND LP VALVE EXTERNAL TO TANK FROM FRONT SPAR TO | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.1
B-LAE | Q | HE32-282300-01-1 (R0004) / OPERATIONAL TEST OF CROSSFEED VALVE USING INDIVIDUAL MOTORS AND CHECK FUEL FLOW IN "OPEN" AND | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.016667
B-LAE | Q | HE32-291000-09-1-01 (R0004) / OPERATIONAL CHECK OF LH HYDRAULIC FIRE SHUT-OFF VALVE AND ASSOCIATED INDICATING SYSTEM | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.0069444
B-LAE | Q | HE32-291000-09-1-02 (R0004) / OPERATIONAL CHECK OF RH HYDRAULIC FIRE SHUT-OFF VALVE AND ASSOCIATED INDICATING SYSTEM | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.0069444
B-LAE | Q | HE32-291900-02-1 (R0003) / FUNCTIONAL CHECK TO MONITOR INTERNAL LEAK RATE OF BLUE HYDRAULIC SYSTEM | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.022222
B-LAE | Q | HE32-293400-01-1 (R0003) / OPERATIONAL TEST OF RESERVOIR LOW AIR PRESSURE WARNING | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.025
B-LAE | Q | HE32-323100-06-1 (R0003) / BITE CHECK USING MCDU TO ENSURE "GEAR NOT DOWN FOR LANDING" WARNINGS OPERATIVE | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.0083333
B-LAE | Q | HE32-324000-17-1 (R0004) / FUNCTIONAL CHECK OF BRAKE ACCUMULATOR SYSTEM | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.16667
B-LAE | Q | HE32-324300-01-3 (R0003) / OPERATIONAL CHECK OF ALTERNATE BRAKING SYSTEM | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.05
B-LAE | Q | HE32-341300-05-1 (R0003) / OPERATIONAL CHECK OF THE 5-MINUTE TIME DELAY OF ADIRU 2 AND 3 POWER DISCONNECTION IN EMERGENC | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.019444
B-LAE | Q | HE32-344200-01-1 (R0004) / OPERATIONAL CHECK AND DETAILED INSPECTION FOR CONTAMINATION OF RADIO ALTIMETER FAN | H | 2933:57 | 12007:33 | 2026-07-26 |  | 0 | 4'000 | 1 | 26 | 0.068056
B-LAE | Q | HE32-344800-04-1 (R0004) / BITE TEST OF THE T/TISS (TAWS PART) | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.083333
B-LAE | Q | HE32-361141-06-1-01 (R0003) / REMOVE INTERMEDIATE PRESSURE BLEED CHECK VALVE OF NO.1 ENG FOR DETAILED INSPECTION | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.19028
B-LAE | Q | HE32-361141-06-1-02 (R0003) / REMOVE INTERMEDIATE PRESSURE BLEED CHECK VALVE OF NO.2 ENG FOR DETAILED INSPECTION | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.19028
B-LAE | Q | HE32-522100-01-1 (R0003) / OPERATIONAL CHECK OF UNLOCKING AND OPENING FROM INSIDE IN ARMED MODE | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.17222
B-LAE | Q | HE32-545900-W3-1-01 (R0004) / DETAILED INSPECTION OF KARMAN FAIRING FIRE SEALS OF LH PYLON | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.041667
B-LAE | Q | HE32-545900-W3-1-02 (R0004) / DETAILED INSPECTION OF KARMAN FAIRING FIRE SEALS OF RH PYLON | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.041667
B-LAE | Q | HE32-545900-W5-1-01 (R0004) / DETAILED INSPECTION OF RMF BLOCK SEAL AND RMF FIRE FINGER SEAL OF LH PYLON | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.070833
B-LAE | Q | HE32-545900-W5-1-02 (R0004) / DETAILED INSPECTION OF RMF BLOCK SEAL AND RMF FIRE FINGER SEAL OF RH PYLON | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.070833
B-LAE | Q | HE32-711000-W1-1-01 (R0003) / FUNCTIONAL CHECK OF THE FAN COWL LATCH TENSION OF NO.1 ENG | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.041667
B-LAE | Q | HE32-711000-W1-1-02 (R0003) / FUNCTIONAL CHECK OF THE FAN COWL LATCH TENSION OF NO.2 ENG | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.041667
B-LAE | Q | HE32-781000-W1-1-01 (R0003) / DETAILED INSPECTION OF THE NOZZLE FIRE FINGER SEALS OF NO.1 ENG | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.073611
B-LAE | Q | HE32-781000-W1-1-02 (R0003) / DETAILED INSPECTION OF THE NOZZLE FIRE FINGER SEALS OF NO.2 ENG | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.073611
B-LAE | Q | HE32-783200-W2-1-01 (R0003) / GENERAL VISUAL INSPECTION OF THE THERMAL PROTECTION SYSTEM OF NO.1 ENG | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.070833
B-LAE | Q | HE32-783200-W2-1-02 (R0003) / GENERAL VISUAL INSPECTION OF THE THERMAL PROTECTION SYSTEM OF NO.2 ENG | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.070833
B-LAE | Q | HE32-783200-W5-1-01 (R0003) / FUNCTIONAL CHECK OF THRUST REVERSER LATCH TENSION OF NO.1 ENG | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.056944
B-LAE | Q | HE32-783200-W5-1-02 (R0003) / FUNCTIONAL CHECK OF THRUST REVERSER LATCH TENSION OF NO.2 ENG | H | 2926:24 | 12000:00 | 2026-07-26 |  | 0 | Thr. 12'000 | 1 | 75 | 0.056944
B-LAA | D | EOA32-29-0012/A32 SERIAL AIRPALNES` HYDRAULIC COMPONENTS LEAK CHECK AND CLEAN | D | 274 | 28.Jul.2026 | 2026-07-28 |  | 0 | 547 D | 2 | 49 | 0.29167
B-LAE | D | EOI-49-0006/[131-9A] REMOVE AND DISCARD OIL FILTER ELEMENTS (8069KM) AND (8076KM) | D | 277 | 31.Jul.2026 | 2026-07-31 |  | 0 | 730 D | 2 | 62 | 0.041667 | 3800708-1 / P-9078
B-LAC | Q | HE32-256241-05-1 (R0003) / CLEAN DOOR GIRT BAR FITTING STOP LEVERS | C | 963 | 3'737 | 2026-07-31 |  | 0 | 1'110 | 1 | 13 | 0.05
B-LAA | Q | HE32-256551-01-1 (R0002) / DISCARD AND REPLACE MEGAPHONE BATTERIES | D | 277 | 31.Jul.2026 | 2026-07-31 |  | 0 | 365 D | 1 | 24 | 0.020833
B-LAC | Q | HE32-31-SCME-010 (R0005) / READOUT PROCEDURE FOR RECORDING INSPECTION OF FDR SYSTEM | D | 277 | 31.Jul.2026 | 2026-07-31 |  | 0 | 365 D | 1 | 24 | 0.048611
B-LAA | Q | HE32-561000-02-1 (R0003) / DETAILED INSPECTION OF ALL COCKPIT WINDOWS FROM OUTSIDE INCLUDING SEALS | D | 277 | 31.Jul.2026 | 2026-07-31 |  | 0 | 365 D | 1 | 24 | 0.054167
B-LAC | Q | HE32-ZL-147-02-1 (R0002) / GENERAL VISUAL INSPECTION OF MLG-WELL AND HYDRAULIC COMPARTMENT (EWIS) | D | 277 | 31.Jul.2026 | 2026-07-31 |  | 0 | 365 D | 1 | 24 | 0.038889
B-LAA | Q | HE32-ZL-400-02-4 (R0003) / GENERAL VISUAL INSPECTION OF POWERPLANTS, NACELLES AND PYLONS | D | 277 | 31.Jul.2026 | 2026-07-31 |  | 0 | 365 D | 1 | 24 | 0.011111
B-LAC | Q | HE32-ZL-711-01-1 (R0002) / GENERAL VISUAL INSPECTION OF NOSE GEAR AND NOSE GEAR DOORS (EWIS) | D | 277 | 31.Jul.2026 | 2026-07-31 |  | 0 | 365 D | 1 | 24 | 0.023611
B-LAC | Q | HE32-ZL-731-01-1 (R0002) / GENERAL VISUAL INSPECTION OF LH/RH MAIN LANDING GEAR INCLUDING CYLINDER AND SECONDARY DOORS ( | D | 277 | 31.Jul.2026 | 2026-07-31 |  | 0 | 365 D | 1 | 24 | 0.034028
B-LAD | V | REPLACE 2100-1228-02/002031660 (COCKPIT VOICE RECORDER) | D | 277 | 31.Jul.2026 | 2026-07-31 |  | 0 |  | 2 |  | 0.0083333 | 2100-1228-02 / 002031660
B-LAA | V | REPLACE 15-40F80/77930029 (PBE) | D | 278 | 01.Aug.2026 | 2026-08-01 |  | 0 |  | 2 |  | 0.016667 | 15-40F80 / 77930029
B-LAA | V | REPLACE 15-40F80/77930038 (PBE) | D | 278 | 01.Aug.2026 | 2026-08-01 |  | 0 |  | 2 |  | 0.016667 | 15-40F80 / 77930038
B-LAA | V | REPLACE 15-40F80/77930053 (PBE) | D | 278 | 01.Aug.2026 | 2026-08-01 |  | 0 |  | 2 |  | 0.016667 | 15-40F80 / 77930053
B-LAC | V | REPLACE 30903886/2220UH (CARTRIDGE) | D | 278 | 01.Aug.2026 | 2026-08-01 |  | 0 |  | 2 |  | 0.091667 | 30903886 / 2220UH
B-LAC | V | REPLACE 30903886/2230UH (CARTRIDGE) | D | 278 | 01.Aug.2026 | 2026-08-01 |  | 0 |  | 2 |  | 0.091667 | 30903886 / 2230UH
B-LAC | V | REPLACE 30903886/2247UH (CARTRIDGE) | D | 278 | 01.Aug.2026 | 2026-08-01 |  | 0 |  | 2 |  | 0.091667 | 30903886 / 2247UH
B-LAC | V | REPLACE 30903886/2280UH (CARTRIDGE) | D | 278 | 01.Aug.2026 | 2026-08-01 |  | 0 |  | 2 |  | 0.091667 | 30903886 / 2280UH
B-LAC | V | REPLACE 33600005-3/A6430D1/W282616 (APU FIRE EXTINGUISHER) | D | 278 | 01.Aug.2026 | 2026-08-01 | 2026-07-01 | B-LAC-PLN-010826-LM |  | 2 |  | 0.075 | 33600005-3 / A6430D1
B-LAC | V | REPLACE 33600105-4/A4321D1/W282617 (ENGINE FIRE EXTINGUISHER) | D | 278 | 01.Aug.2026 | 2026-08-01 | 2026-04-16 | B-LAC-PLN-160526-LM |  | 2 |  | 0.12917 | 33600105-4 / A4321D1
B-LAB | Q | HE32-212600-03-1 (R0003) / OPERATIONAL CHECK OF SMOKE CONFIGURATION CONTROL CIRCUIT | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.013889
B-LAB | Q | HE32-213100-01-1 (R0003) / OPERATIONAL TEST OF THE PRESSURE CONTROL AND MONITORING | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.013889
B-LAB | Q | HE32-213100-02-1 (R0004) / OPERATIONAL TEST OF MANUAL MODE SELECTION AND MANUAL MODE PRESSURE CONTROL AND FUNCTIONAL TES | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.013889
B-LAB | Q | HE32-215000-03-2 (R0003) / DETAILED INSPECTION OF ACTUATOR MECHANISM AND INLET FLAP FOR EXCESSIVE PLAY AND CHECK GAP BET | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.083333
B-LAD | Q | HE32-216000-01-1 (R0004) / CLEAN THE COCKPIT AND CABIN SENSOR DUCT AND TEMPERATURE SENSOR | H | 3004:54 | 12934:59 | 2026-08-02 |  | 0 | 7'500 | 1 | 59 | 0.088889
B-LAB | Q | HE32-216242-01-1 (R0003) / DETAILED INSPECTION OF TRIM AIR CHECK VALVES FLAPPERS FOR CONDITION AND OPERATION | H | 3003:17 | 15410:44 | 2026-08-02 |  | 0 | 12'000 | 1 | 74 | 0.10833
B-LAB | Q | HE32-242200-01-1 (R0003) / OPERATIONAL TEST OF THE TRANSFER INHIBITION | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.0083333
B-LAB | Q | HE32-243400-01-1 (R0003) / OPERATIONAL TEST OF THE "DC EMER CONFIG" CAUTION | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.011111
B-LAD | Q | HE32-253000-02-1 (R0003) / REMOVE AND DISCARD FILTER ELEMENT OF GALLEY | H | 3004:54 | 12934:59 | 2026-08-02 |  | 0 | 7'500 | 1 | 59 | 0.083333
B-LAB | Q | HE32-254000-04-2 (R0003) / DETAILED INSPECTION OF LAVATORY FLOOR PAN | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.0625
B-LAB | Q | HE32-262100-02-1-01 (R0004) / OPERATIONAL CHECK OF LOW-PRESSURE INDICATING CIRCUIT OF ENGINE FIRE-EXTINGUISHER BOTTLES I | H | 3003:17 | 15410:44 | 2026-08-02 |  | 0 | 12'000 | 1 | 74 | 0.023611
B-LAB | Q | HE32-262100-02-1-02 (R0004) / OPERATIONAL CHECK OF LOW-PRESSURE INDICATING CIRCUIT OF ENGINE FIRE-EXTINGUISHER BOTTLES I | H | 3003:17 | 15410:44 | 2026-08-02 |  | 0 | 12'000 | 1 | 74 | 0.022222
B-LAB | Q | HE32-274451-04-1 (R0003) / DETAILED INSPECTION OF THS ACTUATOR BALL SCREW NUT BODY AND SCREW AND CLAW STOPS | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.015278
B-LAB | Q | HE32-274451-06-1 (R0003) / VISUAL CHECK OF THS ACTUATOR THREADED NUT (FAIL-SAFE NUT) | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.0069444
B-LAB | Q | HE32-274451-08-1 (R0003) / INTEGRITY CHECK OF THE THS ACTUATOR BALL SCREW SHAFT (PRIMARY AND SECONDARY LOAD PATH) | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.011111
B-LAB | Q | HE32-275100-01-2 (R0003) / OPERATIONAL TEST OF THE WING TIP BRAKE AND THE PRESSURE OFF BRAKE | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.020833
B-LAB | Q | HE32-275100-02-1 (R0003) / OPERATIONAL TEST OF THE FLAP INTERCONNECTING STRUT AND THE FLAP-ATTACHMENT FAILURE-DETECTION | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.0083333
B-LAB | Q | HE32-275100-03-1-01 (R0003) / CHECK OF LH FLAPS SHAFTING INTEGRITY, INCLUDING INSPECTION OF THE SEAL WITNESS DRAINS | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.025
B-LAB | Q | HE32-275100-03-1-02 (R0003) / CHECK OF RH FLAPS SHAFTING INTEGRITY, INCLUDING INSPECTION OF THE SEAL WITNESS DRAINS | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.025
B-LAB | Q | HE32-275144-01-1-01 (R0003) / DETAILED INSPECTION OF THE INTERCONNECTING STRUT AND ATTACHMENTS OF LH WING | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.0125
B-LAB | Q | HE32-275144-01-1-02 (R0003) / DETAILED INSPECTION OF THE INTERCONNECTING STRUT AND ATTACHMENTS OF RH WING | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.0125
B-LAD | Q | HE32-281500-01-2 (R0003) / OPERATIONAL CHECK OF INDIVIDUAL TRANSFER VALVES TO ENSURE VALVE SHAFT ROTATES VALVE TO OPEN P | H | 3004:54 | 12934:59 | 2026-08-02 |  | 0 | 7'500 | 1 | 59 | 0.038889
B-LAB | Q | HE32-281600-01-1-01 (R0003) / OPERATIONAL CHECK OF THE PYLON CHECK VALVE OF NO.1 ENG TO ENSURE VALVE NOT FAILED OPEN | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.0083333
B-LAB | Q | HE32-281600-01-1-02 (R0003) / OPERATIONAL CHECK OF THE PYLON CHECK VALVE OF NO.2 ENG TO ENSURE VALVE NOT FAILED OPEN | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.0083333
B-LAB | Q | HE32-281600-04-1-01 (R0004) / VISUAL CHECK OF RECIRCULATION RETURN-LINE SHROUD OF LH PYLON | H | 3003:17 | 15410:44 | 2026-08-02 |  | 0 | 12'000 | 1 | 74 | 0.039583
B-LAB | Q | HE32-281600-04-1-02 (R0004) / VISUAL CHECK OF RECIRCULATION RETURN-LINE SHROUD OF RH PYLON | H | 3003:17 | 15410:44 | 2026-08-02 |  | 0 | 12'000 | 1 | 74 | 0.039583
B-LAB | Q | HE32-282100-05-1-01 (R0003) / VISUAL CHECK OF NO.1 ENG PIPES, COUPLINGS AND LP VALVE EXTERNAL TO TANK FROM FRONT SPAR TO | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.091667
B-LAB | Q | HE32-282100-05-1-02 (R0003) / VISUAL CHECK OF NO.2 ENG PIPES, COUPLINGS AND LP VALVE EXTERNAL TO TANK FROM FRONT SPAR TO | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.1
B-LAB | Q | HE32-291000-09-1-01 (R0004) / OPERATIONAL CHECK OF LH HYDRAULIC FIRE SHUT-OFF VALVE AND ASSOCIATED INDICATING SYSTEM | H | 3003:17 | 15410:44 | 2026-08-02 |  | 0 | 12'000 | 1 | 74 | 0.0069444
B-LAB | Q | HE32-291000-09-1-02 (R0004) / OPERATIONAL CHECK OF RH HYDRAULIC FIRE SHUT-OFF VALVE AND ASSOCIATED INDICATING SYSTEM | H | 3003:17 | 15410:44 | 2026-08-02 |  | 0 | 12'000 | 1 | 74 | 0.0069444
B-LAB | Q | HE32-291900-02-1 (R0003) / FUNCTIONAL CHECK TO MONITOR INTERNAL LEAK RATE OF BLUE HYDRAULIC SYSTEM | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.022222
B-LAB | Q | HE32-293400-01-1 (R0003) / OPERATIONAL TEST OF RESERVOIR LOW AIR PRESSURE WARNING | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.025
B-LAB | Q | HE32-323100-06-1 (R0003) / BITE CHECK USING MCDU TO ENSURE "GEAR NOT DOWN FOR LANDING" WARNINGS OPERATIVE | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.0083333
B-LAB | Q | HE32-324000-17-1 (R0004) / FUNCTIONAL CHECK OF BRAKE ACCUMULATOR SYSTEM | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.16667
B-LAB | Q | HE32-324300-01-3 (R0003) / OPERATIONAL CHECK OF ALTERNATE BRAKING SYSTEM | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.05
B-LAB | Q | HE32-341300-05-1 (R0003) / OPERATIONAL CHECK OF THE 5-MINUTE TIME DELAY OF ADIRU 2 AND 3 POWER DISCONNECTION IN EMERGENC | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.019444
B-LAB | Q | HE32-522100-01-1 (R0003) / OPERATIONAL CHECK OF UNLOCKING AND OPENING FROM INSIDE IN ARMED MODE | H | 3003:17 | 15410:44 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.17222
B-LAB | Q | HE32-545900-W3-1-01 (R0004) / DETAILED INSPECTION OF KARMAN FAIRING FIRE SEALS OF LH PYLON | H | 3003:17 | 15410:44 | 2026-08-02 |  | 0 | 12'000 | 1 | 74 | 0.041667
B-LAB | Q | HE32-545900-W3-1-02 (R0004) / DETAILED INSPECTION OF KARMAN FAIRING FIRE SEALS OF RH PYLON | H | 3003:17 | 15410:44 | 2026-08-02 |  | 0 | 12'000 | 1 | 74 | 0.041667
B-LAB | Q | HE32-545900-W5-1-01 (R0004) / DETAILED INSPECTION OF RMF BLOCK SEAL AND RMF FIRE FINGER SEAL OF LH PYLON | H | 3006:35 | 15414:02 | 2026-08-02 |  | 0 | 12'000 | 1 | 74 | 0.070833
B-LAB | Q | HE32-545900-W5-1-02 (R0004) / DETAILED INSPECTION OF RMF BLOCK SEAL AND RMF FIRE FINGER SEAL OF RH PYLON | H | 3006:35 | 15414:02 | 2026-08-02 |  | 0 | 12'000 | 1 | 74 | 0.070833
B-LAB | Q | HE32-711000-W1-1-01 (R0003) / FUNCTIONAL CHECK OF THE FAN COWL LATCH TENSION OF NO.1 ENG | H | 3006:35 | 15414:02 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.041667
B-LAB | Q | HE32-711000-W1-1-02 (R0003) / FUNCTIONAL CHECK OF THE FAN COWL LATCH TENSION OF NO.2 ENG | H | 3006:35 | 15414:02 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.041667
B-LAB | Q | HE32-781000-W1-1-01 (R0003) / DETAILED INSPECTION OF THE NOZZLE FIRE FINGER SEALS OF NO.1 ENG | H | 3006:35 | 15414:02 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.073611
B-LAB | Q | HE32-781000-W1-1-02 (R0003) / DETAILED INSPECTION OF THE NOZZLE FIRE FINGER SEALS OF NO.2 ENG | H | 3006:35 | 15414:02 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.073611
B-LAB | Q | HE32-783200-W2-1-01 (R0003) / GENERAL VISUAL INSPECTION OF THE THERMAL PROTECTION SYSTEM OF NO.1 ENG | H | 3006:35 | 15414:02 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.070833
B-LAB | Q | HE32-783200-W2-1-02 (R0003) / GENERAL VISUAL INSPECTION OF THE THERMAL PROTECTION SYSTEM OF NO.2 ENG | H | 3006:35 | 15414:02 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.070833
B-LAB | Q | HE32-783200-W5-1-01 (R0003) / FUNCTIONAL CHECK OF THRUST REVERSER LATCH TENSION OF NO.1 ENG | H | 3006:35 | 15414:02 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.056944
B-LAB | Q | HE32-783200-W5-1-02 (R0003) / FUNCTIONAL CHECK OF THRUST REVERSER LATCH TENSION OF NO.2 ENG | H | 3006:35 | 15414:02 | 2026-08-02 | 2027-06-18 | B-LAB-PLN-1C_2027 | 12'000 | 1 | 129 | 0.056944
B-LAA | V | REPLACE D30664-709/M15772 (RAFT-SLIDE,FWD) | D | 279 | 02.Aug.2026 | 2026-08-02 |  | 0 |  | 2 |  | 0.125 | D30664-709 / M15772
B-LAC | Q | HE32-344200-01-1 (R0004) / OPERATIONAL CHECK AND DETAILED INSPECTION FOR CONTAMINATION OF RADIO ALTIMETER FAN | H | 3028:17 | 11056:49 | 2026-08-04 |  | 0 | 4'000 | 1 | 24 | 0.068056
B-LAE | V | REPLACE FAKHKG02SW/EFK-1283 (FIRST AID KIT) | ID | 282 | 2'189 | 2026-08-05 |  | 0 |  | 2 |  | 0.0125 | FAKHKG02SW / EFK-1283 | PLN: Please double check if the expiry day of the sad kit is correct.
B-LAD | Q | HE32-262300-09-1 (R0003) / DISCARD WATER ADSORBING FILTER | D | 283 | 06.Aug.2026 | 2026-08-06 |  | 0 | 456 D | 1 | 37 | 0.059722
B-LAE | Q | HE32-262300-09-1 (R0003) / DISCARD WATER ADSORBING FILTER | D | 284 | 07.Aug.2026 | 2026-08-07 |  | 0 | 456 D | 1 | 37 | 0.059722
B-LAB | Q | HE32-215800-01-1 (R0004) / REMOVE CSAS OZONE CONVERTER FOR IN SHOP CLEANING | H | 3073:16 | 15480:43 | 2026-08-08 |  | 0 | 6'000 | 1 | 48 | 0.15833
B-LAE | Q | HE32-323100-01-1 (R0003) / BITE CHECK OF LANDING-GEAR CONTROL INTERFACE-UNIT (LGCIU) WITH USE OF MCDU TO ENSURE THAT CON | H | 3074:54 | 12148:30 | 2026-08-09 |  | 0 | 4'000 | 1 | 23 | 0.016667
B-LAD | Q | HE32-256551-01-1 (R0002) / DISCARD AND REPLACE MEGAPHONE BATTERIES | D | 287 | 10.Aug.2026 | 2026-08-10 |  | 0 | 365 D | 1 | 21 | 0.020833
B-LAD | Q | HE32-561000-02-1 (R0003) / DETAILED INSPECTION OF ALL COCKPIT WINDOWS FROM OUTSIDE INCLUDING SEALS | D | 287 | 10.Aug.2026 | 2026-08-10 |  | 0 | 365 D | 1 | 21 | 0.054167
B-LAD | Q | HE32-ZL-400-02-4 (R0003) / GENERAL VISUAL INSPECTION OF POWERPLANTS, NACELLES AND PYLONS | D | 287 | 10.Aug.2026 | 2026-08-10 |  | 0 | 365 D | 1 | 21 | 0.011111
B-LAA | D | EOI-49-0006/W1415472 /[131-9A] REMOVE AND DISCARD OIL FILTER ELEMENTS (8069KM) AND (8076KM) | D | 288 | 11.Aug.2026 | 2026-08-11 | 2025-11-01 | B-LAA-PLN-7.5K_2025 | 730 D | 2 | 62 | 0.041667 | 3800708-1 / P-5514
B-LAD | Q | HE32-200001-02-1-01 (R0002) / CHECK TO MAKE SURE THAT CONNECTOR AT LH WING IS CORRECTLY TIGHTENED BY MEASUREMENT OF THE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.19028
B-LAD | Q | HE32-200001-02-1-02 (R0002) / CHECK TO MAKE SURE THAT CONNECTOR AT RH WING IS CORRECTLY TIGHTENED BY MEASUREMENT OF THE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.19028
B-LAD | Q | HE32-200003-01-1 (R0002) / GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON THE HARNESSES 4202VB, 4204VB | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0375
B-LAD | Q | HE32-200003-02-1 (R0002) / GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON THE HARNESSES 4202VB, 4204VB | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.040278
B-LAD | Q | HE32-200003-03-1 (R0002) / GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON THE HARNESSES 4202VB, 4204VB | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.023611
B-LAD | Q | HE32-200121-03-1 (R0002) / GENERAL VISUAL INSPECTION OF 90VU, 108VU AND 109VU IN THE FORWARD AVIONIC COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.094444
B-LAD | Q | HE32-200121-04-1 (R0002) / DETAILED INSPECTION OF G, E AND P ROUTES IN THE FORWARD AVIONIC COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.058333
B-LAD | Q | HE32-200125-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE LATERAL AVIONIC COMPARTMENT (ONLY IF CONTAMINATED) (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.058333
B-LAD | Q | HE32-200125-05-1 (R0002) / GENERAL VISUAL INSPECTION OF 105VU, 106VU, 103VU, 107VU AND 70VU INSTALLED IN THE LATERAL AVI | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.047222
B-LAD | Q | HE32-200125-06-1 (R0002) / DETAILED INSPECTION OF G, E AND P ROUTES INSTALLED IN THE LATERAL AVIONIC COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.052778
B-LAD | Q | HE32-200127-02-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE REAR AVIONIC COMPARTMENT (ONLY IF CONTAMINATED) (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.094444
B-LAD | Q | HE32-200127-05-1 (R0002) / GENERAL VISUAL INSPECTION OF 63VU, 80VU, 187VU AND 188VU INSTALLED IN THE REAR AVIONIC COMPAR | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.047222
B-LAD | Q | HE32-200127-07-1 (R0002) / DETAILED INSPECTION OF G, E AND P ROUTES INSTALLED IN THE REAR AVIONIC COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.080556
B-LAD | Q | HE32-200131-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE FORWARD CARGO COMPARTMENT (ONLY IF CONTAMINATED) (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.044444
B-LAD | Q | HE32-200133-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE UNDERFLOOR BAY OF FORWARD CARGO COMPARTMENT (ONLY IF CONTAMIN | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.05
B-LAD | Q | HE32-200137-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE BAY BEHIND FWD CARGO COMPARTMENT (ONLY IF CONTAMINATED) (EWIS | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.036111
B-LAD | Q | HE32-200145-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE ZONE UNDER CABIN FLOOR (ONLY IF CONTAMINATED) (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.025
B-LAD | Q | HE32-200151-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE AFT CARGO COMPARTMENT (ONLY IF CONTAMINATED) (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.044444
B-LAD | Q | HE32-200161-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE BULK CARGO COMPARTMENT (ONLY IF CONTAMINATED) (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.027778
B-LAD | Q | HE32-200191-01-1 (R0003) / CLEAN THE EWIS INSTALLED IN THE AIR CONDITIONING COMPARTMENT AND FAIRINGS (ONLY IF CONTAMINAT | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.21389
B-LAD | Q | HE32-200211-02-1 (R0002) / CLEAN THE EWIS INSTALLED IN 49VU AND 120VU (ONLY IF CONTAMINATED) (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.055556
B-LAD | Q | HE32-200315-01-1 (R0002) / GENERAL VISUAL INSPECTION OF G AND P ROUTES INSTALLED IN THE TAIL CONE AND APU ACCESSORY COMP | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.019444
B-LAD | Q | HE32-253000-01-1 (R0002) / DETAILED INSPECTION OF ATTACHMENT POINTS | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.025
B-LAD | Q | HE32-262541-01-1 (R0002) / DETAILED INSPECTION OF LAVATORY FIRE EXTINGUISHER FOR SIGNS OF LEAKAGE/DISCHARGE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0083333
B-LAD | Q | HE32-272100-02-1 (R0002) / DETAILED INSPECTION OF THE CONTROL CABLES | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.033333
B-LAD | Q | HE32-272100-05-1 (R0003) / OPERATIONAL TEST OF THE CENTERING SPRING ROD | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.022222
B-LAD | Q | HE32-272100-07-1 (R0003) / DETAILED INSPECTION OF MECHANICAL CONTROL LINKAGE IN FIN | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.019444
B-LAD | Q | HE32-275449-06-1-01 (R0002) / DRAIN AND REFILL FLAP ACTUATOR ASSEMBLIES OF LH WING WITH SEMI-FLUID | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.34444
B-LAD | Q | HE32-275449-06-1-02 (R0002) / DRAIN AND REFILL FLAP ACTUATOR ASSEMBLIES OF RH WING WITH SEMI-FLUID | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.34444
B-LAD | Q | HE32-281800-01-1 (R0002) / FUNCTIONAL CHECK OF TANK VAPOUR SEAL AND VENT DRAIN SYSTEM (SFAR88) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.34444
B-LAD | Q | HE32-281800-02-1 (R0003) / DETAILED INSPECTION OF VAPOUR SEAL (SFAR88) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.098611
B-LAD | Q | HE32-281800-05-1 (R0002) / GENERAL VISUAL INSPECTION OF CENTER TANK FWD CARGO BAY INSULATION BLANKETS (SFAR88) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.019444
B-LAD | Q | HE32-291000-04-1 (R0002) / FUNCTIONAL CHECK OF THE POWER TRANSFER UNIT (PTU) GREEN TO YELLOW | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.016667
B-LAD | Q | HE32-323300-01-1 (R0002) / DETAILED INSPECTION OF FREE-FALL MECHANISM INCLUDING CABLES | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.13333
B-LAD | Q | HE32-323300-04-1 (R0002) / FUNCTIONAL CHECK OF FREE-FALL MECHANISM CABLE TENSION | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.13056
B-LAD | Q | HE32-351351-01-1 (R0002) / FUNCTIONAL CHECK OF LOW PRESSURE SWITCH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0083333
B-LAD | Q | HE32-352000-02-1 (R0002) / FUNCTIONAL CHECK OF AUTOMATIC MASK RELEASE, DETAILED INSPECTION OF MASKS AND VISUAL CHECK OF | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.12222
B-LAD | Q | HE32-361101-01-1-01 (R0003) / REPLACE THE UPPER SEALS OF THE BLEED-AIR PRECOOLER EXCHANGER OF LH PYLON | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.027083
B-LAD | Q | HE32-361101-01-1-02 (R0003) / REPLACE THE UPPER SEALS OF THE BLEED-AIR PRECOOLER EXCHANGER OF RH PYLON | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.027083
B-LAD | Q | HE32-361200-01-1 (R0002) / OPERATIONAL CHECK OF CROSSBLEED VALVE IN MANUAL MODE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0125
B-LAD | Q | HE32-384142-01-1 (R0002) / DISCARD SYSTEM FILTER ELEMENT | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.013889
B-LAD | Q | HE32-384242-01-1 (R0004) / DISCARD COMPRESSOR OUTLET FILTER ELEMENT | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.013889
B-LAD | Q | HE32-523100-01-1 (R0002) / FUNCTIONAL CHECK OF FORWARD CARGO COMPARTMENT DOOR (INCLUDES LOCKING MECHANISM, INTERLOCK MEC | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.048611
B-LAD | Q | HE32-523200-01-1 (R0002) / FUNCTIONAL CHECK OF AFT CARGO COMPARTMENT DOOR (INCLUDES LOCKING MECHANISM, INTERLOCK MECHANI | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0375
B-LAD | Q | HE32-525111-02-1 (R0002) / OPERATIONAL CHECK OF ALL PRESSURE SENSING CHANNELS FOR RAPID DECOMPRESSION | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0125
B-LAD | Q | HE32-525111-04-1 (R0002) / OPERATIONAL CHECK OF DOOR OPENING IN CASE OF POWER OFF | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0041667
B-LAD | Q | HE32-525111-05-1 (R0002) / OPERATIONAL CHECK OF DOOR OPENING BY USING THE EMERGENCY CODE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0041667
B-LAD | Q | HE32-530000-01-1 (R0002) / REMOVE AND DETAILED INSPECTION OF PISTON TYPE DRAIN VALVES IN LOWER FUSELAGE SHELL | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.090278
B-LAD | Q | HE32-531102-01-1 (R0003) / DETAILED INSPECTION OF FORWARD PASSENGER/CREW DOOR FRAME, UPPER CORNERS, EXTERNAL SURFACE, LH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.043056
B-LAD | Q | HE32-531163-01-1 (R0003) / GENERAL VISUAL INSPECTION OF INTERNAL STRUCTURE AROUND FWD PASSENGER/CREW DR, ABOVE CABIN FLO | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.13889
B-LAD | Q | HE32-531164-01-1 (R0002) / DETAILED INSPECTION OF FUSELAGE INTERNAL STRUCTURE, BELOW FORWARD PASSENGER/CREW DOOR AND CAB | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.088889
B-LAD | Q | HE32-531166-01-2 (R0002) / DETAILED INSPECTION OF FWD PASSENGER/CREW DOOR CUTOUT LOWER CORNERS INTERNAL STRUCTURE ABOVE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.13889
B-LAD | Q | HE32-531171-01-1 (R0002) / DETAILED INSPECTION OF NLG, SECONDARY DOOR HINGE SUPPORTS ON FUSELAGE, LH/RH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.038889
B-LAD | Q | HE32-531181-01-1 (R0003) / DETAILED INSPECTION OF FUSELAGE INTERNAL STRUCTURE FROM FR 15 TO FR 21, BETWEEN STRINGER 23 A | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.030556
B-LAD | Q | HE32-531189-01-2 (R0002) / DETAILED INSPECTION OF CABIN FLOOR STRUCTURE BETWEEN FR 12 AND FR 21 | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.75556
B-LAD | Q | HE32-532137-03-1 (R0001) / DETAILED INSPECTION OF FORWARD CARGO DOOR CUTOUT PANELS, UPPER AND LOWER CORNERS, EXTERNAL SU | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.025
B-LAD | Q | HE32-532180-01-2 (R0002) / DETAILED INSPECTION OF FUSELAGE INTERNAL STRUCTURE INCLUDING FORWARD FACE OF PRESSURE BULKHEA | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.21111
B-LAD | Q | HE32-533136-01-1 (R0003) / GENERAL VISUAL INSPECTION OF MLG BAY | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.022222
B-LAD | Q | HE32-534107-01-1 (R0002) / DETAILED INSPECTION OF FUSELAGE INTERNAL STRUCTURE, BETWEEN FR 46 AND FR 65, INCLUDING AFT FA | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.33333
B-LAD | Q | HE32-534132-02-1 (R0001) / DETAILED INSPECTION OF AFT PASSENGER/CREW DOOR CUTOUT, UPPER CORNERS, INCLUDING SKIN AND INTE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0055556
B-LAD | Q | HE32-534135-01-4 (R0003) / GENERAL VISUAL INSPECTION OF INTERNAL STRUCTURE AROUND AFT PASSENGER/CREW DOOR CUTOUT ABOVE C | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.088889
B-LAD | Q | HE32-534143-01-3 (R0002) / DETAILED INSPECTION OF AFT PASSENGER/CREW DOOR CUTOUT LOWER CORNERS INTERNAL STRUCTURE, ABOVE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.033333
B-LAD | Q | HE32-534144-01-1 (R0002) / DETAILED INSPECTION OF FUSELAGE INTERNAL STRUCTURE, BELOW CABIN FLOOR PANELS INCLUDING FLOOR | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.088889
B-LAD | Q | HE32-534147-01-1 (R0002) / DETAILED INSPECTION OF THE CABIN FLOOR STRUCTURE, BELOW AND 0.5M AROUND GALLEYS AND TOILETS | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.5
B-LAD | Q | HE32-534148-01-1 (R0003) / GENERAL VISUAL INSPECTION OF FUSELAGE EXTERNAL SURFACE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.39167
B-LAD | Q | HE32-534159-02-1 (R0001) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.036111
B-LAD | Q | HE32-534171-02-1 (R0001) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.011111
B-LAD | Q | HE32-534195-01-2 (R0003) / DETAILED INSPECTION OF CABIN FLOOR STRUCTURE AND STRUCTURE BELOW AFT ENTRANCE AREA, BETWEEN F | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.033333
B-LAD | Q | HE32-535101-01-1 (R0002) / DETAILED INSPECTION OF REAR PRESSURE BULKHEAD COMPLETE AFT FACE AND FUSELAGE INTERNAL STRUCTU | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.10278
B-LAD | Q | HE32-545207-01-1-01 (R0003) / DETAILED INSPECTION OF PYLON-TO-ENGINE AFT ATTACHMENT FITTINGS, OF LH PYLON | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.076389
B-LAD | Q | HE32-545207-01-1-02 (R0003) / DETAILED INSPECTION OF PYLON-TO-ENGINE AFT ATTACHMENT FITTINGS, OF RH PYLON | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.076389
B-LAD | Q | HE32-545900-W2-1-01 (R0003) / OPERATIONAL CHECK OF LH PYLON DRAINAGE SYSTEM IN ZONE C | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.10833
B-LAD | Q | HE32-545900-W2-1-02 (R0003) / OPERATIONAL CHECK OF RH PYLON DRAINAGE SYSTEM IN ZONE C | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.10694
B-LAD | Q | HE32-551010-01-1 (R0002) / DETAILED INSPECTION OF HORIZONTAL STABILIZER, REAR SUPPORT FITTINGS, UPPER AND LOWER ATTACH F | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.044444
B-LAD | Q | HE32-551020-01-1 (R0003) / DETAILED INSPECTION OF HORIZONTAL STABILIZER, HINGE FITTINGS, SUPPORT RIBS AND ACTUATOR FITTI | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.23611
B-LAD | Q | HE32-552002-01-1 (R0002) / DETAILED INSPECTION OF ELEVATOR, HINGE FITTINGS AND ACTUATOR FITTINGS, LH/RH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.17778
B-LAD | Q | HE32-553004-01-1 (R0002) / DETAILED INSPECTION OF VERTICAL STABILIZER, ATTACH FITTINGS, INCLUDING LOAD INTRODUCTION AREA | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.047222
B-LAD | Q | HE32-553005-01-1 (R0002) / DETAILED INSPECTION OF RUDDER HINGE ARM 1, 2, 3, 4 AND 5 AND FIN ACTUATOR FITTINGS (ACTUATOR | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.022222
B-LAD | Q | HE32-553006-01-2 (R0002) / DETAILED INSPECTION OF RUDDER HINGE ARM 6 AND 7 | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.095833
B-LAD | Q | HE32-554003-02-1 (R0003) / SPECIAL DETAILED INSPECTION (US) OF RUDDER SIDE PANELS, IN AREA OF RUDDER BEARINGS, IN THE BO | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.063889
B-LAD | Q | HE32-554005-01-1 (R0002) / DETAILED INSPECTION OF RUDDER ATTACH FITTING 1, 2, 3, 4 AND 5 AND RUDDER ACTUATOR ATTACH FITT | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.022222
B-LAD | Q | HE32-554006-01-1 (R0002) / DETAILED INSPECTION OF RUDDER ATTACH FITTING 6 AND 7 | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.045833
B-LAD | Q | HE32-554008-01-1 (R0002) / SPECIAL DETAILED INSPECTION OF HONEYCOMB CORE OF THE RUDDER SIDE PANEL, LH/RH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.10417
B-LAD | Q | HE32-554009-01-1 (R0002) / SPECIAL DETAILED INSPECTION (ELCH TEST) OF THE BONDING LAYERS BETWEEN RUDDER SIDE PANEL HONEY | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.19444
B-LAD | Q | HE32-562101-01-1 (R0002) / DETAILED INSPECTION OF CABIN WINDOW PANES, INCLUDING WINDOW PANES IN DOORS | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.52778
B-LAD | Q | HE32-571122-01-1 (R0002) / DETAILED INSPECTION OF CENTER WING BOX, REAR SPAR AFT FACE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.125
B-LAD | Q | HE32-571157-01-1 (R0003) / DETAILED INSPECTION OF CENTER WING BOX, UPPER SKIN UPPER SURFACE AND BEAMS INCLUDING FRAME FE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.125
B-LAD | Q | HE32-572049-03-1-01 (R0003) / DETAILED INSPECTION OF LH OUTER WING, BOTTOM SKIN, LOWER SURFACE AT DRAIN HOLES FOR TRACK | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.010417
B-LAD | Q | HE32-572049-03-1-02 (R0003) / DETAILED INSPECTION OF RH OUTER WING, BOTTOM SKIN, LOWER SURFACE AT DRAIN HOLES FOR TRACK | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.010417
B-LAD | Q | HE32-572153-01-1-01 (R0003) / DETAILED INSPECTION OF LH OUTER WING, BOTTOM SKIN LOWER SURFACE, AT DRAIN HOLES FOR SLAT C | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0048611
B-LAD | Q | HE32-572153-01-1-02 (R0003) / DETAILED INSPECTION OF RH OUTER WING, BOTTOM SKIN LOWER SURFACE, AT DRAIN HOLES FOR SLAT C | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0048611
B-LAD | Q | HE32-572651-01-2-01 (R0003) / DETAILED INSPECTION OF LH OUTER WING, REAR-SPAR-AFT-FACE RETRACTION-JACK-FITTING | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0041667
B-LAD | Q | HE32-572651-01-2-02 (R0003) / DETAILED INSPECTION OF RH OUTER WING, REAR-SPAR-AFT-FACE RETRACTION-JACK-FITTING | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0041667
B-LAD | Q | HE32-574206-01-1-01 (R0002) / DETAILED INSPECTION OF LH SLAT 1, PINION AND RACK TEETH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.019444
B-LAD | Q | HE32-574206-01-1-02 (R0002) / DETAILED INSPECTION OF RH SLAT 1, PINION AND RACK TEETH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.019444
B-LAD | Q | HE32-574306-01-2-01 (R0002) / DETAILED INSPECTION OF LH SLAT 2, PINION AND RACK TEETH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0125
B-LAD | Q | HE32-574306-01-2-02 (R0002) / DETAILED INSPECTION OF RH SLAT 2, PINION AND RACK TEETH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0125
B-LAD | Q | HE32-574406-01-1-01 (R0002) / DETAILED INSPECTION OF LH SLAT 3, PINION AND RACK TEETH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0125
B-LAD | Q | HE32-574406-01-1-02 (R0002) / DETAILED INSPECTION OF RH SLAT 3, PINION AND RACK TEETH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0125
B-LAD | Q | HE32-574506-01-1-01 (R0002) / DETAILED INSPECTION OF LH SLAT 4, PINION AND RACK TEETH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.023611
B-LAD | Q | HE32-574506-01-1-02 (R0002) / DETAILED INSPECTION OF RH SLAT 4, PINION AND RACK TEETH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.023611
B-LAD | Q | HE32-574606-01-1-01 (R0002) / DETAILED INSPECTION OF LH SLAT 5, PINION AND RACK TEETH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.020833
B-LAD | Q | HE32-574606-01-1-02 (R0002) / DETAILED INSPECTION OF RH SLAT 5, PINION AND RACK TEETH | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.020833
B-LAD | Q | HE32-575151-03-1-01 (R0001) / GENERAL VISUAL INSPECTION OF LH OUTER WING, TRAILING EDGE, FALSE REAR SPAR, FORWARD AND AF | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | 2'191 D | 1 | 86 | 0.034028
B-LAD | Q | HE32-575151-03-1-02 (R0001) / GENERAL VISUAL INSPECTION OF RH OUTER WING, TRAILING EDGE, FALSE REAR SPAR, FORWARD AND AF | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | 2'191 D | 1 | 86 | 0.034028
B-LAD | Q | HE32-575167-01-1-01 (R0003) / DETAILED INSPECTION OF LH OUTER WING, BOTTOM SKIN PANEL NO. 3, UPPER SURFACE, BETWEEN REAR | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0097222
B-LAD | Q | HE32-575167-01-1-02 (R0003) / DETAILED INSPECTION OF RH OUTER WING, BOTTOM SKIN PANEL NO. 3, UPPER SURFACE, BETWEEN REAR | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0097222
B-LAD | Q | HE32-711311-01-1-01 (R0002) / DETAILED INSPECTION OF FAN COWL DOORS HINGES AND SURROUNDING STRUCTURE (150MM AROUND HINGE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.048611
B-LAD | Q | HE32-711311-01-1-02 (R0002) / DETAILED INSPECTION OF FAN COWL DOORS HINGES AND SURROUNDING STRUCTURE (150MM AROUND HINGE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.048611
B-LAD | Q | HE32-711312-01-1-01 (R0002) / DETAILED INSPECTION OF THE FAN COWL DOOR LATCHES AND SURROUNDING STRUCTURE (150MM AROUND L | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.048611
B-LAD | Q | HE32-711312-01-1-02 (R0002) / DETAILED INSPECTION OF THE FAN COWL DOOR LATCHES AND SURROUNDING STRUCTURE (150MM AROUND L | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.048611
B-LAD | Q | HE32-712121-02-1-01 (R0001) / DETAILED INSPECTION OF FORWARD ENGINE MOUNT INSTALLATION EXPOSED SURFACES OF NO.1 ENG | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0375
B-LAD | Q | HE32-712121-02-1-02 (R0001) / DETAILED INSPECTION OF FORWARD ENGINE MOUNT INSTALLATION EXPOSED SURFACES OF NO.2 ENG | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0375
B-LAD | Q | HE32-712221-02-1-01 (R0001) / DETAILED INSPECTION OF AFT ENGINE MOUNT INSTALLATION EXPOSED SURFACES OF NO.1 ENG | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0375
B-LAD | Q | HE32-712221-02-1-02 (R0001) / DETAILED INSPECTION OF AFT ENGINE MOUNT INSTALLATION EXPOSED SURFACES OF NO.2 ENG | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0375
B-LAD | Q | HE32-722102-01-1-01 (R0002) / DETAILED INSPECTION OF NO.1 ENGINE FAN CASE V-GROOVE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.070833
B-LAD | Q | HE32-722102-01-1-02 (R0002) / DETAILED INSPECTION OF NO.2 ENGINE FAN CASE V-GROOVE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.070833
B-LAD | Q | HE32-783216-01-1-01 (R0002) / DETAILED INSPECTION OF THRUST REVERSER V-BLADES OF NO.1 ENG | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.056944
B-LAD | Q | HE32-783216-01-1-02 (R0002) / DETAILED INSPECTION OF THRUST REVERSER V-BLADES OF NO.2 ENG | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.056944
B-LAD | Q | HE32-ZL-110-01-1 (R0002) / GENERAL VISUAL INSPECTION OF RADOME (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.011111
B-LAD | Q | HE32-ZL-121-02-1 (R0002) / GENERAL VISUAL INSPECTION OF FORWARD AVIONIC COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.066667
B-LAD | Q | HE32-ZL-125-02-1 (R0003) / GENERAL VISUAL INSPECTION OF LATERAL AVIONIC COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.041667
B-LAD | Q | HE32-ZL-127-02-2 (R0002) / GENERAL VISUAL INSPECTION OF REAR AVIONIC COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.069444
B-LAD | Q | HE32-ZL-131-02-1 (R0003) / GENERAL VISUAL INSPECTION OF FORWARD CARGO COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.036111
B-LAD | Q | HE32-ZL-133-01-1 (R0004) / GENERAL VISUAL INSPECTION OF UNDERFLOOR BAY OF FWD CARGO COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.05
B-LAD | Q | HE32-ZL-145-01-1 (R0002) / GENERAL VISUAL INSPECTION OF ZONE UNDER CABIN FLOOR (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.13611
B-LAD | Q | HE32-ZL-147-03-1 (R0003) / GENERAL VISUAL INSPECTION OF MLG-WELL AND HYDRAULIC COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.05
B-LAD | Q | HE32-ZL-151-02-3 (R0003) / GENERAL VISUAL INSPECTION OF AFT CARGO COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.091667
B-LAD | Q | HE32-ZL-153-01-1 (R0003) / GENERAL VISUAL INSPECTION OF UNDERFLOOR BAY OF AFT CARGO COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.036111
B-LAD | Q | HE32-ZL-161-02-3 (R0001) / GENERAL VISUAL INSPECTION OF BULK CARGO COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.072222
B-LAD | Q | HE32-ZL-163-01-1 (R0002) / GENERAL VISUAL INSPECTION OF UNDERFLOOR BAY OF BULK CARGO COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.055556
B-LAD | Q | HE32-ZL-171-02-1 (R0003) / GENERAL VISUAL INSPECTION OF AFT CABIN UNDERFLOOR COMPARTMENT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.075
B-LAD | Q | HE32-ZL-191-02-1 (R0004) / GENERAL VISUAL INSPECTION OF AIR CONDITIONING COMPARTMENT AND FAIRINGS (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.26944
B-LAD | Q | HE32-ZL-193-01-1 (R0003) / GENERAL VISUAL INSPECTION OF UPPER WING FAIRING SLIDE STOWAGE (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.025
B-LAD | Q | HE32-ZL-197-01-1 (R0002) / GENERAL VISUAL INSPECTION OF REAR FAIRING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.14028
B-LAD | Q | HE32-ZL-211-01-1 (R0002) / GENERAL VISUAL INSPECTION OF COCKPIT (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.05
B-LAD | Q | HE32-ZL-317-01-1 (R0002) / GENERAL VISUAL INSPECTION OF TAIL CONE APU EXHAUST AREA (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.011111
B-LAD | Q | HE32-ZL-325-02-3 (R0001) / GENERAL VISUAL INSPECTION OF VERTICAL STABILIZER TRAILING EDGE (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.077778
B-LAD | Q | HE32-ZL-331-01-1 (R0002) / GENERAL VISUAL INSPECTION OF TRIMMABLE HORIZONTAL STABILIZER LEADING EDGE (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.175
B-LAD | Q | HE32-ZL-334-02-1 (R0002) / GENERAL VISUAL INSPECTION OF TRIMMABLE HORIZONTAL STABILIZER TRAILING EDGE (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.24167
B-LAD | Q | HE32-ZL-433-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF AIR INTAKE OF NO.1 ENG (EWIS) (INTERNAL AREA AS FAR AS VISIBL | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.075694
B-LAD | Q | HE32-ZL-433-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF AIR INTAKE OF NO.2 ENG (EWIS) (INTERNAL AREA AS FAR AS VISIBL | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.050694
B-LAD | Q | HE32-ZL-473-01-1-01 (R0003) / GENERAL VISUAL INSPECTION OF AFT PYLON FAIRING OF LH PYLON (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.048611
B-LAD | Q | HE32-ZL-473-01-1-02 (R0003) / GENERAL VISUAL INSPECTION OF AFT PYLON FAIRING OF RH PYLON (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.048611
B-LAD | Q | HE32-ZL-521-01-1-01 (R0003) / GENERAL VISUAL INSPECTION OF STRUCTURE OF INBOARD FIXED LEADING-EDGE OF LH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.050694
B-LAD | Q | HE32-ZL-521-01-1-02 (R0003) / GENERAL VISUAL INSPECTION OF STRUCTURE OF INBOARD FIXED LEADING-EDGE OF RH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.050694
B-LAD | Q | HE32-ZL-522-01-2-01 (R0002) / GENERAL VISUAL INSPECTION OF STRUCTURE OF OUTBOARD FIXED LEADING-EDGE OF LH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.092361
B-LAD | Q | HE32-ZL-522-01-2-02 (R0002) / GENERAL VISUAL INSPECTION OF STRUCTURE OF OUTBOARD FIXED LEADING-EDGE OF RH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.092361
B-LAD | Q | HE32-ZL-531-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING OF LH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.044444
B-LAD | Q | HE32-ZL-531-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING OF RH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.044444
B-LAD | Q | HE32-ZL-532-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING OF LH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.044444
B-LAD | Q | HE32-ZL-532-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING OF RH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.044444
B-LAD | Q | HE32-ZL-533-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING OF LH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.044444
B-LAD | Q | HE32-ZL-533-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING OF RH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.044444
B-LAD | Q | HE32-ZL-534-01-3-01 (R0003) / GENERAL VISUAL INSPECTION OF LH WING TIP (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.055556
B-LAD | Q | HE32-ZL-534-01-3-02 (R0003) / GENERAL VISUAL INSPECTION OF RH WING TIP (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.055556
B-LAD | Q | HE32-ZL-540-01-1-01 (R0003) / GENERAL VISUAL INSPECTION OF WING FUEL TANK OF LH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.058333
B-LAD | Q | HE32-ZL-540-01-1-02 (R0003) / GENERAL VISUAL INSPECTION OF WING FUEL TANK OF RH WING (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.055556
B-LAD | Q | HE32-ZL-571-02-1 (R0002) / GENERAL VISUAL INSPECTION OF MLG BAY (EWIS) | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.038889
B-LAD | Q | HE32-ZL-811-01-1 (R0002) / GENERAL VISUAL INSPECTION OF FWD AVIONICS COMPARTMENT DOOR (EWIS) (INCLUDING EXTERNAL SURFACE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.0083333
B-LAD | Q | HE32-ZL-812-01-1 (R0002) / GENERAL VISUAL INSPECTION OF LATERAL AVIONICS COMPARTMENT DOORS (EWIS) (INCLUDING EXTERNAL SU | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.022222
B-LAD | Q | HE32-ZL-824-01-1 (R0002) / GENERAL VISUAL INSPECTION OF REAR AVIONIC COMPARTMENT DOOR (EWIS) (INCLUDING EXTERNAL SURFACE | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.011111
B-LAD | Q | HE32-ZL-833-02-1 (R0002) / GENERAL VISUAL INSPECTION OF FWD AND AFT OVERWING EMERGENCY EXIT HATCHES (INCLUDING DOOR SURR | D | 290 | 13.Aug.2026 | 2026-08-13 |  | 0 | Thr. 2'191 D | 1 | 86 | 0.094444
B-LAE | Q | HE32-291000-15-1 (R0003) / ANALYZE HYDRAULIC FLUID (HYDRAULIC FLUID SAMPLING) | D | 291 | 14.Aug.2026 | 2026-08-14 |  | 0 | 730 D | 1 | 60 | 0.10972
B-LAB | Q | HE32-ZL-825-01-1 (R0003) / GENERAL VISUAL INSPECTION OF FWD CARGO COMPARTMENT DOOR (INCLUDING FUSELAGE DOOR SILL, DOOR S | D | 294 | 17.Aug.2026 | 2026-08-17 | 2026-06-01 | B-LAB-PLN-7.5K-OOP_2026 | 1'095 D | 1 | 93 | 0.019444 |  | BRIDGE AT 7.5K 2026
B-LAB | Q | HE32-ZL-826-01-1 (R0003) / GENERAL VISUAL INSPECTION OF AFT CARGO COMPARTMENT DOOR (INCLUDING FUSELAGE DOOR SILL, DOOR S | D | 294 | 17.Aug.2026 | 2026-08-17 | 2026-06-01 | B-LAB-PLN-7.5K-OOP_2026 | 1'095 D | 1 | 93 | 0.019444 |  | BRIDGE AT 7.5K 2026 FOR TASK ESCALATE TO 1C INTERVAL
B-LAA | Q | HE32-256241-05-1 (R0003) / CLEAN DOOR GIRT BAR FITTING STOP LEVERS | C | 1'022 | 6'718 | 2026-08-18 |  | 0 | 1'110 | 1 | 7 | 0.05
B-LAD | Q | HE32-545228-01-1-01 (R0002) / GENERAL VISUAL INSPECTION OF LH PYLON, REVERSER FITTINGS | H | 3169:55 | 13100:00 | 2026-08-18 |  | 0 | Thr. 13'100 | 1 | 75 | 0.021528
B-LAD | Q | HE32-545228-01-1-02 (R0002) / GENERAL VISUAL INSPECTION OF RH PYLON, REVERSER FITTINGS | H | 3169:55 | 13100:00 | 2026-08-18 |  | 0 | Thr. 13'100 | 1 | 75 | 0.024306
B-LAD | D | EOI-49-0006/[131-9A] REMOVE AND DISCARD OIL FILTER ELEMENTS (8069KM) AND (8076KM) | D | 296 | 19.Aug.2026 | 2026-08-19 |  | 0 | 730 D | 2 | 59 | 0.041667 | 3800708-1 / P-8927
B-LAE | Q | HE32-342200-02-1 (R0003) / DRAINING AND FLUSHING OF STANDBY PNEUMATIC CIRCUITS | H | 3190:03 | 12263:39 | 2026-08-19 |  | 0 | 6'000 | 1 | 46 | 0.26806
B-LAD | Q | HE32-256241-05-1 (R0003) / CLEAN DOOR GIRT BAR FITTING STOP LEVERS | C | 1'058 | 4'944 | 2026-08-20 |  | 0 | 1'110 | 1 | 4 | 0.05
B-LAB | D | EO-VSB-26-0001/FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 298 | 21.Aug.2026 | 2026-08-21 |  | 0 | 365 D | 1 | 18 | 0.020833 | P3APP003010A / 000617
B-LAB | D | EO-VSB-26-0001/FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 298 | 21.Aug.2026 | 2026-08-21 |  | 0 | 365 D | 1 | 18 | 0.020833 | P3APP003010A / 000360
B-LAB | D | EO-VSB-26-0001/FIRE EXTINGUISHER – INSPECTION FOR HIGH TEMPERATURE | D | 298 | 21.Aug.2026 | 2026-08-21 |  | 0 | 365 D | 1 | 18 | 0.020833 | P3APP003010A / 000439
B-LAE | Q | HE32-256551-01-1 (R0002) / DISCARD AND REPLACE MEGAPHONE BATTERIES | D | 298 | 21.Aug.2026 | 2026-08-21 |  | 0 | 365 D | 1 | 18 | 0.020833
B-LAE | Q | HE32-274451-11-1 (R0004) / DETAILED INSPECTION OF THSA UPPER ATTACHMENTS FOR PRIMARY AND SECONDARY LOAD PATH | D | 298 | 21.Aug.2026 | 2026-08-21 |  | 0 | 304 D | 1 | 1 | 0.086111
B-LAD | Q | HE32-323300-05-2 (R0002) / OPERATIONAL CHECK OF FREE-FALL MECHANICAL CONTROL | H | 3204:54 | 13134:59 | 2026-08-21 |  | 0 | 7'700 | 1 | 58 | 0.25417
B-LAE | Q | HE32-561000-02-1 (R0003) / DETAILED INSPECTION OF ALL COCKPIT WINDOWS FROM OUTSIDE INCLUDING SEALS | D | 298 | 21.Aug.2026 | 2026-08-21 |  | 0 | 365 D | 1 | 18 | 0.054167
B-LAE | Q | HE32-ZL-400-02-4 (R0003) / GENERAL VISUAL INSPECTION OF POWERPLANTS, NACELLES AND PYLONS | D | 298 | 21.Aug.2026 | 2026-08-21 |  | 0 | 365 D | 1 | 18 | 0.011111
B-LAC | Q | HE32-275446-01-1-02 (R0002) / LUBRICATE FLAP TRACK 1 DRIVE LEVER ARM AND ALL CARRIAGE ROLLERS ON ALL FLAP TRACKS OF THE | D | 299 | 22.Aug.2026 | 2026-08-22 |  | 0 | 304 D | 1 | 1 | 0.055556
B-LAA | Q | HE32-275446-01-1-01 (R0002) / LUBRICATE FLAP TRACK 1 DRIVE LEVER ARM AND ALL CARRIAGE ROLLERS ON ALL FLAP TRACKS OF THE | D | 300 | 23.Aug.2026 | 2026-08-23 |  | 0 | 304 D | 1 | 1 | 0.055556
B-LAE | V | REPLACE FAKHKG02SW/EFK-927 (FIRST AID KIT) | ID | 301 | 2'149 | 2026-08-24 |  | 0 |  | 2 |  | 0.0125 | FAKHKG02SW / EFK-927 | PLN: Please double check if the expiry day of the sad kit is correct.
B-LAB | Q | HE32-274451-11-1 (R0004) / DETAILED INSPECTION OF THSA UPPER ATTACHMENTS FOR PRIMARY AND SECONDARY LOAD PATH | D | 302 | 25.Aug.2026 | 2026-08-25 |  | 0 | 304 D | 1 | 0 | 0.086111
B-LAB | Q | HE32-275446-01-1-02 (R0002) / LUBRICATE FLAP TRACK 1 DRIVE LEVER ARM AND ALL CARRIAGE ROLLERS ON ALL FLAP TRACKS OF THE | D | 302 | 25.Aug.2026 | 2026-08-25 |  | 0 | 304 D | 1 | 0 | 0.055556
B-LAC | Q | HE32-323100-01-1 (R0003) / BITE CHECK OF LANDING-GEAR CONTROL INTERFACE-UNIT (LGCIU) WITH USE OF MCDU TO ENSURE THAT CON | H | 3251:21 | 11279:53 | 2026-08-25 |  | 0 | 4'000 | 1 | 18 | 0.016667
B-LAC | V | REPLACE FAKHKG02SW/EFK-167 (FIRST AID KIT) | ID | 303 | 657 | 2026-08-26 |  | 0 |  | 2 |  | 0.0125 | FAKHKG02SW / EFK-167 | PLN: Please double check if the expiry day of the sad kit is correct.
B-LAD | V | REPLACE FAKHKG02SW/EFK-183 (FIRST AID KIT) | ID | 304 | 578 | 2026-08-27 |  | 0 |  | 2 |  | 0.0125 | FAKHKG02SW / EFK-183 | PLN: Please double check if the expiry day of the sad kit is correct.
B-LAD | D | EOA32-29-0012/A32 SERIAL AIRPALNES` HYDRAULIC COMPONENTS LEAK CHECK AND CLEAN | D | 307 | 30.Aug.2026 | 2026-08-30 |  | 0 | 547 D | 2 | 43 | 0.29167
B-LAB | D | EO-A320-56-1023/WINDOWS - FIXED WINDOWS - INSPECTION OF FRONT WINDSHIELD | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.13542 | STA320-2-8-2 / 23192
B-LAB | D | EO-A320-56-1023/WINDOWS - FIXED WINDOWS - INSPECTION OF FRONT WINDSHIELD | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.13542 | STA320-1-8-2 / 71055
B-LAB | D | EOA32-24-0016/APPLY TEMPORARY PROTECTION TO END FITTINGS OF A32 SERIES AIRCRAFT OF E | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 36 MT | 2 | 71 | 0.055556 |  | EOE: Plan with HE32-ZL-575-01-1 with standard C CHK package
B-LAB | Q | HE32-200435-02-1-01 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE FAN COMPARTMENT OF NO.1 ENG (EWIS) | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.027778
B-LAB | Q | HE32-200435-02-1-02 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE FAN COMPARTMENT OF NO.2 ENG (EWIS) | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.027778
B-LAB | Q | HE32-200453-02-1-01 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE CORE COMPARTMENT OF NO.1 ENG (EWIS) | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.05
B-LAB | Q | HE32-200453-02-1-02 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE CORE COMPARTMENT OF NO.2 ENG (EWIS) | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.05
B-LAB | Q | HE32-272100-08-1 (R0002) / LUBRICATE THE RUDDER PEDAL ADJUSTMENT MECHANISM | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.077778
B-LAB | Q | HE32-272400-03-1 (R0001) / LUBRICATE RUDDER HINGE BEARING NO. 6 | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.088889
B-LAB | Q | HE32-272400-06-1 (R0002) / LUBRICATE THE RUDDER SERVOCONTROL ROD EYE END BEARING | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.077778
B-LAB | Q | HE32-273400-08-1 (R0002) / LUBRICATE THE ELEVATOR SERVOCONTROL ROD EYE END BEARING | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.11389
B-LAB | Q | HE32-274100-03-1 (R0001) / LUBRICATE THE THS MECHANICAL CONTROL CHAINS AND REAR CABLE (AREA OF TENSION REGULATOR) | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.2875
B-LAB | Q | HE32-291000-25-1 (R0001) / OPERATIONAL CHECK OF PORT D CHECK VALVE OF PTU MANIFOLD IN GREEN AND YELLOW HYDRAULIC SYSTEM | D | 308 | 31.Aug.2026 | 2026-08-31 | 2026-06-01 | B-LAB-PLN-7.5K-OOP_2026 |  | 1 |  | 0.22917 |  | MR info: AMS I5R0 Bridging applied. Do not defer this task.
B-LAB | Q | HE32-383100-05-1 (R0002) / DETAILED INSPECTION OF CLEANLINESS INSIDE THE WASTE TANK | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.28472
B-LAB | Q | HE32-521000-14-1 (R0003) / LUBRICATE THE HINGE ARM SUPPORT FITTING BEARINGS OF PASSENGER DOORS | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.052778
B-LAB | Q | HE32-521121-01-1 (R0003) / LUBRICATE THE EXTERIOR CONTROL HANDLES AND TELESCOPIC ARMS OF PASSENGER DOORS | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.083333
B-LAB | Q | HE32-523000-01-1 (R0002) / LUBRICATIE THE CARGO DOORS | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.15833
B-LAB | Q | HE32-523000-03-1 (R0002) / LUBRICATE EXTERIOR CARGO DOOR HANDLE | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.066667
B-LAB | Q | HE32-523300-01-1 (R0002) / LUBRICATE THE BULK CARGO COMPARTMENT DOOR HANDLE AND HINGE ARM BEARINGS | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.033333
B-LAB | Q | HE32-ZL-435-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF FAN COMPARTMENT OF NO.1 ENG (EWIS) | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.017361
B-LAB | Q | HE32-ZL-435-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF FAN COMPARTMENT OF NO.2 ENG (EWIS) | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 | 730 D | 1 | 57 | 0.017361
B-LAC | V | REPLACE 2100-1228-02/002030565 (COCKPIT VOICE RECORDER) | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 |  | 2 |  | 0.0083333 | 2100-1228-02 / 002030565
B-LAA | V | REPLACE UPK-HKG-01/EUK-013 (UNIVERAL PRECAUTION KIT) | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 |  | 2 |  | 0.0125 | UPK-HKG-01 / EUK-013
B-LAB | V | REPLACE UPK-HKG-01/EUK-061 (UNIVERAL PRECAUTION KIT) | D | 308 | 31.Aug.2026 | 2026-08-31 |  | 0 |  | 2 |  | 0.0125 | UPK-HKG-01 / EUK-061
B-LAE | D | EOCOM-32-0324/DETAILED VISUAL INSPECTION OF NLG TORQUE LINK APEX PIN AND NUT | D | 309 | 01.Sep.2026 | 2026-09-01 |  | 0 | 540 D | 2 | 42 | 0.25 |  | EOE: Align with AMS task HE32-322127-01-1 if possible
B-LAA | V | REPLACE 15-40F80/78253009 (PBE) | D | 309 | 01.Sep.2026 | 2026-09-01 |  | 0 |  | 2 |  | 0.016667 | 15-40F80 / 78253009
B-LAC | V | REPLACE 15-40F80/78577036 (PBE) | D | 309 | 01.Sep.2026 | 2026-09-01 |  | 0 |  | 2 |  | 0.016667 | 15-40F80 / 78577036
B-LAC | V | REPLACE 15-40F80/78577042 (PBE) | D | 309 | 01.Sep.2026 | 2026-09-01 |  | 0 |  | 2 |  | 0.016667 | 15-40F80 / 78577042
B-LAC | V | REPLACE 15-40F80/78577048 (PBE) | D | 309 | 01.Sep.2026 | 2026-09-01 |  | 0 |  | 2 |  | 0.016667 | 15-40F80 / 78577048
B-LAC | V | REPLACE 15-40F80/78577056 (PBE) | D | 309 | 01.Sep.2026 | 2026-09-01 |  | 0 |  | 2 |  | 0.016667 | 15-40F80 / 78577056
B-LAB | Q | HE32-341300-07-1-02 (R0002) / FLUSH THE RH TOTAL PRESSURE LINE | H | 3341:42 | 15749:09 | 2026-09-02 |  | 0 | 6'000 | 1 | 44 | 0.086111
B-LAB | Q | HE32-783200-W3-1-02 (R0003) / GENERAL VISUAL INSPECTION OF THE THRUST REVERSER FIRE SEALS AND VAPOR BARRIER SEALS OF NO. | H | 3341:42 | 15749:09 | 2026-09-02 |  | 0 | 6'000 | 1 | 44 | 0.063889
B-LAD | D | EOA32-32-0056/INSPECTION OF HYD LEAKAGE AT NLG SWIVEL SELECTOR UNION FOR A32 SERIES | H | 3350:55 | 13281:00 | 2026-09-03 |  | 0 | 7'500 | 2 | 55 | 0.041667
B-LAE | D | EO-A320-56-1023/WINDOWS - FIXED WINDOWS - INSPECTION OF FRONT WINDSHIELD | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.13542 | STA320-2-8-2 / 28452
B-LAE | D | EO-A320-56-1023/WINDOWS - FIXED WINDOWS - INSPECTION OF FRONT WINDSHIELD | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.13542 | STA320-1-8-2 / 94715
B-LAE | D | EOA32-24-0016/APPLY TEMPORARY PROTECTION TO END FITTINGS OF A32 SERIES AIRCRAFT OF E | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 36 MT | 2 | 71 | 0.055556 |  | EOE: Plan with HE32-ZL-575-01-1 with standard C CHK package
B-LAE | Q | HE32-200435-02-1-01 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE FAN COMPARTMENT OF NO.1 ENG (EWIS) | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.027778
B-LAE | Q | HE32-200435-02-1-02 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE FAN COMPARTMENT OF NO.2 ENG (EWIS) | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.027778
B-LAE | Q | HE32-200453-02-1-01 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE CORE COMPARTMENT OF NO.1 ENG (EWIS) | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.05
B-LAE | Q | HE32-200453-02-1-02 (R0003) / DETAILED INSPECTION OF EWIS INSTALLED IN THE CORE COMPARTMENT OF NO.2 ENG (EWIS) | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.05
B-LAE | Q | HE32-212600-08-1 (R0003) / OPERATIONAL CHECK OF AIR INLET CHECK VALVE 2150HM | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.027083
B-LAE | Q | HE32-272100-08-1 (R0002) / LUBRICATE THE RUDDER PEDAL ADJUSTMENT MECHANISM | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.077778
B-LAE | Q | HE32-272400-06-1 (R0002) / LUBRICATE THE RUDDER SERVOCONTROL ROD EYE END BEARING | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.077778
B-LAE | Q | HE32-273400-02-2-01 (R0002) / FUNCTIONAL CHECK OF THE LH ELEVATOR SERVOCONTROL BEARINGS FOR EXCESSIVE PLAY AND CONDITION | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.047222
B-LAE | Q | HE32-273400-02-2-02 (R0002) / FUNCTIONAL CHECK OF THE RH ELEVATOR SERVOCONTROL BEARINGS FOR EXCESSIVE PLAY AND CONDITION | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.047222
B-LAE | Q | HE32-273400-08-1 (R0002) / LUBRICATE THE ELEVATOR SERVOCONTROL ROD EYE END BEARING | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.11389
B-LAE | Q | HE32-291000-25-1 (R0001) / OPERATIONAL CHECK OF PORT D CHECK VALVE OF PTU MANIFOLD IN GREEN AND YELLOW HYDRAULIC SYSTEM | D | 316 | 08.Sep.2026 | 2026-09-08 | 2026-05-23 | B-LAE-PLN-BM-OOP_2026 |  | 1 |  | 0.22917 |  | MR info: AMS I5R0 Bridging applied. Do not defer this task.
B-LAE | Q | HE32-303100-01-1-01 (R0001) / FUNCTIONAL CHECK OF THE INSULATION RESISTANCE OF NO.1 PITOT PROBE HEATER | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.066667
B-LAE | Q | HE32-303100-01-1-02 (R0001) / FUNCTIONAL CHECK OF THE INSULATION RESISTANCE OF NO.2 PITOT PROBE HEATER | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.066667
B-LAE | Q | HE32-303100-01-1-03 (R0001) / FUNCTIONAL CHECK OF THE INSULATION RESISTANCE OF NO.3 PITOT PROBE HEATER | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.066667
B-LAE | Q | HE32-322113-01-1 (R0002) / FUNCTIONAL CHECK OF NLG SHOCK ABSORBER CHARGE PRESSURE AND FLUID LEVEL | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.25
B-LAE | Q | HE32-323100-02-1 (R0003) / DETAILED INSPECTION OF GEAR UPLOCK AND DOOR UPLOCK UNITS AND ROLLERS/PINS | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.1
B-LAE | Q | HE32-34-SCME-010 (R0002) / FUNCTIONAL TEST OF THE ATC/MODE S TRANSPONDER AND VERIFICATION OF THE MODE S ADDRESS | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.095833
B-LAE | Q | HE32-351000-01-1 (R0002) / OPERATIONAL CHECK OF FLIGHT CREW OXYGEN SYSTEM | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.05
B-LAE | Q | HE32-351241-01-1 (R0002) / DETAILED INSPECTION OF OXYGEN MASKS (OUT OF BOX) WITH HARNESS INFLATED | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.0625
B-LAE | Q | HE32-383100-02-1 (R0002) / CLEAN AND DO AN INSPECTION OF THE WATER SEPARATOR AND ASSOCIATED FILTER ELEMENT | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.1875
B-LAE | Q | HE32-383100-05-1 (R0002) / DETAILED INSPECTION OF CLEANLINESS INSIDE THE WASTE TANK | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.28472
B-LAE | Q | HE32-521000-14-1 (R0003) / LUBRICATE THE HINGE ARM SUPPORT FITTING BEARINGS OF PASSENGER DOORS | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.052778
B-LAE | Q | HE32-521121-01-1 (R0003) / LUBRICATE THE EXTERIOR CONTROL HANDLES AND TELESCOPIC ARMS OF PASSENGER DOORS | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.083333
B-LAE | Q | HE32-523000-01-1 (R0002) / LUBRICATIE THE CARGO DOORS | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.15833
B-LAE | Q | HE32-523000-03-1 (R0002) / LUBRICATE EXTERIOR CARGO DOOR HANDLE | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.066667
B-LAE | Q | HE32-523300-01-1 (R0002) / LUBRICATE THE BULK CARGO COMPARTMENT DOOR HANDLE AND HINGE ARM BEARINGS | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.033333
B-LAE | Q | HE32-ZL-100-02-1 (R0002) / GENERAL VISUAL INSPECTION OF THE LOWER HALF OF THE FUSELAGE | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.034028
B-LAE | Q | HE32-ZL-123-02-1 (R0002) / GENERAL VISUAL INSPECTION OF NOSE GEAR WELL (EWIS) | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.013194
B-LAE | Q | HE32-ZL-191-01-2 (R0004) / GENERAL VISUAL INSPECTION OF AIR CONDITIONING COMPARTMENT AND FAIRINGS (EWIS) | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.15833
B-LAE | Q | HE32-ZL-435-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF FAN COMPARTMENT OF NO.1 ENG (EWIS) | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.017361
B-LAE | Q | HE32-ZL-435-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF FAN COMPARTMENT OF NO.2 ENG (EWIS) | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.017361
B-LAE | Q | HE32-ZL-831-01-1 (R0002) / GENERAL VISUAL INSPECTION OF AFT PASSENGER/CREW DOORS INCLUDING DOOR STOPS ON FUSELAGE DOOR F | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.050694
B-LAE | Q | HE32-ZL-831-04-1 (R0002) / GENERAL VISUAL INSPECTION OF FWD PASSENGER/CREW DOORS INCLUDING DOOR STOPS ON FUSELAGE DOOR F | D | 316 | 08.Sep.2026 | 2026-09-08 |  | 0 | 730 D | 1 | 56 | 0.050694
B-LAE | D | EOA32-32-0056/INSPECTION OF HYD LEAKAGE AT NLG SWIVEL SELECTOR UNION FOR A32 SERIES | H | 3453:40 | 12527:16 | 2026-09-13 |  | 0 | 7'500 | 2 | 53 | 0.041667
B-LAE | Q | HE32-262300-05-1 (R0005) / FUNCTIONAL CHECK OF TIME DELAY FOR ILLUMINATION OF "DISCH AGENT 2" REMINDER LIGHT | H | 3474:54 | 12548:30 | 2026-09-15 |  | 0 | 4'400 | 1 | 21 | 0.12639
B-LAE | Q | HE32-262300-06-5 (R0005) / CHECK OF FIRING CIRCUIT CONTINUITY AND THE OPERATIONAL CHECK OF PRIORITY SWITCHING | H | 3474:54 | 12548:30 | 2026-09-15 |  | 0 | 4'400 | 1 | 21 | 0.061111
B-LAC | Q | HE32-256551-01-1 (R0002) / DISCARD AND REPLACE MEGAPHONE BATTERIES | D | 324 | 16.Sep.2026 | 2026-09-16 |  | 0 | 365 D | 1 | 11 | 0.020833
B-LAC | Q | HE32-561000-02-1 (R0003) / DETAILED INSPECTION OF ALL COCKPIT WINDOWS FROM OUTSIDE INCLUDING SEALS | D | 324 | 16.Sep.2026 | 2026-09-16 |  | 0 | 365 D | 1 | 11 | 0.054167
B-LAC | Q | HE32-ZL-400-02-4 (R0003) / GENERAL VISUAL INSPECTION OF POWERPLANTS, NACELLES AND PYLONS | D | 324 | 16.Sep.2026 | 2026-09-16 |  | 0 | 365 D | 1 | 11 | 0.011111
B-LAD | Q | HE32-254000-01-1 (R0003) / DETAILED INSPECTION OF WASTE COMPARTMENT INCLUDING WASTE FLAP AND OPERATIONAL CHECK OF WASTE | H | 3504:54 | 13434:59 | 2026-09-18 |  | 0 | 8'000 | 1 | 56 | 0.029167
B-LAD | Q | HE32-292000-04-1 (R0003) / OPERATIONAL CHECK OF RAT MANUAL DEPLOYMENT AND FUNCTIONAL CHECK OF RAT USING GROUND TEST UNIT | H | 3510:16 | 13440:21 | 2026-09-18 |  | 0 | 4'000 | 1 | 12 | 0.38611
B-LAD | Q | HE32-323000-17-1 (R0005) / FUNCTIONAL CHECK OF LGCIU POWER SUPPLY RELAYS | H | 3504:54 | 13434:59 | 2026-09-18 |  | 0 | 8'000 | 1 | 56 | 0.034722
B-LAE | Q | HE32-711312-02-1-01 (R0001) / GENERAL VISUAL INSPECTION OF FAN COWL DOORS LATCHES AND SURROUNDING STRUCTURE (150 MM AROU | H | 3515:32 | 12589:08 | 2026-09-19 |  | 0 | 6'800 | 1 | 48 | 0.027778
B-LAE | Q | HE32-783219-01-1-01 (R0001) / GENERAL VISUAL INSPECTION OF THRUST REVERSER LATCH BEAMS, LATCH 1A/1B, LATCH 2 TO 4 AND SU | H | 3515:32 | 12589:08 | 2026-09-19 |  | 0 | 6'800 | 1 | 48 | 0.040278
B-LAE | Q | HE32-783220-01-1-01 (R0001) / GENERAL VISUAL INSPECTION OF THRUST REVERSER LOWER BUMPER 2, LATCH 5 AND SURROUNDING STRUC | H | 3515:32 | 12589:08 | 2026-09-19 |  | 0 | 6'800 | 1 | 48 | 0.070833
B-LAA | Q | HE32-470000-01-1 (R0004) / REPLACE D-ULPA FILTER ELEMENT | H | 3554:06 | 18990:40 | 2026-09-22 |  | 0 | 7'000 | 1 | 49 | 0.091667
B-LAA | D | EOA32-32-0056/W1324550 /INSPECTION OF HYD LEAKAGE AT NLG SWIVEL SELECTOR UNION FOR A32 SERIES | H | 3588:47 | 19025:21 | 2026-09-26 | 2025-11-01 | B-LAA-PLN-7.5K_2025 | 7'500 | 2 | 53 | 0.041667
B-LAE | Q | HE32-274000-03-1 (R0004) / OPERATIONAL CHECK OF THS ACTUATOR JAMMING PROTECTION DEVICE | H | 3602:56 | 12676:32 | 2026-09-27 |  | 0 | 6'000 | 1 | 39 | 0.073611
B-LAE | Q | HE32-274451-02-2 (R0003) / CHECK THE OIL LEVEL OF THE THS-ACTUATOR GEARBOX | H | 3602:56 | 12676:32 | 2026-09-27 |  | 0 | 6'000 | 1 | 39 | 0.023611
B-LAA | Q | HE32-292251-02-1 (R0002) / DETAILED INSPECTION OF RAT ASSEMBLY AND DOORS IN DEPLOYED POSITION AND LUBRICATION OF DOORS L | D | 335 | 27.Sep.2026 | 2026-09-27 |  | 0 | 608 D | 1 | 44 | 0.18472
B-LAB | Q | HE32-273400-01-1 (R0003) / OPERATIONAL CHECK OF THE ELEVATOR DAMPING MEASUREMENT BY BITE | H | 3619:17 | 16026:44 | 2026-09-28 |  | 0 | 5'000 | 1 | 27 | 0.015278
B-LAE | Q | HE32-216000-01-1 (R0004) / CLEAN THE COCKPIT AND CABIN SENSOR DUCT AND TEMPERATURE SENSOR | H | 3631:00 | 12704:36 | 2026-09-29 |  | 0 | 7'500 | 1 | 51 | 0.088889
B-LAE | Q | HE32-253000-02-1 (R0003) / REMOVE AND DISCARD FILTER ELEMENT OF GALLEY | H | 3631:00 | 12704:36 | 2026-09-29 |  | 0 | 7'500 | 1 | 51 | 0.083333
B-LAB | Q | HE32-262300-05-1 (R0005) / FUNCTIONAL CHECK OF TIME DELAY FOR ILLUMINATION OF "DISCH AGENT 2" REMINDER LIGHT | H | 3627:38 | 16035:05 | 2026-09-29 |  | 0 | 4'400 | 1 | 17 | 0.12639
B-LAB | Q | HE32-262300-06-5 (R0005) / CHECK OF FIRING CIRCUIT CONTINUITY AND THE OPERATIONAL CHECK OF PRIORITY SWITCHING | H | 3627:38 | 16035:05 | 2026-09-29 |  | 0 | 4'400 | 1 | 17 | 0.061111
B-LAE | Q | HE32-281500-01-2 (R0003) / OPERATIONAL CHECK OF INDIVIDUAL TRANSFER VALVES TO ENSURE VALVE SHAFT ROTATES VALVE TO OPEN P | H | 3631:00 | 12704:36 | 2026-09-29 |  | 0 | 7'500 | 1 | 51 | 0.038889
B-LAD | Q | HE32-31-SCME-010 (R0005) / READOUT PROCEDURE FOR RECORDING INSPECTION OF FDR SYSTEM | D | 337 | 29.Sep.2026 | 2026-09-29 | 2026-08-29 | B-LAD-PLN-290826-LM | 365 D | 1 | 92 | 0.048611
B-LAB | V | REPLACE FAKHKG02SW/EFK-132 (FIRST AID KIT) | ID | 337 | 950 | 2026-09-29 |  | 0 |  | 2 |  | 0.0125 | FAKHKG02SW / EFK-132 | PLN: Please double check if the expiry day of the sad kit is correct.
B-LAC | Q | HE32-292000-04-1 (R0003) / OPERATIONAL CHECK OF RAT MANUAL DEPLOYMENT AND FUNCTIONAL CHECK OF RAT USING GROUND TEST UNIT | H | 3633:02 | 11661:34 | 2026-09-30 |  | 0 | 4'000 | 1 | 9 | 0.38611
B-LAE | V | REPLACE 3552AAADAACXCD/P12011135 (CYLINDER ASSY-OXYGEN PORTABLE) | D | 338 | 30.Sep.2026 | 2026-09-30 |  | 0 |  | 2 |  | 0.016667 | 3552AAADAACXCD / P12011135
B-LAA | V | REPLACE UPK-HKG-01/EUK-029 (UNIVERAL PRECAUTION KIT) | D | 338 | 30.Sep.2026 | 2026-09-30 |  | 0 |  | 2 |  | 0.0125 | UPK-HKG-01 / EUK-029
B-LAE | V | REPLACE UPK-HKG-01/EUK-128 (UNIVERAL PRECAUTION KIT) | D | 338 | 30.Sep.2026 | 2026-09-30 |  | 0 |  | 2 |  | 0.0125 | UPK-HKG-01 / EUK-128
B-LAE | V | REPLACE UPK-HKG-01/EUK-159 (UNIVERAL PRECAUTION KIT) | D | 338 | 30.Sep.2026 | 2026-09-30 |  | 0 |  | 2 |  | 0.0125 | UPK-HKG-01 / EUK-159
B-LAE | D | EO-A320-25-1CKY/W1575822 /MISCELLANEOUS EMERGENCY EQUIPMENT - REINTRODUCE ELT | D | 340 | 02.Oct.2026 | 2026-10-02 | 2026-05-23 | B-LAE-PLN-BM-OOP_2026 | Thr. 36 MT | 2 | 88 | 0.1875
B-LAE | D | EOA32-20-0006/W922336 /DETAILED INSPECTION OF BONDING LEADS LOCATED ON THE MOVABLE SURFACES | D | 340 | 02.Oct.2026 | 2026-10-02 | 2026-05-23 | B-LAE-PLN-2C_2026 | 1'095 D | 2 | 88 | 0.75 |  | 1C
B-LAE | D | EOA32-24-0010/OPENING AND CLOSING ALL CIRCUIT BREAKERS OF A32 SERIES AIRCRAFT | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 2 | 68 | 0.020833
B-LAD | D | EOA32-28-0015/W911935 /A32 SAMPLE FUEL FOR MICROBIOLOGICAL CONTAMINATION ANALYSIS | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'215 D | 2 | 72 | 0.058333
B-LAE | D | EOD-25-0016/W1510658 /A320-271N FLEET CARPETS REPLACEMENT | D | 340 | 02.Oct.2026 | 2026-10-02 | 2026-05-23 | B-LAE-PLN-1C_2026_PT | 1'095 D | 2 | 88 | 0.1875 |  | EOE: Assign either EOD-25-0016 / EOA32-25-0141 but not both
B-LAE | D | EOI-57-0002/DETAILED VISUAL INSPECTIONS OF LH/RH WING SLAT TRACK CLOSING PLATES | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 608 D | 2 | 44 | 0.10417
B-LAE | Q | HE32-200002-01-1-01 (R0002) / GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON HARNESSES 405VB TO 409VB FOR LH THS | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.041667
B-LAE | Q | HE32-200002-01-1-02 (R0002) / GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON HARNESSES 400VB TO 404VB FOR RH THS | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.041667
B-LAE | Q | HE32-237100-01-1 (R0002) / OPERATIONAL CHECK OF CVR AND CVR-CHANNEL RECORDING | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.033333
B-LAE | Q | HE32-243000-13-1 (R0001) / CLEAN THE TRANSFORMER RECTIFIER (TR) 1 AND 2 | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'461 D | 1 | 76 | 0.044444
B-LAE | Q | HE32-243000-14-1 (R0001) / CLEANING OF THE ESSENTIAL TRANSFORMER RECTIFIER | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'461 D | 1 | 76 | 0.041667
B-LAE | Q | HE32-256535-04-1 (R0005) / GENERAL VISUAL INSPECTION OF EXTERNAL ELT ANTENNA | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.041667
B-LAE | Q | HE32-256536-01-1 (R0002) / OPERATIONAL CHECK OF THE LOW-FREQUENCY UNDERWATER LOCATOR BEACON (ULB) | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.047222
B-LAE | Q | HE32-262541-04-1 (R0002) / VISUAL CHECK OF FIRE EXTINGUISHER BOTTLE PRESSURE READING | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.013889
B-LAE | Q | HE32-272100-12-1 (R0001) / LUBRICATE RUDDER CONTROL CABLES IN REAR PART (ZONE 310) | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.027778
B-LAE | Q | HE32-275451-01-1 (R0002) / REPLENISH FLAP PCU GEARBOX TO CONFIRM FLUID LEVEL | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.077778
B-LAE | Q | HE32-278451-01-1 (R0002) / REPLENISH SLAT PCU GEARBOX TO CONFIRM FLUID LEVEL | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.011111
B-LAE | Q | HE32-281247-01-1-01 (R0002) / VISUAL CHECK OF LHW NACA INTAKE FOR SIGNS OF BLOCKAGE | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.011111
B-LAE | Q | HE32-281247-01-1-02 (R0002) / VISUAL CHECK OF RHW NACA INTAKE FOR SIGNS OF BLOCKAGE | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.0097222
B-LAE | Q | HE32-291000-06-1 (R0002) / FUNCTIONAL CHECK OF THE POWER TRANSFER UNIT (PTU) YELLOW TO GREEN | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.0083333
B-LAE | Q | HE32-291000-20-1 (R0002) / OPERATIONAL CHECK OF EDP DEPRESSURIZATION | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.083333
B-LAE | Q | HE32-321113-04-1-01 (R0002) / FUNCTIONAL CHECK OF LEFT MLG SHOCK ABSORBER CHARGE PRESSURE | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.033333
B-LAE | Q | HE32-321113-04-1-02 (R0002) / FUNCTIONAL CHECK OF RIGHT MLG SHOCK ABSORBER CHARGE PRESSURE | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.033333
B-LAE | Q | HE32-323100-05-1 (R0002) / DETAILED INSPECTION OF NOSE GEAR DOOR OPERATING MECHANISM | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.030556
B-LAE | Q | HE32-353000-07-1 (R0003) / DETAILED INSPECTION OF PORTABLE OXYGEN MASK | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.016667
B-LAE | Q | HE32-491200-B2-1 (R0003) / GENERAL VISUAL INSPECTION OF APU SUSPENSION SYSTEM FOR CONDITION AND SECURITY | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.034028
B-LAE | Q | HE32-491300-B1-1 (R0004) / GENERAL VISUAL INSPECTION OF ALL APU COMPARTMENT FIRE WALLS AND SEALS | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.086111
B-LAE | Q | HE32-498000-B1-1 (R0003) / GENERAL VISUAL INSPECTION OF APU COMPARTMENT EXHAUST MUFFLER INSULATION COVERS AND BELLOWS | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.013889
B-LAE | Q | HE32-521000-02-1 (R0002) / FUNCTIONAL CHECK OF DOOR SUSPENSION | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.05
B-LAE | Q | HE32-521000-04-1 (R0002) / DETAILED INSPECTION OF PASSENGER/CREW DOOR FOR INTEGRITY AND GOOD ADJUSTMENT OF MECHANISMS (I | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.13611
B-LAE | Q | HE32-521121-02-1-01 (R0004) / LUBRICATE THE SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM OF LH FWD DOOR | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.30556
B-LAE | Q | HE32-521121-02-1-02 (R0004) / LUBRICATE THE SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM OF RH FWD DOOR | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.30556
B-LAE | Q | HE32-521121-02-1-03 (R0004) / LUBRICATE THE SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM OF LH AFT DOOR | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.30556
B-LAE | Q | HE32-521121-02-1-04 (R0004) / LUBRICATE THE SAFETY PIN GUIDE FITTING AND DOOR ARMING/DISARMING MECHANISM OF RH AFT DOOR | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.30556
B-LAE | Q | HE32-524100-02-1 (R0002) / LUBRICATE EXTERIOR AVIONIC COMPARTMENT DOOR HANDLE | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.016667
B-LAE | Q | HE32-531151-02-1 (R0001) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.040278
B-LAE | Q | HE32-531176-02-1 (R0001) / GENERAL VISUAL INSPECTION OF COCKPIT SIDE WINDOWS, EXTERNAL VISIBLE PORTION OF FRAMEWORK, BET | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.0041667
B-LAE | Q | HE32-531178-02-1 (R0003) / GENERAL VISUAL INSPECTION OF COCKPIT WINDSHIELD, EXTERNAL VISIBLE PORTION OF FRAMEWORK AND EX | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.0041667
B-LAE | Q | HE32-531182-02-1 (R0001) / DETAILED INSPECTION OF SLIDING WINDOW FRAME, UPPER AND LOWER FRAMES AND FR4 AND FR8 FRAMES, I | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.17222
B-LAE | Q | HE32-531900-03-1 (R0002) / OPERATIONAL CHECK OF PISTON TYPE DRAIN VALVES IN LOWER FUSELAGE SHELL FROM OUTSIDE | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.05
B-LAE | Q | HE32-531900-10-1 (R0001) / GENERAL VISUAL INSPECTION OF DRAIN HOLE AND GAP AT RADOME | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.0069444
B-LAE | Q | HE32-533900-01-1 (R0002) / OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE HOLES IN PRESSURE FLOOR FROM MLG BAY | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.0083333
B-LAE | Q | HE32-534134-02-1 (R0001) / DETAILED INSPECTION OF DOOR STOP FITTINGS PROTRUDING PART NOT COVERED BY THE LINING ON FRAME | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.026389
B-LAE | Q | HE32-535900-01-1 (R0002) / OPERATIONAL CHECK OF SINGLE DRAIN PIPE AFT OF FR 70 FROM OUTSIDE | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.013889
B-LAE | Q | HE32-535900-02-1 (R0002) / OPERATIONAL CHECK OF RUBBER FLAP DRAIN VALVE AT BULK CARGO COMPARTMENT DOOR FROM OUTSIDE | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.013889
B-LAE | Q | HE32-561200-02-1 (R0002) / LUBRICATE THE COCKPIT SLIDING WINDOW TRACKS | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.016667
B-LAE | Q | HE32-783200-W6-1-01 (R0002) / FUNCTIONAL CHECK OF PRESSURE RELIEF DOOR LATCH TENSION OF NO.1 ENG | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.025
B-LAE | Q | HE32-783200-W6-1-02 (R0002) / FUNCTIONAL CHECK OF PRESSURE RELIEF DOOR LATCH TENSION OF NO.2 ENG | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.025
B-LAE | Q | HE32-ZL-131-01-1 (R0004) / GENERAL VISUAL INSPECTION OF FORWARD CARGO COMPARTMENT (EWIS) | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.044444
B-LAE | Q | HE32-ZL-151-01-1 (R0004) / GENERAL VISUAL INSPECTION OF AFT CARGO COMPARTMENT (AS FAR AS VISIBLE, IF ACT IS INSTALLED) ( | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.044444
B-LAE | Q | HE32-ZL-161-01-1 (R0002) / GENERAL VISUAL INSPECTION OF BULK CARGO COMPARTMENT (EWIS) | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.023611
B-LAE | Q | HE32-ZL-315-01-1 (R0003) / GENERAL VISUAL INSPECTION OF TAIL CONE APU AND ACCESSORY COMPARTMENT (EWIS) | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.019444
B-LAE | Q | HE32-ZL-437-01-4-01 (R0003) / GENERAL VISUAL INSPECTION OF FAN COWL OF NO.1 ENG (EWIS) | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.027778
B-LAE | Q | HE32-ZL-437-01-4-02 (R0003) / GENERAL VISUAL INSPECTION OF FAN COWL OF NO.2 ENG (EWIS) | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.027778
B-LAE | Q | HE32-ZL-734-01-1 (R0002) / GENERAL VISUAL INSPECTION OF MAIN LANDING GEAR MAIN DOORS (EWIS) | D | 340 | 02.Oct.2026 | 2026-10-02 |  | 0 | 1'095 D | 1 | 68 | 0.022222
B-LAD | D | EOA32-36-0012/W1420158 /PERFORM LEAK CHECK ON COMBO SEALS ON A32 SERIES AIRCRAFT PYLON DUCT SL | D | 343 | 05.Oct.2026 | 2026-10-05 | 2026-05-23 | B-LAD-PLN-1C_2026_PT | 1'215 D | 2 | 89 | 0.13889 |  | EOE: the C check plan is correct, ignore the due date alert
B-LAD | Q | HE32-321111-03-1-01 (R0003) / FUNCTIONAL CHECK OF LH MLG TORQUE LINK DAMPER FLUID LEVEL | C | 1'219 | 5'105 | 2026-10-05 |  | 0 | 3'000 | 1 | 59 | 0.0083333
B-LAD | Q | HE32-321111-03-1-02 (R0003) / FUNCTIONAL CHECK OF RH MLG TORQUE LINK DAMPER FLUID LEVEL | C | 1'219 | 5'105 | 2026-10-05 |  | 0 | 3'000 | 1 | 59 | 0.0083333
B-LAE | Q | HE32-351000-08-1 (R0002) / FUNCTIONAL CHECK OF ECAM OXYGEN CYLINDER CONTENTS INDICATION COMPARED WITH CYLINDER PRESSURE | H | 3690:03 | 12763:39 | 2026-10-05 |  | 0 | 6'500 | 1 | 43 | 0.031944
B-LAB | D | EOA32-32-0056/INSPECTION OF HYD LEAKAGE AT NLG SWIVEL SELECTOR UNION FOR A32 SERIES | H | 3707:13 | 16114:40 | 2026-10-06 |  | 0 | 7'500 | 2 | 50 | 0.041667
B-LAA | Q | HE32-215800-01-1 (R0004) / REMOVE CSAS OZONE CONVERTER FOR IN SHOP CLEANING | H | 3709:28 | 19146:02 | 2026-10-07 |  | 0 | 6'000 | 1 | 38 | 0.15833
B-LAD | Q | HE32-272145-01-1 (R0002) / FUNCTIONAL CHECK OF THE TENSION REGULATOR (POINTER WITHIN THE LIMITS) | D | 345 | 07.Oct.2026 | 2026-10-07 |  | 0 | 1'217 D | 1 | 71 | 0.044444
B-LAD | Q | HE32-274142-01-1 (R0002) / FUNCTIONAL CHECK OF POINTER ON TENSION COMPENSATOR (SCALE WITHIN LIMITS) | D | 345 | 07.Oct.2026 | 2026-10-07 |  | 0 | 1'217 D | 1 | 71 | 0.0375
B-LAD | Q | HE32-274451-05-1 (R0002) / DETAILED INSPECTION OF THE UPPER AND LOWER THS-ACTUATOR ATTACHMENTS (PRIMARY AND SECONDARY) | D | 345 | 07.Oct.2026 | 2026-10-07 |  | 0 | 1'217 D | 1 | 71 | 0.023611
B-LAD | Q | HE32-491600-B1-1 (R0004) / DETAILED INSPECTION OF APU AIR INTAKE, DIFFUSER ELBOW, SEALS AND FELT METAL | D | 345 | 07.Oct.2026 | 2026-10-07 |  | 0 | 1'217 D | 1 | 71 | 0.030556
B-LAE | Q | HE32-272400-03-1 (R0001) / LUBRICATE RUDDER HINGE BEARING NO. 6 | D | 346 | 08.Oct.2026 | 2026-10-08 |  | 0 | 730 D | 1 | 52 | 0.088889
B-LAE | Q | HE32-274000-01-1 (R0001) / LUBRICATE THE THS BEARINGS AND ATTACHMENT FITTINGS | D | 346 | 08.Oct.2026 | 2026-10-08 |  | 0 | 730 D | 1 | 52 | 0.089583
B-LAE | Q | HE32-274100-03-1 (R0001) / LUBRICATE THE THS MECHANICAL CONTROL CHAINS AND REAR CABLE (AREA OF TENSION REGULATOR) | D | 346 | 08.Oct.2026 | 2026-10-08 |  | 0 | 730 D | 1 | 52 | 0.2875
B-LAE | Q | HE32-527100-02-1 (R0003) / LUBRICATE THE DOOR WARNING PROXIMITY SWITCH ACTUATING MECHANISM | D | 346 | 08.Oct.2026 | 2026-10-08 |  | 0 | 547 D | 1 | 36 | 0.25
B-LAB | Q | HE32-ZL-147-02-1 (R0002) / GENERAL VISUAL INSPECTION OF MLG-WELL AND HYDRAULIC COMPARTMENT (EWIS) | D | 347 | 09.Oct.2026 | 2026-10-09 |  | 0 | 365 D | 1 | 4 | 0.038889
B-LAB | Q | HE32-ZL-711-01-1 (R0002) / GENERAL VISUAL INSPECTION OF NOSE GEAR AND NOSE GEAR DOORS (EWIS) | D | 347 | 09.Oct.2026 | 2026-10-09 |  | 0 | 365 D | 1 | 4 | 0.023611
B-LAB | Q | HE32-ZL-731-01-1 (R0002) / GENERAL VISUAL INSPECTION OF LH/RH MAIN LANDING GEAR INCLUDING CYLINDER AND SECONDARY DOORS ( | D | 347 | 09.Oct.2026 | 2026-10-09 |  | 0 | 365 D | 1 | 4 | 0.034028
B-LAB | Q | HE32-212141-01-1 (R0002) / DISCARD FILTER ELEMENTS OF RECIRCULATION SYSTEM | H | 3782:31 | 16189:58 | 2026-10-13 |  | 0 | 5'000 | 1 | 24 | 0.088889
B-LAE | Q | HE32-292000-05-1 (R0003) / OPERATIONAL CHECK OF RAM AIR TURBINE (RAT) AUTOMATIC DEPLOYMENT | H | 3800:44 | 12874:20 | 2026-10-15 |  | 0 | 4'000 | 1 | 4 | 0.051389
B-LAD | D | EO-A320-53-1326/FUSELAGE - CENTER FUSELAGE - INSPECT MLG DOOR HINGE FITTING ON KEEL | C | 1'265 | 5'151 | 2026-10-18 |  | 0 | 3'000 | 1 | 57 | 0.70833 |  | EOE: Accomplishment of this EO is acceptable means to HKE AMS
B-LAB | Q | HE32-292000-05-1 (R0003) / OPERATIONAL CHECK OF RAM AIR TURBINE (RAT) AUTOMATIC DEPLOYMENT | H | 3825:45 | 16233:12 | 2026-10-18 |  | 0 | 4'000 | 1 | 4 | 0.051389
B-LAE | Q | HE32-323300-05-2 (R0002) / OPERATIONAL CHECK OF FREE-FALL MECHANICAL CONTROL | H | 3831:00 | 12904:36 | 2026-10-18 |  | 0 | 7'700 | 1 | 50 | 0.25417
B-LAA | V | REPLACE 89794077/C17010551 (CYLINDER ASSY) | D | 358 | 20.Oct.2026 | 2026-10-20 |  | 0 |  | 2 |  | 0.041667 | 89794077 / C17010551
B-LAE | Q | HE32-200001-02-1-01 (R0002) / CHECK TO MAKE SURE THAT CONNECTOR AT LH WING IS CORRECTLY TIGHTENED BY MEASUREMENT OF THE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.19028
B-LAE | Q | HE32-200001-02-1-02 (R0002) / CHECK TO MAKE SURE THAT CONNECTOR AT RH WING IS CORRECTLY TIGHTENED BY MEASUREMENT OF THE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.19028
B-LAE | Q | HE32-200003-01-1 (R0002) / GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON THE HARNESSES 4202VB, 4204VB | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0375
B-LAE | Q | HE32-200003-02-1 (R0002) / GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON THE HARNESSES 4202VB, 4204VB | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.040278
B-LAE | Q | HE32-200003-03-1 (R0002) / GENERAL VISUAL INSPECTION OF ELEMENTS FITTED ON THE HARNESSES 4202VB, 4204VB | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.023611
B-LAE | Q | HE32-200121-03-1 (R0002) / GENERAL VISUAL INSPECTION OF 90VU, 108VU AND 109VU IN THE FORWARD AVIONIC COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.094444
B-LAE | Q | HE32-200121-04-1 (R0002) / DETAILED INSPECTION OF G, E AND P ROUTES IN THE FORWARD AVIONIC COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.058333
B-LAE | Q | HE32-200125-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE LATERAL AVIONIC COMPARTMENT (ONLY IF CONTAMINATED) (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.058333
B-LAE | Q | HE32-200125-05-1 (R0002) / GENERAL VISUAL INSPECTION OF 105VU, 106VU, 103VU, 107VU AND 70VU INSTALLED IN THE LATERAL AVI | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.047222
B-LAE | Q | HE32-200125-06-1 (R0002) / DETAILED INSPECTION OF G, E AND P ROUTES INSTALLED IN THE LATERAL AVIONIC COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.052778
B-LAE | Q | HE32-200127-02-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE REAR AVIONIC COMPARTMENT (ONLY IF CONTAMINATED) (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.094444
B-LAE | Q | HE32-200127-05-1 (R0002) / GENERAL VISUAL INSPECTION OF 63VU, 80VU, 187VU AND 188VU INSTALLED IN THE REAR AVIONIC COMPAR | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.047222
B-LAE | Q | HE32-200127-07-1 (R0002) / DETAILED INSPECTION OF G, E AND P ROUTES INSTALLED IN THE REAR AVIONIC COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.080556
B-LAE | Q | HE32-200131-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE FORWARD CARGO COMPARTMENT (ONLY IF CONTAMINATED) (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.044444
B-LAE | Q | HE32-200133-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE UNDERFLOOR BAY OF FORWARD CARGO COMPARTMENT (ONLY IF CONTAMIN | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.05
B-LAE | Q | HE32-200137-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE BAY BEHIND FWD CARGO COMPARTMENT (ONLY IF CONTAMINATED) (EWIS | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.036111
B-LAE | Q | HE32-200145-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE ZONE UNDER CABIN FLOOR (ONLY IF CONTAMINATED) (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.025
B-LAE | Q | HE32-200151-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE AFT CARGO COMPARTMENT (ONLY IF CONTAMINATED) (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.044444
B-LAE | Q | HE32-200161-01-1 (R0002) / CLEAN THE EWIS INSTALLED IN THE BULK CARGO COMPARTMENT (ONLY IF CONTAMINATED) (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.027778
B-LAE | Q | HE32-200191-01-1 (R0003) / CLEAN THE EWIS INSTALLED IN THE AIR CONDITIONING COMPARTMENT AND FAIRINGS (ONLY IF CONTAMINAT | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.21389
B-LAE | Q | HE32-200211-02-1 (R0002) / CLEAN THE EWIS INSTALLED IN 49VU AND 120VU (ONLY IF CONTAMINATED) (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.055556
B-LAE | Q | HE32-200315-01-1 (R0002) / GENERAL VISUAL INSPECTION OF G AND P ROUTES INSTALLED IN THE TAIL CONE AND APU ACCESSORY COMP | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.019444
B-LAE | Q | HE32-253000-01-1 (R0002) / DETAILED INSPECTION OF ATTACHMENT POINTS | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.025
B-LAE | Q | HE32-262541-01-1 (R0002) / DETAILED INSPECTION OF LAVATORY FIRE EXTINGUISHER FOR SIGNS OF LEAKAGE/DISCHARGE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0083333
B-LAE | Q | HE32-272100-02-1 (R0002) / DETAILED INSPECTION OF THE CONTROL CABLES | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.033333
B-LAE | Q | HE32-272100-05-1 (R0003) / OPERATIONAL TEST OF THE CENTERING SPRING ROD | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.022222
B-LAE | Q | HE32-272100-07-1 (R0003) / DETAILED INSPECTION OF MECHANICAL CONTROL LINKAGE IN FIN | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.019444
B-LAE | Q | HE32-275449-06-1-01 (R0002) / DRAIN AND REFILL FLAP ACTUATOR ASSEMBLIES OF LH WING WITH SEMI-FLUID | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.34444
B-LAE | Q | HE32-275449-06-1-02 (R0002) / DRAIN AND REFILL FLAP ACTUATOR ASSEMBLIES OF RH WING WITH SEMI-FLUID | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.34444
B-LAE | Q | HE32-281800-01-1 (R0002) / FUNCTIONAL CHECK OF TANK VAPOUR SEAL AND VENT DRAIN SYSTEM (SFAR88) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.34444
B-LAE | Q | HE32-281800-02-1 (R0003) / DETAILED INSPECTION OF VAPOUR SEAL (SFAR88) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.098611
B-LAE | Q | HE32-281800-05-1 (R0002) / GENERAL VISUAL INSPECTION OF CENTER TANK FWD CARGO BAY INSULATION BLANKETS (SFAR88) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.019444
B-LAE | Q | HE32-291000-04-1 (R0002) / FUNCTIONAL CHECK OF THE POWER TRANSFER UNIT (PTU) GREEN TO YELLOW | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.016667
B-LAE | Q | HE32-323300-01-1 (R0002) / DETAILED INSPECTION OF FREE-FALL MECHANISM INCLUDING CABLES | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.13333
B-LAE | Q | HE32-323300-04-1 (R0002) / FUNCTIONAL CHECK OF FREE-FALL MECHANISM CABLE TENSION | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.13056
B-LAE | Q | HE32-351351-01-1 (R0002) / FUNCTIONAL CHECK OF LOW PRESSURE SWITCH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0083333
B-LAE | Q | HE32-352000-02-1 (R0002) / FUNCTIONAL CHECK OF AUTOMATIC MASK RELEASE, DETAILED INSPECTION OF MASKS AND VISUAL CHECK OF | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.12222
B-LAE | Q | HE32-361101-01-1-01 (R0003) / REPLACE THE UPPER SEALS OF THE BLEED-AIR PRECOOLER EXCHANGER OF LH PYLON | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.027083
B-LAE | Q | HE32-361101-01-1-02 (R0003) / REPLACE THE UPPER SEALS OF THE BLEED-AIR PRECOOLER EXCHANGER OF RH PYLON | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.027083
B-LAE | Q | HE32-361200-01-1 (R0002) / OPERATIONAL CHECK OF CROSSBLEED VALVE IN MANUAL MODE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0125
B-LAE | Q | HE32-384142-01-1 (R0002) / DISCARD SYSTEM FILTER ELEMENT | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.013889
B-LAE | Q | HE32-384242-01-1 (R0004) / DISCARD COMPRESSOR OUTLET FILTER ELEMENT | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.013889
B-LAE | Q | HE32-523100-01-1 (R0002) / FUNCTIONAL CHECK OF FORWARD CARGO COMPARTMENT DOOR (INCLUDES LOCKING MECHANISM, INTERLOCK MEC | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.048611
B-LAE | Q | HE32-523200-01-1 (R0002) / FUNCTIONAL CHECK OF AFT CARGO COMPARTMENT DOOR (INCLUDES LOCKING MECHANISM, INTERLOCK MECHANI | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0375
B-LAE | Q | HE32-525111-02-1 (R0002) / OPERATIONAL CHECK OF ALL PRESSURE SENSING CHANNELS FOR RAPID DECOMPRESSION | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0125
B-LAE | Q | HE32-525111-04-1 (R0002) / OPERATIONAL CHECK OF DOOR OPENING IN CASE OF POWER OFF | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0041667
B-LAE | Q | HE32-525111-05-1 (R0002) / OPERATIONAL CHECK OF DOOR OPENING BY USING THE EMERGENCY CODE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0041667
B-LAE | Q | HE32-530000-01-1 (R0002) / REMOVE AND DETAILED INSPECTION OF PISTON TYPE DRAIN VALVES IN LOWER FUSELAGE SHELL | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.090278
B-LAE | Q | HE32-531102-01-1 (R0003) / DETAILED INSPECTION OF FORWARD PASSENGER/CREW DOOR FRAME, UPPER CORNERS, EXTERNAL SURFACE, LH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.043056
B-LAE | Q | HE32-531163-01-1 (R0003) / GENERAL VISUAL INSPECTION OF INTERNAL STRUCTURE AROUND FWD PASSENGER/CREW DR, ABOVE CABIN FLO | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.13889
B-LAE | Q | HE32-531164-01-1 (R0002) / DETAILED INSPECTION OF FUSELAGE INTERNAL STRUCTURE, BELOW FORWARD PASSENGER/CREW DOOR AND CAB | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.088889
B-LAE | Q | HE32-531166-01-2 (R0002) / DETAILED INSPECTION OF FWD PASSENGER/CREW DOOR CUTOUT LOWER CORNERS INTERNAL STRUCTURE ABOVE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.13889
B-LAE | Q | HE32-531171-01-1 (R0002) / DETAILED INSPECTION OF NLG, SECONDARY DOOR HINGE SUPPORTS ON FUSELAGE, LH/RH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.038889
B-LAE | Q | HE32-531181-01-1 (R0003) / DETAILED INSPECTION OF FUSELAGE INTERNAL STRUCTURE FROM FR 15 TO FR 21, BETWEEN STRINGER 23 A | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.030556
B-LAE | Q | HE32-531189-01-2 (R0002) / DETAILED INSPECTION OF CABIN FLOOR STRUCTURE BETWEEN FR 12 AND FR 21 | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.75556
B-LAE | Q | HE32-532137-03-1 (R0001) / DETAILED INSPECTION OF FORWARD CARGO DOOR CUTOUT PANELS, UPPER AND LOWER CORNERS, EXTERNAL SU | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.025
B-LAE | Q | HE32-532180-01-2 (R0002) / DETAILED INSPECTION OF FUSELAGE INTERNAL STRUCTURE INCLUDING FORWARD FACE OF PRESSURE BULKHEA | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.21111
B-LAE | Q | HE32-533136-01-1 (R0003) / GENERAL VISUAL INSPECTION OF MLG BAY | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.022222
B-LAE | Q | HE32-534107-01-1 (R0002) / DETAILED INSPECTION OF FUSELAGE INTERNAL STRUCTURE, BETWEEN FR 46 AND FR 65, INCLUDING AFT FA | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.33333
B-LAE | Q | HE32-534132-02-1 (R0001) / DETAILED INSPECTION OF AFT PASSENGER/CREW DOOR CUTOUT, UPPER CORNERS, INCLUDING SKIN AND INTE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0055556
B-LAE | Q | HE32-534135-01-4 (R0003) / GENERAL VISUAL INSPECTION OF INTERNAL STRUCTURE AROUND AFT PASSENGER/CREW DOOR CUTOUT ABOVE C | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.088889
B-LAE | Q | HE32-534143-01-3 (R0002) / DETAILED INSPECTION OF AFT PASSENGER/CREW DOOR CUTOUT LOWER CORNERS INTERNAL STRUCTURE, ABOVE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.033333
B-LAE | Q | HE32-534144-01-1 (R0002) / DETAILED INSPECTION OF FUSELAGE INTERNAL STRUCTURE, BELOW CABIN FLOOR PANELS INCLUDING FLOOR | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.088889
B-LAE | Q | HE32-534147-01-1 (R0002) / DETAILED INSPECTION OF THE CABIN FLOOR STRUCTURE, BELOW AND 0.5M AROUND GALLEYS AND TOILETS | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.5
B-LAE | Q | HE32-534148-01-1 (R0003) / GENERAL VISUAL INSPECTION OF FUSELAGE EXTERNAL SURFACE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.39167
B-LAE | Q | HE32-534159-02-1 (R0001) / DETAILED INSPECTION OF AFT CARGO DOOR CUTOUT UPPER AND LOWER CORNERS, EXTERNAL SURFACE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.036111
B-LAE | Q | HE32-534171-02-1 (R0001) / DETAILED INSPECTION OF FUSELAGE SKIN OF BULK CARGO DOOR CUTOUT AT UPPER CORNERS | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.011111
B-LAE | Q | HE32-534195-01-2 (R0003) / DETAILED INSPECTION OF CABIN FLOOR STRUCTURE AND STRUCTURE BELOW AFT ENTRANCE AREA, BETWEEN F | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.033333
B-LAE | Q | HE32-535101-01-1 (R0002) / DETAILED INSPECTION OF REAR PRESSURE BULKHEAD COMPLETE AFT FACE AND FUSELAGE INTERNAL STRUCTU | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.10278
B-LAE | Q | HE32-545207-01-1-01 (R0003) / DETAILED INSPECTION OF PYLON-TO-ENGINE AFT ATTACHMENT FITTINGS, OF LH PYLON | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.076389
B-LAE | Q | HE32-545207-01-1-02 (R0003) / DETAILED INSPECTION OF PYLON-TO-ENGINE AFT ATTACHMENT FITTINGS, OF RH PYLON | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.076389
B-LAE | Q | HE32-545900-W2-1-01 (R0003) / OPERATIONAL CHECK OF LH PYLON DRAINAGE SYSTEM IN ZONE C | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.10833
B-LAE | Q | HE32-545900-W2-1-02 (R0003) / OPERATIONAL CHECK OF RH PYLON DRAINAGE SYSTEM IN ZONE C | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.10694
B-LAE | Q | HE32-551010-01-1 (R0002) / DETAILED INSPECTION OF HORIZONTAL STABILIZER, REAR SUPPORT FITTINGS, UPPER AND LOWER ATTACH F | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.044444
B-LAE | Q | HE32-551020-01-1 (R0003) / DETAILED INSPECTION OF HORIZONTAL STABILIZER, HINGE FITTINGS, SUPPORT RIBS AND ACTUATOR FITTI | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.23611
B-LAE | Q | HE32-552002-01-1 (R0002) / DETAILED INSPECTION OF ELEVATOR, HINGE FITTINGS AND ACTUATOR FITTINGS, LH/RH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.17778
B-LAE | Q | HE32-553004-01-1 (R0002) / DETAILED INSPECTION OF VERTICAL STABILIZER, ATTACH FITTINGS, INCLUDING LOAD INTRODUCTION AREA | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.047222
B-LAE | Q | HE32-553005-01-1 (R0002) / DETAILED INSPECTION OF RUDDER HINGE ARM 1, 2, 3, 4 AND 5 AND FIN ACTUATOR FITTINGS (ACTUATOR | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.022222
B-LAE | Q | HE32-553006-01-2 (R0002) / DETAILED INSPECTION OF RUDDER HINGE ARM 6 AND 7 | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.095833
B-LAE | Q | HE32-554003-02-1 (R0003) / SPECIAL DETAILED INSPECTION (US) OF RUDDER SIDE PANELS, IN AREA OF RUDDER BEARINGS, IN THE BO | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.063889
B-LAE | Q | HE32-554005-01-1 (R0002) / DETAILED INSPECTION OF RUDDER ATTACH FITTING 1, 2, 3, 4 AND 5 AND RUDDER ACTUATOR ATTACH FITT | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.022222
B-LAE | Q | HE32-554006-01-1 (R0002) / DETAILED INSPECTION OF RUDDER ATTACH FITTING 6 AND 7 | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.045833
B-LAE | Q | HE32-554008-01-1 (R0002) / SPECIAL DETAILED INSPECTION OF HONEYCOMB CORE OF THE RUDDER SIDE PANEL, LH/RH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.10417
B-LAE | Q | HE32-554009-01-1 (R0002) / SPECIAL DETAILED INSPECTION (ELCH TEST) OF THE BONDING LAYERS BETWEEN RUDDER SIDE PANEL HONEY | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.19444
B-LAE | Q | HE32-562101-01-1 (R0002) / DETAILED INSPECTION OF CABIN WINDOW PANES, INCLUDING WINDOW PANES IN DOORS | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.52778
B-LAE | Q | HE32-571122-01-1 (R0002) / DETAILED INSPECTION OF CENTER WING BOX, REAR SPAR AFT FACE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.125
B-LAE | Q | HE32-571157-01-1 (R0003) / DETAILED INSPECTION OF CENTER WING BOX, UPPER SKIN UPPER SURFACE AND BEAMS INCLUDING FRAME FE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.125
B-LAE | Q | HE32-572049-03-1-01 (R0003) / DETAILED INSPECTION OF LH OUTER WING, BOTTOM SKIN, LOWER SURFACE AT DRAIN HOLES FOR TRACK | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.010417
B-LAE | Q | HE32-572049-03-1-02 (R0003) / DETAILED INSPECTION OF RH OUTER WING, BOTTOM SKIN, LOWER SURFACE AT DRAIN HOLES FOR TRACK | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.010417
B-LAE | Q | HE32-572153-01-1-01 (R0003) / DETAILED INSPECTION OF LH OUTER WING, BOTTOM SKIN LOWER SURFACE, AT DRAIN HOLES FOR SLAT C | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0048611
B-LAE | Q | HE32-572153-01-1-02 (R0003) / DETAILED INSPECTION OF RH OUTER WING, BOTTOM SKIN LOWER SURFACE, AT DRAIN HOLES FOR SLAT C | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0048611
B-LAE | Q | HE32-572651-01-2-01 (R0003) / DETAILED INSPECTION OF LH OUTER WING, REAR-SPAR-AFT-FACE RETRACTION-JACK-FITTING | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0041667
B-LAE | Q | HE32-572651-01-2-02 (R0003) / DETAILED INSPECTION OF RH OUTER WING, REAR-SPAR-AFT-FACE RETRACTION-JACK-FITTING | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0041667
B-LAE | Q | HE32-574206-01-1-01 (R0002) / DETAILED INSPECTION OF LH SLAT 1, PINION AND RACK TEETH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.019444
B-LAE | Q | HE32-574206-01-1-02 (R0002) / DETAILED INSPECTION OF RH SLAT 1, PINION AND RACK TEETH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.019444
B-LAE | Q | HE32-574306-01-2-01 (R0002) / DETAILED INSPECTION OF LH SLAT 2, PINION AND RACK TEETH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0125
B-LAE | Q | HE32-574306-01-2-02 (R0002) / DETAILED INSPECTION OF RH SLAT 2, PINION AND RACK TEETH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0125
B-LAE | Q | HE32-574406-01-1-01 (R0002) / DETAILED INSPECTION OF LH SLAT 3, PINION AND RACK TEETH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0125
B-LAE | Q | HE32-574406-01-1-02 (R0002) / DETAILED INSPECTION OF RH SLAT 3, PINION AND RACK TEETH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0125
B-LAE | Q | HE32-574506-01-1-01 (R0002) / DETAILED INSPECTION OF LH SLAT 4, PINION AND RACK TEETH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.023611
B-LAE | Q | HE32-574506-01-1-02 (R0002) / DETAILED INSPECTION OF RH SLAT 4, PINION AND RACK TEETH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.023611
B-LAE | Q | HE32-574606-01-1-01 (R0002) / DETAILED INSPECTION OF LH SLAT 5, PINION AND RACK TEETH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.020833
B-LAE | Q | HE32-574606-01-1-02 (R0002) / DETAILED INSPECTION OF RH SLAT 5, PINION AND RACK TEETH | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.020833
B-LAE | Q | HE32-575151-03-1-01 (R0001) / GENERAL VISUAL INSPECTION OF LH OUTER WING, TRAILING EDGE, FALSE REAR SPAR, FORWARD AND AF | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | 2'191 D | 1 | 83 | 0.034028
B-LAE | Q | HE32-575151-03-1-02 (R0001) / GENERAL VISUAL INSPECTION OF RH OUTER WING, TRAILING EDGE, FALSE REAR SPAR, FORWARD AND AF | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | 2'191 D | 1 | 83 | 0.034028
B-LAE | Q | HE32-575167-01-1-01 (R0003) / DETAILED INSPECTION OF LH OUTER WING, BOTTOM SKIN PANEL NO. 3, UPPER SURFACE, BETWEEN REAR | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0097222
B-LAE | Q | HE32-575167-01-1-02 (R0003) / DETAILED INSPECTION OF RH OUTER WING, BOTTOM SKIN PANEL NO. 3, UPPER SURFACE, BETWEEN REAR | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0097222
B-LAE | Q | HE32-711311-01-1-01 (R0002) / DETAILED INSPECTION OF FAN COWL DOORS HINGES AND SURROUNDING STRUCTURE (150MM AROUND HINGE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.048611
B-LAE | Q | HE32-711311-01-1-02 (R0002) / DETAILED INSPECTION OF FAN COWL DOORS HINGES AND SURROUNDING STRUCTURE (150MM AROUND HINGE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.048611
B-LAE | Q | HE32-711312-01-1-01 (R0002) / DETAILED INSPECTION OF THE FAN COWL DOOR LATCHES AND SURROUNDING STRUCTURE (150MM AROUND L | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.048611
B-LAE | Q | HE32-711312-01-1-02 (R0002) / DETAILED INSPECTION OF THE FAN COWL DOOR LATCHES AND SURROUNDING STRUCTURE (150MM AROUND L | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.048611
B-LAE | Q | HE32-712121-02-1-01 (R0001) / DETAILED INSPECTION OF FORWARD ENGINE MOUNT INSTALLATION EXPOSED SURFACES OF NO.1 ENG | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0375
B-LAE | Q | HE32-712121-02-1-02 (R0001) / DETAILED INSPECTION OF FORWARD ENGINE MOUNT INSTALLATION EXPOSED SURFACES OF NO.2 ENG | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0375
B-LAE | Q | HE32-712221-02-1-01 (R0001) / DETAILED INSPECTION OF AFT ENGINE MOUNT INSTALLATION EXPOSED SURFACES OF NO.1 ENG | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0375
B-LAE | Q | HE32-712221-02-1-02 (R0001) / DETAILED INSPECTION OF AFT ENGINE MOUNT INSTALLATION EXPOSED SURFACES OF NO.2 ENG | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0375
B-LAE | Q | HE32-722102-01-1-01 (R0002) / DETAILED INSPECTION OF NO.1 ENGINE FAN CASE V-GROOVE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.070833
B-LAE | Q | HE32-722102-01-1-02 (R0002) / DETAILED INSPECTION OF NO.2 ENGINE FAN CASE V-GROOVE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.070833
B-LAE | Q | HE32-783216-01-1-01 (R0002) / DETAILED INSPECTION OF THRUST REVERSER V-BLADES OF NO.1 ENG | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.056944
B-LAE | Q | HE32-783216-01-1-02 (R0002) / DETAILED INSPECTION OF THRUST REVERSER V-BLADES OF NO.2 ENG | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.056944
B-LAE | Q | HE32-ZL-110-01-1 (R0002) / GENERAL VISUAL INSPECTION OF RADOME (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.011111
B-LAE | Q | HE32-ZL-121-02-1 (R0002) / GENERAL VISUAL INSPECTION OF FORWARD AVIONIC COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.066667
B-LAE | Q | HE32-ZL-125-02-1 (R0003) / GENERAL VISUAL INSPECTION OF LATERAL AVIONIC COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.041667
B-LAE | Q | HE32-ZL-127-02-2 (R0002) / GENERAL VISUAL INSPECTION OF REAR AVIONIC COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.069444
B-LAE | Q | HE32-ZL-131-02-1 (R0003) / GENERAL VISUAL INSPECTION OF FORWARD CARGO COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.036111
B-LAE | Q | HE32-ZL-133-01-1 (R0004) / GENERAL VISUAL INSPECTION OF UNDERFLOOR BAY OF FWD CARGO COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.05
B-LAE | Q | HE32-ZL-145-01-1 (R0002) / GENERAL VISUAL INSPECTION OF ZONE UNDER CABIN FLOOR (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.13611
B-LAE | Q | HE32-ZL-147-03-1 (R0003) / GENERAL VISUAL INSPECTION OF MLG-WELL AND HYDRAULIC COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.05
B-LAE | Q | HE32-ZL-151-02-3 (R0003) / GENERAL VISUAL INSPECTION OF AFT CARGO COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.091667
B-LAE | Q | HE32-ZL-153-01-1 (R0003) / GENERAL VISUAL INSPECTION OF UNDERFLOOR BAY OF AFT CARGO COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.036111
B-LAE | Q | HE32-ZL-161-02-3 (R0001) / GENERAL VISUAL INSPECTION OF BULK CARGO COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.072222
B-LAE | Q | HE32-ZL-163-01-1 (R0002) / GENERAL VISUAL INSPECTION OF UNDERFLOOR BAY OF BULK CARGO COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.055556
B-LAE | Q | HE32-ZL-171-02-1 (R0003) / GENERAL VISUAL INSPECTION OF AFT CABIN UNDERFLOOR COMPARTMENT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.075
B-LAE | Q | HE32-ZL-191-02-1 (R0004) / GENERAL VISUAL INSPECTION OF AIR CONDITIONING COMPARTMENT AND FAIRINGS (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.26944
B-LAE | Q | HE32-ZL-193-01-1 (R0003) / GENERAL VISUAL INSPECTION OF UPPER WING FAIRING SLIDE STOWAGE (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.025
B-LAE | Q | HE32-ZL-197-01-1 (R0002) / GENERAL VISUAL INSPECTION OF REAR FAIRING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.14028
B-LAE | Q | HE32-ZL-211-01-1 (R0002) / GENERAL VISUAL INSPECTION OF COCKPIT (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.05
B-LAE | Q | HE32-ZL-317-01-1 (R0002) / GENERAL VISUAL INSPECTION OF TAIL CONE APU EXHAUST AREA (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.011111
B-LAE | Q | HE32-ZL-325-02-3 (R0001) / GENERAL VISUAL INSPECTION OF VERTICAL STABILIZER TRAILING EDGE (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.077778
B-LAE | Q | HE32-ZL-331-01-1 (R0002) / GENERAL VISUAL INSPECTION OF TRIMMABLE HORIZONTAL STABILIZER LEADING EDGE (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.175
B-LAE | Q | HE32-ZL-334-02-1 (R0002) / GENERAL VISUAL INSPECTION OF TRIMMABLE HORIZONTAL STABILIZER TRAILING EDGE (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.24167
B-LAE | Q | HE32-ZL-433-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF AIR INTAKE OF NO.1 ENG (EWIS) (INTERNAL AREA AS FAR AS VISIBL | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.075694
B-LAE | Q | HE32-ZL-433-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF AIR INTAKE OF NO.2 ENG (EWIS) (INTERNAL AREA AS FAR AS VISIBL | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.050694
B-LAE | Q | HE32-ZL-473-01-1-01 (R0003) / GENERAL VISUAL INSPECTION OF AFT PYLON FAIRING OF LH PYLON (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.048611
B-LAE | Q | HE32-ZL-473-01-1-02 (R0003) / GENERAL VISUAL INSPECTION OF AFT PYLON FAIRING OF RH PYLON (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.048611
B-LAE | Q | HE32-ZL-521-01-1-01 (R0003) / GENERAL VISUAL INSPECTION OF STRUCTURE OF INBOARD FIXED LEADING-EDGE OF LH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.050694
B-LAE | Q | HE32-ZL-521-01-1-02 (R0003) / GENERAL VISUAL INSPECTION OF STRUCTURE OF INBOARD FIXED LEADING-EDGE OF RH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.050694
B-LAE | Q | HE32-ZL-522-01-2-01 (R0002) / GENERAL VISUAL INSPECTION OF STRUCTURE OF OUTBOARD FIXED LEADING-EDGE OF LH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.092361
B-LAE | Q | HE32-ZL-522-01-2-02 (R0002) / GENERAL VISUAL INSPECTION OF STRUCTURE OF OUTBOARD FIXED LEADING-EDGE OF RH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.092361
B-LAE | Q | HE32-ZL-531-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING OF LH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.044444
B-LAE | Q | HE32-ZL-531-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 2 AND FAIRING OF RH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.044444
B-LAE | Q | HE32-ZL-532-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING OF LH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.044444
B-LAE | Q | HE32-ZL-532-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 3 AND FAIRING OF RH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.044444
B-LAE | Q | HE32-ZL-533-02-1-01 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING OF LH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.044444
B-LAE | Q | HE32-ZL-533-02-1-02 (R0003) / GENERAL VISUAL INSPECTION OF FLAP TRACK NO 4 AND FAIRING OF RH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.044444
B-LAE | Q | HE32-ZL-534-01-3-01 (R0003) / GENERAL VISUAL INSPECTION OF LH WING TIP (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.055556
B-LAE | Q | HE32-ZL-534-01-3-02 (R0003) / GENERAL VISUAL INSPECTION OF RH WING TIP (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.055556
B-LAE | Q | HE32-ZL-540-01-1-01 (R0003) / GENERAL VISUAL INSPECTION OF WING FUEL TANK OF LH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.058333
B-LAE | Q | HE32-ZL-540-01-1-02 (R0003) / GENERAL VISUAL INSPECTION OF WING FUEL TANK OF RH WING (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.055556
B-LAE | Q | HE32-ZL-571-02-1 (R0002) / GENERAL VISUAL INSPECTION OF MLG BAY (EWIS) | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.038889
B-LAE | Q | HE32-ZL-811-01-1 (R0002) / GENERAL VISUAL INSPECTION OF FWD AVIONICS COMPARTMENT DOOR (EWIS) (INCLUDING EXTERNAL SURFACE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.0083333
B-LAE | Q | HE32-ZL-812-01-1 (R0002) / GENERAL VISUAL INSPECTION OF LATERAL AVIONICS COMPARTMENT DOORS (EWIS) (INCLUDING EXTERNAL SU | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.022222
B-LAE | Q | HE32-ZL-824-01-1 (R0002) / GENERAL VISUAL INSPECTION OF REAR AVIONIC COMPARTMENT DOOR (EWIS) (INCLUDING EXTERNAL SURFACE | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.011111
B-LAE | Q | HE32-ZL-833-02-1 (R0002) / GENERAL VISUAL INSPECTION OF FWD AND AFT OVERWING EMERGENCY EXIT HATCHES (INCLUDING DOOR SURR | D | 361 | 23.Oct.2026 | 2026-10-23 |  | 0 | Thr. 2'191 D | 1 | 83 | 0.094444
B-LAE | Q | HE32-292000-04-1 (R0003) / OPERATIONAL CHECK OF RAT MANUAL DEPLOYMENT AND FUNCTIONAL CHECK OF RAT USING GROUND TEST UNIT | H | 3896:47 | 12970:23 | 2026-10-24 |  | 0 | 4'000 | 1 | 2 | 0.38611
B-LAD | Q | HE32-470000-01-1 (R0004) / REPLACE D-ULPA FILTER ELEMENT | H | 3908:21 | 13838:26 | 2026-10-25 |  | 0 | 7'000 | 1 | 44 | 0.091667
B-LAB | D | EO-A320-23-1B10/INTRODUCE CIDS DIRECTOR PART NUMBER (P/N) Z014H010035C AND | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.27083 | Z014H000333B / 014H00012105
B-LAB | D | EO-A320-23-1B10/INTRODUCE CIDS DIRECTOR PART NUMBER (P/N) Z014H010035C AND | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.27083 | Z014H000333B / 014H00012864
B-LAA | D | EO-A320-23-1B10/INTRODUCE CIDS DIRECTOR PART NUMBER (P/N) Z014H010035C AND | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.27083 | Z014H000333B / 014H00010699
B-LAA | D | EO-A320-23-1B10/INTRODUCE CIDS DIRECTOR PART NUMBER (P/N) Z014H010035C AND | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.27083 | Z014H000333B / 014H00010700
B-LAC | D | EO-A320-23-1B10/INTRODUCE CIDS DIRECTOR PART NUMBER (P/N) Z014H010035C AND | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.27083 | Z014H000333B / 014H00006033
B-LAC | D | EO-A320-23-1B10/INTRODUCE CIDS DIRECTOR PART NUMBER (P/N) Z014H010035C AND | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.27083 | Z014H000333B / 014H00010933
B-LAE | D | EOD-25-0040/[LEASE RETURN] REMOVE ADDITIONAL FIRE CONTAINMENT BAG IN CABIN | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.020833 |  | EOE info: Don not plan unless EOL input
B-LAD | D | EOD-25-0040/[LEASE RETURN] REMOVE ADDITIONAL FIRE CONTAINMENT BAG IN CABIN | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.020833 |  | EOE info: Don not plan unless EOL input
B-LAA | D | EOD-25-0040/[LEASE RETURN] REMOVE ADDITIONAL FIRE CONTAINMENT BAG IN CABIN | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.020833 |  | EOE info: Don not plan unless EOL input
B-LAC | D | EOD-25-0040/[LEASE RETURN] REMOVE ADDITIONAL FIRE CONTAINMENT BAG IN CABIN | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.020833 |  | EOE info: Don not plan unless EOL input
B-LAB | D | EOD-25-0040/[LEASE RETURN] REMOVE ADDITIONAL FIRE CONTAINMENT BAG IN CABIN | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.020833 |  | EOE info: Don not plan unless EOL input
B-LAE | D | EOD-51-0003/REPAINT NEW EXTERIOR LIVERY AND EXTERIOR MARKINGS ON A320NEO (ABRASION | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 1900-04-15 16:00
B-LAD | D | EOD-51-0003/REPAINT NEW EXTERIOR LIVERY AND EXTERIOR MARKINGS ON A320NEO (ABRASION | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 1900-04-15 16:00
B-LAC | D | EOD-51-0003/REPAINT NEW EXTERIOR LIVERY AND EXTERIOR MARKINGS ON A320NEO (ABRASION | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 1900-04-15 16:00 |  | EOE: planned in chemical way , do not assign this EO
B-LAC | D | EOI-32-0002/REPLACEMENT OF BRAKE FAN ASSY GROMMET | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.020833
B-LAE | D | EOI-32-0002/REPLACEMENT OF BRAKE FAN ASSY GROMMET | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.020833
B-LAB | D | EOI-32-0002/REPLACEMENT OF BRAKE FAN ASSY GROMMET | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.020833
B-LAA | D | EOI-32-0002/REPLACEMENT OF BRAKE FAN ASSY GROMMET | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.020833
B-LAD | D | EOI-32-0002/REPLACEMENT OF BRAKE FAN ASSY GROMMET | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  | 0.020833
B-LAC | Q | HE32-11-NRME-010 (R0001) / CHECK OF THE EXTERNAL MARKS OF THE PASSENGER DOORS AND EMERGENCY EXITS | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.041667
B-LAE | Q | HE32-11-NRME-010 (R0001) / CHECK OF THE EXTERNAL MARKS OF THE PASSENGER DOORS AND EMERGENCY EXITS | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.041667
B-LAD | Q | HE32-11-NRME-010 (R0001) / CHECK OF THE EXTERNAL MARKS OF THE PASSENGER DOORS AND EMERGENCY EXITS | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.041667
B-LAB | Q | HE32-11-NRME-010 (R0001) / CHECK OF THE EXTERNAL MARKS OF THE PASSENGER DOORS AND EMERGENCY EXITS | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.041667
B-LAA | Q | HE32-11-NRME-010 (R0001) / CHECK OF THE EXTERNAL MARKS OF THE PASSENGER DOORS AND EMERGENCY EXITS | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.041667
B-LAA | Q | HE32-242100-22-1-01 (R0001) / OPERATIONAL CHECK OF THE DISCONNECT AND RECONNECT FUNCTION OF NO.1 IDG | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.036806
B-LAB | Q | HE32-242100-22-1-01 (R0001) / OPERATIONAL CHECK OF THE DISCONNECT AND RECONNECT FUNCTION OF NO.1 IDG | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.036806
B-LAD | Q | HE32-242100-22-1-01 (R0001) / OPERATIONAL CHECK OF THE DISCONNECT AND RECONNECT FUNCTION OF NO.1 IDG | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.036806
B-LAE | Q | HE32-242100-22-1-01 (R0001) / OPERATIONAL CHECK OF THE DISCONNECT AND RECONNECT FUNCTION OF NO.1 IDG | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.036806
B-LAC | Q | HE32-242100-22-1-01 (R0001) / OPERATIONAL CHECK OF THE DISCONNECT AND RECONNECT FUNCTION OF NO.1 IDG | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.036806
B-LAB | Q | HE32-242100-22-1-02 (R0001) / OPERATIONAL CHECK OF THE DISCONNECT AND RECONNECT FUNCTION OF NO.2 IDG | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.036806
B-LAA | Q | HE32-242100-22-1-02 (R0001) / OPERATIONAL CHECK OF THE DISCONNECT AND RECONNECT FUNCTION OF NO.2 IDG | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.036806
B-LAD | Q | HE32-242100-22-1-02 (R0001) / OPERATIONAL CHECK OF THE DISCONNECT AND RECONNECT FUNCTION OF NO.2 IDG | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.036806
B-LAE | Q | HE32-242100-22-1-02 (R0001) / OPERATIONAL CHECK OF THE DISCONNECT AND RECONNECT FUNCTION OF NO.2 IDG | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.036806
B-LAC | Q | HE32-242100-22-1-02 (R0001) / OPERATIONAL CHECK OF THE DISCONNECT AND RECONNECT FUNCTION OF NO.2 IDG | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.036806
B-LAB | Q | HE32-256241-04-1 (R0001) / OPERATIONAL CHECK OF FWD AND AFT PAX/CREW DOOR ESCAPE SLIDE/RAFT DEPLOYMENT | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.67083
B-LAD | Q | HE32-256241-04-1 (R0001) / OPERATIONAL CHECK OF FWD AND AFT PAX/CREW DOOR ESCAPE SLIDE/RAFT DEPLOYMENT | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.67083
B-LAE | Q | HE32-256241-04-1 (R0001) / OPERATIONAL CHECK OF FWD AND AFT PAX/CREW DOOR ESCAPE SLIDE/RAFT DEPLOYMENT | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.67083
B-LAA | Q | HE32-256241-04-1 (R0001) / OPERATIONAL CHECK OF FWD AND AFT PAX/CREW DOOR ESCAPE SLIDE/RAFT DEPLOYMENT | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.67083
B-LAC | Q | HE32-256241-04-1 (R0001) / OPERATIONAL CHECK OF FWD AND AFT PAX/CREW DOOR ESCAPE SLIDE/RAFT DEPLOYMENT | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.67083
B-LAA | Q | HE32-256242-03-1 (R0003) / OPERATIONAL CHECK OF OFF WING EMERGENCY EXIT ESCAPE SLIDE DEPLOYMENT | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.50278
B-LAD | Q | HE32-256242-03-1 (R0003) / OPERATIONAL CHECK OF OFF WING EMERGENCY EXIT ESCAPE SLIDE DEPLOYMENT | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.50278
B-LAE | Q | HE32-256242-03-1 (R0003) / OPERATIONAL CHECK OF OFF WING EMERGENCY EXIT ESCAPE SLIDE DEPLOYMENT | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.50278
B-LAC | Q | HE32-256242-03-1 (R0003) / OPERATIONAL CHECK OF OFF WING EMERGENCY EXIT ESCAPE SLIDE DEPLOYMENT | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.50278
B-LAD | Q | HE32-291000-15-1-1 (R0003) / ANALYZE HYDRAULIC FLUID (WORK AFTER HYDRAULIC FLUID ANALYSIS) | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.047222
B-LAB | Q | HE32-291000-15-1-1 (R0003) / ANALYZE HYDRAULIC FLUID (WORK AFTER HYDRAULIC FLUID ANALYSIS) | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.047222
B-LAE | Q | HE32-291000-15-1-1 (R0003) / ANALYZE HYDRAULIC FLUID (WORK AFTER HYDRAULIC FLUID ANALYSIS) | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.047222
B-LAC | Q | HE32-291000-15-1-1 (R0003) / ANALYZE HYDRAULIC FLUID (WORK AFTER HYDRAULIC FLUID ANALYSIS) | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.047222
B-LAC | Q | HE32-341300-11-1A (R0002) / CLEAN THE PITOT PROBE 1 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAB | Q | HE32-341300-11-1A (R0002) / CLEAN THE PITOT PROBE 1 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAA | Q | HE32-341300-11-1A (R0002) / CLEAN THE PITOT PROBE 1 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAD | Q | HE32-341300-11-1A (R0002) / CLEAN THE PITOT PROBE 1 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAE | Q | HE32-341300-11-1A (R0002) / CLEAN THE PITOT PROBE 1 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAA | Q | HE32-341300-11-1B (R0002) / CLEAN THE PITOT PROBE 2 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAE | Q | HE32-341300-11-1B (R0002) / CLEAN THE PITOT PROBE 2 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAD | Q | HE32-341300-11-1B (R0002) / CLEAN THE PITOT PROBE 2 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAB | Q | HE32-341300-11-1B (R0002) / CLEAN THE PITOT PROBE 2 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAD | Q | HE32-341300-11-1C (R0002) / CLEAN THE PITOT PROBE 3 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAA | Q | HE32-341300-11-1C (R0002) / CLEAN THE PITOT PROBE 3 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAE | Q | HE32-341300-11-1C (R0002) / CLEAN THE PITOT PROBE 3 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAC | Q | HE32-341300-11-1C (R0002) / CLEAN THE PITOT PROBE 3 | D | 1471649 |  | 1517606 |  | 0 |  | 1 |  | 0.053472
B-LAC | D | PW1000G-C-72-00-0205-00A-930A/ENGINE - GEARBOX ASSEMBLY, ANGLE - INSPECTION OF THE ANGLE GEARBOX | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P772359
B-LAE | D | PW1000G-C-72-00-0205-00A-930A/ENGINE - GEARBOX ASSEMBLY, ANGLE - INSPECTION OF THE ANGLE GEARBOX | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P772226
B-LAE | D | PW1000G-C-72-00-0205-00A-930A/ENGINE - GEARBOX ASSEMBLY, ANGLE - INSPECTION OF THE ANGLE GEARBOX | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P772225
B-LAA | D | PW1000G-C-72-00-0205-00A-930A/ENGINE - GEARBOX ASSEMBLY, ANGLE - INSPECTION OF THE ANGLE GEARBOX | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P771230
B-LAA | D | PW1000G-C-72-00-0205-00A-930A/ENGINE - GEARBOX ASSEMBLY, ANGLE - INSPECTION OF THE ANGLE GEARBOX | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P770440
B-LAD | D | PW1000G-C-72-00-0205-00A-930A/ENGINE - GEARBOX ASSEMBLY, ANGLE - INSPECTION OF THE ANGLE GEARBOX | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P770277
B-LAB | D | PW1000G-C-72-00-0205-00A-930A/ENGINE - GEARBOX ASSEMBLY, ANGLE - INSPECTION OF THE ANGLE GEARBOX | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P770220
B-LAB | D | PW1000G-C-72-00-0205-00A-930A/ENGINE - GEARBOX ASSEMBLY, ANGLE - INSPECTION OF THE ANGLE GEARBOX | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P770214
B-LAE | D | PW1100G-A-72-00-0236-00A-930A/REPLACE THE OLD MAIN GEARBOX OIL SUPPLY TUBE ASSEMBLY (LP35) WITH A | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P772225
B-LAA | D | PW1100G-A-72-00-0236-00A-930A/REPLACE THE OLD MAIN GEARBOX OIL SUPPLY TUBE ASSEMBLY (LP35) WITH A | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P771230
B-LAA | D | PW1100G-A-72-00-0236-00A-930A/REPLACE THE OLD MAIN GEARBOX OIL SUPPLY TUBE ASSEMBLY (LP35) WITH A | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P770440
B-LAD | D | PW1100G-A-72-00-0236-00A-930A/REPLACE THE OLD MAIN GEARBOX OIL SUPPLY TUBE ASSEMBLY (LP35) WITH A | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P770277
B-LAB | D | PW1100G-A-72-00-0236-00A-930A/REPLACE THE OLD MAIN GEARBOX OIL SUPPLY TUBE ASSEMBLY (LP35) WITH A | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P770220
B-LAB | D | PW1100G-A-72-00-0236-00A-930A/REPLACE THE OLD MAIN GEARBOX OIL SUPPLY TUBE ASSEMBLY (LP35) WITH A | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P770214
B-LAC | D | PW1100G-A-72-00-0236-00A-930A/REPLACE THE OLD MAIN GEARBOX OIL SUPPLY TUBE ASSEMBLY (LP35) WITH A | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P772359
B-LAE | D | PW1100G-A-72-00-0236-00A-930A/REPLACE THE OLD MAIN GEARBOX OIL SUPPLY TUBE ASSEMBLY (LP35) WITH A | D | 1471649 |  | 1517606 |  | 0 |  | 2 |  |  | PW1127GA-JM / P772226

## Data Dictionary
中文 | [5 empty] | English.ver
列名 | 中文含义 | 数据格式示例 | 行业术语解释 | 算法中是否使用 | 用途说明 | Column Name | Description | Data Type / Example | Usage in Genetic Algorithm | Notes
A/C | 飞机编号 | B-1234, A320-001 | A/C = Aircraft（飞机），唯一标识单架飞机，用于区分不同飞机的维修任务 | ❌ 否 | 辅助分类字段，算法按 “任务” 调度，不按 “飞机” 分组，故不参与计算 | A/C | Aircraft registration number (unique aircraft ID) | String: B-LAE, B-LAB | Not used | Unique identifier for individual aircraft; not used in scheduling logic
Type | 飞机型号 | B737-800, A321neo | 飞机的具体型号，不同型号的维修任务类型 / 工时可能不同，但本算法已通过工时归一化处理 | ❌ 否 | 辅助信息字段，不影响调度间隔计算，仅用于数据分类参考 | Type | Aircraft variant/type code | String: D, Q, V | Not used | Aircraft configuration category; for reference only
Event/Description | 维修任务编号 / 描述 | TASK-001, Engine Oil Change | 任务的唯一编号 + 具体维修内容（如 “发动机换油”“航电系统检测”） | ✅ 是 | 算法中用于标识任务唯一性，确保 1110 个任务不重复 | Event/Description | Unique maintenance task ID + detailed work description | String: Maintenance task name + code | Used | Unique task ID for tracking 1110 maintenance tasks
Dimension（日期单位） | 时间维度单位 | Day, Month | 定义后续 “Interval”“To go”“Expected” 列的时间单位（本数据中均为 “Day”，即天） | ✅ 是 | 关键辅助字段！算法需确认间隔单位为 “天”，才能统一计算维修间隔利用率 | Dimension | Time unit for interval and scheduling metrics | String: D (Day), H (Hour) | Used | Defines unit for Interval, To go, and Expected; mostly Day
To go（还剩多少时间） | 距离任务到期的剩余时间 | 30, 45 | 基于 “Dimension” 单位（天），表示当前到任务必须完成的剩余天数 | ❌ 否 | 动态时间字段（随当前日期变化），算法按 “固定间隔调度”，不依赖到期时间 | To go | Remaining time until task deadline (per Dimension unit) | Numeric: 2, 35, 142 | Not used | Dynamic remaining time; fixed-interval scheduling does not rely on it
Due at | 任务到期日期 | 2024-12-31, 180 | 任务必须完成的截止日期（可能为具体日期或 “Dimension” 单位下的数值） | ❌ 否 | 同 “To go”，属于动态截止时间，算法核心是 “间隔优化”，不依赖到期日 | Due at | Official deadline / due date for task completion | Date / Numeric: 29.Oct.2025 | Not used | Hard deadline; GA optimizes interval compliance, not deadline chasing
Expected（同一单位日期） | 预计完成日期 | 2024-12-25, 175 | 计划完成任务的日期（基于 “Dimension” 单位），通常早于 “Due at” | ❌ 否 | 计划参考字段，不影响调度间隔的计算逻辑 | Expected | Planned completion date (same unit as Dimension) | Date / Numeric: 10/29/25 | Not used | Preliminary planning date; not used in optimization
Interval | 最大维修间隔（天） | 120, 180, N/A | 制造商规定的该任务两次维修的最大间隔（天），超过会影响飞机安全性 | ✅ 是 | 核心约束字段！算法中用于计算 “维修间隔利用率”（实际间隔 / 最大间隔），需满足 80%-90% | Interval | Maximum allowed maintenance interval (manufacturer-specified) | Numeric: 40, 150, 800 | Used | Core constraint: computes utilization = actual gap / max interval
Yield | 维修合格率 / 收益率 | 98%, 0.95 | 该类维修任务的成功完成率（百分比或小数），反映维修可靠性 | ❌ 否 | 质量评估字段，不影响调度间隔的优化，仅用于结果分析参考 | Yield | Task completion yield / reliability rate | Numeric: 75, 99, 100 | Not used | Quality indicator; for analysis only
EstMH (All) | 预估总工时（Man-Hours） | 01:30, 0 days 02:15:00, 3.5 | 完成该任务所需的总工时，混合格式需标准化为 “小时数”（如 01:30→1.5 小时） | ✅ 是 | 核心计算字段！用于计算 “日均成本”（工时 / 间隔）和 “每日人力负载”，需满足≤20 工时 / 天 | EstMH (All) | Estimated total man-hours required to complete the task | Time / String: 1:30, 7:08, 5:30 | Used | Core input: calculates daily manpower load & operational cost
Rotable | 是否为可轮换部件 | Yes, No, Y, N | Rotable = Rotable Component（可轮换部件），指可拆换、维修后重复使用的部件 | ❌ 否 | 部件属性字段，不影响调度间隔计算，仅用于任务分类（如发动机部件、航电部件） | Rotable | Indicates if task involves a rotable (reusable) component | String: Part number / blank | Not used | Component logistics reference; not used in scheduling
Remarks | 备注信息 | Priority: High, Special Tool | 任务的特殊说明（如 “高优先级”“需专用工具”），补充任务执行要求 | ❌ 否 | 执行辅助字段，不参与算法计算，仅用于实际维修执行参考 | Remarks | Special instructions, operational notes, or engine side (L/R/Both) | String: LH ENG, RH ENG, MUST DO | Not used | Execution guidance; no impact on GA optimization
左右 engines | 发动机位置（左 / 右） | Left, Right, Both | 若任务与发动机相关，标识涉及的发动机位置（左发、右发、双发） | ❌ 否 | 位置信息字段，不影响调度间隔，仅用于维修时的位置确认